## Sheet1
Project 1 | 22
[6 empty] | triangular | [7 empty] | right-triangular | [7 empty] | left-triangular
activity | immediate predecessor | a | m | b | rand | start time | duration | finish time | trial | project duration | success | average duration | success rate | start time | duration | finish time | trial | project duration | success | average duration | success rate | start time | duration | finish time | trial | project duration | success | average duration | success rate
A |  | 2 | 3 | 4 | 0.75388 | 0 | 3.2984 | 3.2984 |  | 21.8518 | 1 | 21.9294 | 0.512 | 0 | 3.1335 | 3.1335 |  | 24.1732 | 0 | 24.2029 | 0.039 | 0 | 3.0831 | 3.0831 |  | 19.7508 | 1 | 19.7074 | 0.961
B | A | 2 | 3.5 | 4 | 0.38553 | 3.2984 | 3.0755 | 6.3739 | 1 | 22.7075 | 0 |  |  | 3.1335 | 3.902 | 7.0355 | 1 | 24.5615 | 0 |  |  | 3.0831 | 3.3597 | 6.4428 | 1 | 19.3765 | 1
C | B | 1 | 2 | 2.5 | 0.24753 | 6.3739 | 1.6093 | 7.9832 | 2 | 21.016 | 1 |  |  | 7.0355 | 2.3556 | 9.391 | 2 | 25.8743 | 0 |  |  | 6.4428 | 1.5958 | 8.0386 | 2 | 17.8253 | 1
D | B,C | 5 | 6 | 8 | 0.58623 | 7.9832 | 6.4244 | 14.4076 | 3 | 21.6959 | 1 |  |  | 9.391 | 5.5948 | 14.9859 | 3 | 24.9832 | 0 |  |  | 8.0386 | 5.0253 | 13.0639 | 3 | 17.5195 | 1
E | D | 2 | 3 | 4.5 | 0.45229 | 14.4076 | 3.0669 | 17.4744 | 4 | 21.5251 | 1 |  |  | 14.9859 | 4.3909 | 19.3768 | 4 | 23.1893 | 0 |  |  | 13.0639 | 3.4549 | 16.5188 | 4 | 19.2563 | 1
F | E | 3 | 4 | 5 | 0.80615 | 17.4744 | 4.3773 | 21.8518 | 5 | 22.3413 | 0 |  |  | 19.3768 | 4.7964 | 24.1732 | 5 | 24.9206 | 0 |  |  | 16.5188 | 3.0536 | 19.5724 | 5 | 20.3107 | 1
G | E | 1 | 1.25 | 1.5 | 0.20265 | 17.4744 | 1.1592 | 18.6336 | 6 | 21.439 | 1 |  |  | 19.3768 | 1.479 | 20.8558 | 6 | 23.6572 | 0 |  |  | 16.5188 | 1.0437 | 17.5624 | 6 | 18.625 | 1
H | G | 2 | 3 | 4 | 0.27585 | 18.6336 | 2.7428 | 21.3763 | 7 | 21.0703 | 1 |  |  | 20.8558 | 2.8137 | 23.6695 | 7 | 23.9987 | 0 |  |  | 17.5624 | 2.1884 | 19.7508 | 7 | 19.9331 | 1
I | F,H | 0 | 0 | 0 | 0.84054 | 21.8518 | 0 | 21.8518 | 8 | 20.8582 | 1 |  |  | 24.1732 | 0 | 24.1732 | 8 | 25.1392 | 0 |  |  | 19.7508 | 0 | 19.7508 | 8 | 19.3533 | 1
[9 empty] | 9 | 21.1137 | 1 | [5 empty] | 9 | 23.8765 | 0 | [5 empty] | 9 | 17.799 | 1
[9 empty] | 10 | 21.3779 | 1 | [5 empty] | 10 | 22.656 | 0 | [5 empty] | 10 | 20.103 | 1
[9 empty] | 11 | 19.9468 | 1 | [5 empty] | 11 | 22.9253 | 0 | [5 empty] | 11 | 20.8628 | 1
[9 empty] | 12 | 22.1907 | 0 | [5 empty] | 12 | 23.3723 | 0 | [5 empty] | 12 | 18.3821 | 1
[9 empty] | 13 | 24.7098 | 0 | [5 empty] | 13 | 24.9945 | 0 | [5 empty] | 13 | 18.2992 | 1
[9 empty] | 14 | 23.2483 | 0 | [5 empty] | 14 | 23.6675 | 0 | [5 empty] | 14 | 20.1118 | 1
[9 empty] | 15 | 23.0982 | 0 | [5 empty] | 15 | 26.4257 | 0 | [5 empty] | 15 | 22.5899 | 0
[9 empty] | 16 | 19.3386 | 1 | [5 empty] | 16 | 25.1803 | 0 | [5 empty] | 16 | 20.9831 | 1
[9 empty] | 17 | 21.5195 | 1 | [5 empty] | 17 | 23.8934 | 0 | [5 empty] | 17 | 18.9795 | 1
[9 empty] | 18 | 22.13 | 0 | [5 empty] | 18 | 24.3125 | 0 | [5 empty] | 18 | 21.7487 | 1
[9 empty] | 19 | 21.6138 | 1 | [5 empty] | 19 | 24.7463 | 0 | [5 empty] | 19 | 20.7224 | 1
[9 empty] | 20 | 22.0797 | 0 | [5 empty] | 20 | 24.5951 | 0 | [5 empty] | 20 | 18.367 | 1
[9 empty] | 21 | 21.8652 | 1 | [5 empty] | 21 | 23.7294 | 0 | [5 empty] | 21 | 19.7847 | 1
[9 empty] | 22 | 23.0242 | 0 | [5 empty] | 22 | 22.9096 | 0 | [5 empty] | 22 | 19.4287 | 1
[9 empty] | 23 | 24.2484 | 0 | [5 empty] | 23 | 25.2592 | 0 | [5 empty] | 23 | 20.1696 | 1
[9 empty] | 24 | 19.5667 | 1 | [5 empty] | 24 | 23.808 | 0 | [5 empty] | 24 | 18.597 | 1
[9 empty] | 25 | 22.0607 | 0 | [5 empty] | 25 | 23.3041 | 0 | [5 empty] | 25 | 21.2122 | 1
[9 empty] | 26 | 19.8053 | 1 | [5 empty] | 26 | 24.6158 | 0 | [5 empty] | 26 | 19.1641 | 1
[9 empty] | 27 | 21.0037 | 1 | [5 empty] | 27 | 24.8993 | 0 | [5 empty] | 27 | 21.1617 | 1
[9 empty] | 28 | 20.2921 | 1 | [5 empty] | 28 | 23.7913 | 0 | [5 empty] | 28 | 17.4649 | 1
[9 empty] | 29 | 22.0453 | 0 | [5 empty] | 29 | 24.2044 | 0 | [5 empty] | 29 | 19.7442 | 1
[9 empty] | 30 | 22.5831 | 0 | [5 empty] | 30 | 25.7058 | 0 | [5 empty] | 30 | 18.9934 | 1
[9 empty] | 31 | 21.8687 | 1 | [5 empty] | 31 | 22.3379 | 0 | [5 empty] | 31 | 20.8799 | 1
[9 empty] | 32 | 21.1131 | 1 | [5 empty] | 32 | 25.3202 | 0 | [5 empty] | 32 | 20.8803 | 1
[9 empty] | 33 | 20.1745 | 1 | [5 empty] | 33 | 26.2542 | 0 | [5 empty] | 33 | 20.2223 | 1
[9 empty] | 34 | 20.7399 | 1 | [5 empty] | 34 | 25.0721 | 0 | [5 empty] | 34 | 19.5978 | 1
[9 empty] | 35 | 23.1219 | 0 | [5 empty] | 35 | 25.0417 | 0 | [5 empty] | 35 | 17.6955 | 1
[9 empty] | 36 | 21.8836 | 1 | [5 empty] | 36 | 22.5861 | 0 | [5 empty] | 36 | 20.451 | 1
[9 empty] | 37 | 21.7726 | 1 | [5 empty] | 37 | 24.5479 | 0 | [5 empty] | 37 | 18.4874 | 1
[9 empty] | 38 | 20.5767 | 1 | [5 empty] | 38 | 23.1188 | 0 | [5 empty] | 38 | 19.4651 | 1
[9 empty] | 39 | 21.8306 | 1 | [5 empty] | 39 | 26.064 | 0 | [5 empty] | 39 | 19.8909 | 1
[9 empty] | 40 | 22.3498 | 0 | [5 empty] | 40 | 23.5057 | 0 | [5 empty] | 40 | 20.6495 | 1
[9 empty] | 41 | 22.4384 | 0 | [5 empty] | 41 | 21.5975 | 1 | [5 empty] | 41 | 19.1739 | 1
[9 empty] | 42 | 23.4226 | 0 | [5 empty] | 42 | 22.644 | 0 | [5 empty] | 42 | 19.9921 | 1
[9 empty] | 43 | 20.7884 | 1 | [5 empty] | 43 | 26.1454 | 0 | [5 empty] | 43 | 19.7297 | 1
[9 empty] | 44 | 22.251 | 0 | [5 empty] | 44 | 24.7212 | 0 | [5 empty] | 44 | 21.4916 | 1
[9 empty] | 45 | 22.4203 | 0 | [5 empty] | 45 | 25.5598 | 0 | [5 empty] | 45 | 21.9633 | 1
[9 empty] | 46 | 21.1177 | 1 | [5 empty] | 46 | 24.3522 | 0 | [5 empty] | 46 | 19.9365 | 1
[9 empty] | 47 | 22.2026 | 0 | [5 empty] | 47 | 25.1608 | 0 | [5 empty] | 47 | 20.4444 | 1
[9 empty] | 48 | 23.2422 | 0 | [5 empty] | 48 | 25.4658 | 0 | [5 empty] | 48 | 20.7923 | 1
[9 empty] | 49 | 22.9374 | 0 | [5 empty] | 49 | 21.4621 | 1 | [5 empty] | 49 | 19.1304 | 1
[9 empty] | 50 | 19.9812 | 1 | [5 empty] | 50 | 25.1216 | 0 | [5 empty] | 50 | 20.0669 | 1
[9 empty] | 51 | 22.6219 | 0 | [5 empty] | 51 | 23.3152 | 0 | [5 empty] | 51 | 18.2205 | 1
[9 empty] | 52 | 20.1986 | 1 | [5 empty] | 52 | 21.4377 | 1 | [5 empty] | 52 | 18.0848 | 1
[9 empty] | 53 | 22.0089 | 0 | [5 empty] | 53 | 24.4484 | 0 | [5 empty] | 53 | 19.8384 | 1
[9 empty] | 54 | 21.631 | 1 | [5 empty] | 54 | 25.2836 | 0 | [5 empty] | 54 | 22.8559 | 0
[9 empty] | 55 | 21.023 | 1 | [5 empty] | 55 | 21.5207 | 1 | [5 empty] | 55 | 20.5152 | 1
[9 empty] | 56 | 22.663 | 0 | [5 empty] | 56 | 25.1176 | 0 | [5 empty] | 56 | 19.9277 | 1
[9 empty] | 57 | 22.9321 | 0 | [5 empty] | 57 | 25.0265 | 0 | [5 empty] | 57 | 21.6188 | 1
[9 empty] | 58 | 22.4929 | 0 | [5 empty] | 58 | 22.6735 | 0 | [5 empty] | 58 | 19.9037 | 1
[9 empty] | 59 | 21.0859 | 1 | [5 empty] | 59 | 22.7256 | 0 | [5 empty] | 59 | 20.6132 | 1
[9 empty] | 60 | 22.5146 | 0 | [5 empty] | 60 | 25.0258 | 0 | [5 empty] | 60 | 20.7976 | 1
[9 empty] | 61 | 23.989 | 0 | [5 empty] | 61 | 24.5028 | 0 | [5 empty] | 61 | 20.0686 | 1
[9 empty] | 62 | 20.8602 | 1 | [5 empty] | 62 | 23.241 | 0 | [5 empty] | 62 | 19.5396 | 1
[9 empty] | 63 | 22.5143 | 0 | [5 empty] | 63 | 25.6252 | 0 | [5 empty] | 63 | 19.0207 | 1
[9 empty] | 64 | 20.6361 | 1 | [5 empty] | 64 | 22.3979 | 0 | [5 empty] | 64 | 20.3217 | 1
[9 empty] | 65 | 22.5716 | 0 | [5 empty] | 65 | 21.5493 | 1 | [5 empty] | 65 | 20.2505 | 1
[9 empty] | 66 | 24.1958 | 0 | [5 empty] | 66 | 23.9829 | 0 | [5 empty] | 66 | 18.8221 | 1
[9 empty] | 67 | 22.4875 | 0 | [5 empty] | 67 | 24.3109 | 0 | [5 empty] | 67 | 18.4856 | 1
[9 empty] | 68 | 20.4012 | 1 | [5 empty] | 68 | 24.4741 | 0 | [5 empty] | 68 | 20.3943 | 1
[9 empty] | 69 | 24.5002 | 0 | [5 empty] | 69 | 23.9229 | 0 | [5 empty] | 69 | 20.127 | 1
[9 empty] | 70 | 24.2523 | 0 | [5 empty] | 70 | 23.2771 | 0 | [5 empty] | 70 | 17.7335 | 1
[9 empty] | 71 | 20.1269 | 1 | [5 empty] | 71 | 23.6853 | 0 | [5 empty] | 71 | 19.3369 | 1
[9 empty] | 72 | 21.2623 | 1 | [5 empty] | 72 | 25.5613 | 0 | [5 empty] | 72 | 20.0055 | 1
[9 empty] | 73 | 22.0922 | 0 | [5 empty] | 73 | 24.5202 | 0 | [5 empty] | 73 | 18.8368 | 1
[9 empty] | 74 | 18.8422 | 1 | [5 empty] | 74 | 23.6982 | 0 | [5 empty] | 74 | 21.6726 | 1
[9 empty] | 75 | 22.2806 | 0 | [5 empty] | 75 | 22.7891 | 0 | [5 empty] | 75 | 19.0219 | 1
[9 empty] | 76 | 22.356 | 0 | [5 empty] | 76 | 24.1179 | 0 | [5 empty] | 76 | 19.425 | 1
[9 empty] | 77 | 21.5371 | 1 | [5 empty] | 77 | 25.1512 | 0 | [5 empty] | 77 | 20.5727 | 1
[9 empty] | 78 | 22.2276 | 0 | [5 empty] | 78 | 24.0085 | 0 | [5 empty] | 78 | 18.7984 | 1
[9 empty] | 79 | 21.1132 | 1 | [5 empty] | 79 | 25.8814 | 0 | [5 empty] | 79 | 20.8503 | 1
[9 empty] | 80 | 24.4246 | 0 | [5 empty] | 80 | 24.6052 | 0 | [5 empty] | 80 | 20.0185 | 1
[9 empty] | 81 | 20.5439 | 1 | [5 empty] | 81 | 23.8262 | 0 | [5 empty] | 81 | 18.0472 | 1
[9 empty] | 82 | 22.5984 | 0 | [5 empty] | 82 | 24.9941 | 0 | [5 empty] | 82 | 20.3922 | 1
[9 empty] | 83 | 22.021 | 0 | [5 empty] | 83 | 24.0872 | 0 | [5 empty] | 83 | 19.3631 | 1
[9 empty] | 84 | 22.192 | 0 | [5 empty] | 84 | 24.393 | 0 | [5 empty] | 84 | 21.3749 | 1
[9 empty] | 85 | 20.4204 | 1 | [5 empty] | 85 | 24.5694 | 0 | [5 empty] | 85 | 19.7151 | 1
[9 empty] | 86 | 22.2719 | 0 | [5 empty] | 86 | 26.2484 | 0 | [5 empty] | 86 | 21.7774 | 1
[9 empty] | 87 | 23.0533 | 0 | [5 empty] | 87 | 25.5458 | 0 | [5 empty] | 87 | 18.5063 | 1
[9 empty] | 88 | 21.4598 | 1 | [5 empty] | 88 | 24.9317 | 0 | [5 empty] | 88 | 20.5845 | 1
[9 empty] | 89 | 21.7552 | 1 | [5 empty] | 89 | 23.5214 | 0 | [5 empty] | 89 | 17.5269 | 1
[9 empty] | 90 | 21.4891 | 1 | [5 empty] | 90 | 24.9355 | 0 | [5 empty] | 90 | 18.0131 | 1
[9 empty] | 91 | 21.6113 | 1 | [5 empty] | 91 | 24.1988 | 0 | [5 empty] | 91 | 20.1782 | 1
[9 empty] | 92 | 20.8774 | 1 | [5 empty] | 92 | 22.2598 | 0 | [5 empty] | 92 | 20.0444 | 1
[9 empty] | 93 | 20.063 | 1 | [5 empty] | 93 | 25.2578 | 0 | [5 empty] | 93 | 21.2644 | 1
[9 empty] | 94 | 21.145 | 1 | [5 empty] | 94 | 23.6447 | 0 | [5 empty] | 94 | 18.6063 | 1
[9 empty] | 95 | 22.4878 | 0 | [5 empty] | 95 | 21.7688 | 1 | [5 empty] | 95 | 18.4655 | 1
[9 empty] | 96 | 21.6557 | 1 | [5 empty] | 96 | 25.8915 | 0 | [5 empty] | 96 | 20.5262 | 1
[9 empty] | 97 | 24.9285 | 0 | [5 empty] | 97 | 25.8324 | 0 | [5 empty] | 97 | 19.9489 | 1
[9 empty] | 98 | 21.6274 | 1 | [5 empty] | 98 | 24.6305 | 0 | [5 empty] | 98 | 17.812 | 1
[9 empty] | 99 | 21.6671 | 1 | [5 empty] | 99 | 22.5122 | 0 | [5 empty] | 99 | 20.7166 | 1
[9 empty] | 100 | 21.4914 | 1 | [5 empty] | 100 | 22.8377 | 0 | [5 empty] | 100 | 20.6769 | 1
[9 empty] | 101 | 22.6847 | 0 | [5 empty] | 101 | 25.682 | 0 | [5 empty] | 101 | 17.4635 | 1
[9 empty] | 102 | 21.8868 | 1 | [5 empty] | 102 | 23.1658 | 0 | [5 empty] | 102 | 20.1132 | 1
[9 empty] | 103 | 23.1588 | 0 | [5 empty] | 103 | 25.4727 | 0 | [5 empty] | 103 | 19.7245 | 1
[9 empty] | 104 | 20.4502 | 1 | [5 empty] | 104 | 23.9308 | 0 | [5 empty] | 104 | 21.441 | 1
[9 empty] | 105 | 21.5905 | 1 | [5 empty] | 105 | 25.2846 | 0 | [5 empty] | 105 | 20.3175 | 1
[9 empty] | 106 | 22.7776 | 0 | [5 empty] | 106 | 26.0477 | 0 | [5 empty] | 106 | 17.5944 | 1
[9 empty] | 107 | 22.7053 | 0 | [5 empty] | 107 | 24.4567 | 0 | [5 empty] | 107 | 17.5406 | 1
[9 empty] | 108 | 19.8953 | 1 | [5 empty] | 108 | 21.871 | 1 | [5 empty] | 108 | 20.248 | 1
[9 empty] | 109 | 25.3463 | 0 | [5 empty] | 109 | 21.5104 | 1 | [5 empty] | 109 | 18.6686 | 1
[9 empty] | 110 | 22.4778 | 0 | [5 empty] | 110 | 23.3009 | 0 | [5 empty] | 110 | 18.8875 | 1
[9 empty] | 111 | 21.0301 | 1 | [5 empty] | 111 | 25.8865 | 0 | [5 empty] | 111 | 20.9172 | 1
[9 empty] | 112 | 22.1786 | 0 | [5 empty] | 112 | 23.8251 | 0 | [5 empty] | 112 | 19.466 | 1
[9 empty] | 113 | 21.9281 | 1 | [5 empty] | 113 | 23.495 | 0 | [5 empty] | 113 | 20.6794 | 1
[9 empty] | 114 | 21.6929 | 1 | [5 empty] | 114 | 23.6386 | 0 | [5 empty] | 114 | 19.4632 | 1
[9 empty] | 115 | 21.9404 | 1 | [5 empty] | 115 | 24.5337 | 0 | [5 empty] | 115 | 20.7255 | 1
[9 empty] | 116 | 20.4367 | 1 | [5 empty] | 116 | 24.9024 | 0 | [5 empty] | 116 | 19.0236 | 1
[9 empty] | 117 | 19.825 | 1 | [5 empty] | 117 | 25.8188 | 0 | [5 empty] | 117 | 18.0062 | 1
[9 empty] | 118 | 22.2692 | 0 | [5 empty] | 118 | 25.4681 | 0 | [5 empty] | 118 | 20.9868 | 1
[9 empty] | 119 | 20.4181 | 1 | [5 empty] | 119 | 25.3954 | 0 | [5 empty] | 119 | 20.0732 | 1
[9 empty] | 120 | 22.4571 | 0 | [5 empty] | 120 | 25.1659 | 0 | [5 empty] | 120 | 21.3725 | 1
[9 empty] | 121 | 22.3108 | 0 | [5 empty] | 121 | 23.9867 | 0 | [5 empty] | 121 | 19.1055 | 1
[9 empty] | 122 | 21.3523 | 1 | [5 empty] | 122 | 24.8959 | 0 | [5 empty] | 122 | 17.959 | 1
[9 empty] | 123 | 22.0848 | 0 | [5 empty] | 123 | 23.7287 | 0 | [5 empty] | 123 | 19.0871 | 1
[9 empty] | 124 | 22.1261 | 0 | [5 empty] | 124 | 23.0182 | 0 | [5 empty] | 124 | 18.7626 | 1
[9 empty] | 125 | 21.7993 | 1 | [5 empty] | 125 | 26.1363 | 0 | [5 empty] | 125 | 20.5067 | 1
[9 empty] | 126 | 23.6711 | 0 | [5 empty] | 126 | 24.5285 | 0 | [5 empty] | 126 | 17.8995 | 1
[9 empty] | 127 | 22.2645 | 0 | [5 empty] | 127 | 23.5657 | 0 | [5 empty] | 127 | 19.0297 | 1
[9 empty] | 128 | 20.309 | 1 | [5 empty] | 128 | 24.8206 | 0 | [5 empty] | 128 | 19.6809 | 1
[9 empty] | 129 | 20.5812 | 1 | [5 empty] | 129 | 24.0767 | 0 | [5 empty] | 129 | 24.5503 | 0
[9 empty] | 130 | 22.5222 | 0 | [5 empty] | 130 | 23.6372 | 0 | [5 empty] | 130 | 18.8764 | 1
[9 empty] | 131 | 22.0259 | 0 | [5 empty] | 131 | 23.5069 | 0 | [5 empty] | 131 | 19.1071 | 1
[9 empty] | 132 | 21.5117 | 1 | [5 empty] | 132 | 25.6392 | 0 | [5 empty] | 132 | 19.4899 | 1
[9 empty] | 133 | 23.3143 | 0 | [5 empty] | 133 | 24.1977 | 0 | [5 empty] | 133 | 21.0322 | 1
[9 empty] | 134 | 20.773 | 1 | [5 empty] | 134 | 23.3491 | 0 | [5 empty] | 134 | 19.2595 | 1
[9 empty] | 135 | 19.855 | 1 | [5 empty] | 135 | 25.4507 | 0 | [5 empty] | 135 | 19.1824 | 1
[9 empty] | 136 | 22.019 | 0 | [5 empty] | 136 | 25.213 | 0 | [5 empty] | 136 | 19.4848 | 1
[9 empty] | 137 | 19.6619 | 1 | [5 empty] | 137 | 23.2569 | 0 | [5 empty] | 137 | 17.4119 | 1
[9 empty] | 138 | 22.2739 | 0 | [5 empty] | 138 | 25.9702 | 0 | [5 empty] | 138 | 18.2696 | 1
[9 empty] | 139 | 20.5539 | 1 | [5 empty] | 139 | 24.0195 | 0 | [5 empty] | 139 | 20.1549 | 1
[9 empty] | 140 | 23.3111 | 0 | [5 empty] | 140 | 22.6822 | 0 | [5 empty] | 140 | 19.6946 | 1
[9 empty] | 141 | 22.335 | 0 | [5 empty] | 141 | 24.6465 | 0 | [5 empty] | 141 | 20.0966 | 1
[9 empty] | 142 | 23.3656 | 0 | [5 empty] | 142 | 25.4505 | 0 | [5 empty] | 142 | 20.5255 | 1
[9 empty] | 143 | 21.9302 | 1 | [5 empty] | 143 | 26.1606 | 0 | [5 empty] | 143 | 18.7147 | 1
[9 empty] | 144 | 20.026 | 1 | [5 empty] | 144 | 26.024 | 0 | [5 empty] | 144 | 18.1414 | 1
[9 empty] | 145 | 23.0734 | 0 | [5 empty] | 145 | 21.2693 | 1 | [5 empty] | 145 | 18.1799 | 1
[9 empty] | 146 | 21.7729 | 1 | [5 empty] | 146 | 24.5971 | 0 | [5 empty] | 146 | 19.1284 | 1
[9 empty] | 147 | 21.4865 | 1 | [5 empty] | 147 | 26.2439 | 0 | [5 empty] | 147 | 21.0673 | 1
[9 empty] | 148 | 24.2363 | 0 | [5 empty] | 148 | 23.4468 | 0 | [5 empty] | 148 | 21.2261 | 1
[9 empty] | 149 | 22.354 | 0 | [5 empty] | 149 | 24.4484 | 0 | [5 empty] | 149 | 20.15 | 1
[9 empty] | 150 | 22.2086 | 0 | [5 empty] | 150 | 24.1517 | 0 | [5 empty] | 150 | 19.336 | 1
[9 empty] | 151 | 21.9585 | 1 | [5 empty] | 151 | 25.301 | 0 | [5 empty] | 151 | 22.0486 | 0
[9 empty] | 152 | 22.41 | 0 | [5 empty] | 152 | 25.1185 | 0 | [5 empty] | 152 | 18.7947 | 1
[9 empty] | 153 | 23.0121 | 0 | [5 empty] | 153 | 25.6732 | 0 | [5 empty] | 153 | 18.9173 | 1
[9 empty] | 154 | 21.5181 | 1 | [5 empty] | 154 | 23.6325 | 0 | [5 empty] | 154 | 21.1311 | 1
[9 empty] | 155 | 21.3465 | 1 | [5 empty] | 155 | 22.8346 | 0 | [5 empty] | 155 | 19.1781 | 1
[9 empty] | 156 | 23.6843 | 0 | [5 empty] | 156 | 24.6493 | 0 | [5 empty] | 156 | 20.0602 | 1
[9 empty] | 157 | 21.51 | 1 | [5 empty] | 157 | 26.7829 | 0 | [5 empty] | 157 | 19.7689 | 1
[9 empty] | 158 | 21.4131 | 1 | [5 empty] | 158 | 26.1843 | 0 | [5 empty] | 158 | 19.7006 | 1
[9 empty] | 159 | 23.7572 | 0 | [5 empty] | 159 | 25.2068 | 0 | [5 empty] | 159 | 20.6551 | 1
[9 empty] | 160 | 21.8716 | 1 | [5 empty] | 160 | 24.6688 | 0 | [5 empty] | 160 | 18.8611 | 1
[9 empty] | 161 | 21.5661 | 1 | [5 empty] | 161 | 24.8665 | 0 | [5 empty] | 161 | 19.7428 | 1
[9 empty] | 162 | 21.4429 | 1 | [5 empty] | 162 | 24.8835 | 0 | [5 empty] | 162 | 18.4537 | 1
[9 empty] | 163 | 20.8403 | 1 | [5 empty] | 163 | 22.7149 | 0 | [5 empty] | 163 | 18.578 | 1
[9 empty] | 164 | 21.0663 | 1 | [5 empty] | 164 | 21.9793 | 1 | [5 empty] | 164 | 19.586 | 1
[9 empty] | 165 | 24.2067 | 0 | [5 empty] | 165 | 23.7011 | 0 | [5 empty] | 165 | 18.0578 | 1
[9 empty] | 166 | 21.2627 | 1 | [5 empty] | 166 | 24.3887 | 0 | [5 empty] | 166 | 20.5278 | 1
[9 empty] | 167 | 21.3402 | 1 | [5 empty] | 167 | 24.4002 | 0 | [5 empty] | 167 | 22.0268 | 0
[9 empty] | 168 | 21.1612 | 1 | [5 empty] | 168 | 25.0419 | 0 | [5 empty] | 168 | 19.9695 | 1
[9 empty] | 169 | 20.705 | 1 | [5 empty] | 169 | 23.6313 | 0 | [5 empty] | 169 | 21.2707 | 1
[9 empty] | 170 | 22.4359 | 0 | [5 empty] | 170 | 25.9975 | 0 | [5 empty] | 170 | 19.8411 | 1
[9 empty] | 171 | 21.5349 | 1 | [5 empty] | 171 | 22.3551 | 0 | [5 empty] | 171 | 18.0662 | 1
[9 empty] | 172 | 20.3171 | 1 | [5 empty] | 172 | 24.4887 | 0 | [5 empty] | 172 | 19.2026 | 1
[9 empty] | 173 | 23.4417 | 0 | [5 empty] | 173 | 23.6448 | 0 | [5 empty] | 173 | 19.788 | 1
[9 empty] | 174 | 21.8405 | 1 | [5 empty] | 174 | 23.3585 | 0 | [5 empty] | 174 | 18.6966 | 1
[9 empty] | 175 | 20.4891 | 1 | [5 empty] | 175 | 25.1448 | 0 | [5 empty] | 175 | 22.1881 | 0
[9 empty] | 176 | 22.8744 | 0 | [5 empty] | 176 | 24.5926 | 0 | [5 empty] | 176 | 18.9241 | 1
[9 empty] | 177 | 23.5647 | 0 | [5 empty] | 177 | 23.0122 | 0 | [5 empty] | 177 | 18.6582 | 1
[9 empty] | 178 | 21.8072 | 1 | [5 empty] | 178 | 26.4145 | 0 | [5 empty] | 178 | 19.3962 | 1
[9 empty] | 179 | 20.7388 | 1 | [5 empty] | 179 | 24.5613 | 0 | [5 empty] | 179 | 19.73 | 1
[9 empty] | 180 | 21.9522 | 1 | [5 empty] | 180 | 22.2511 | 0 | [5 empty] | 180 | 19.151 | 1
[9 empty] | 181 | 24.6119 | 0 | [5 empty] | 181 | 24.4974 | 0 | [5 empty] | 181 | 20.2544 | 1
[9 empty] | 182 | 21.8412 | 1 | [5 empty] | 182 | 25.0601 | 0 | [5 empty] | 182 | 20.4083 | 1
[9 empty] | 183 | 22.7232 | 0 | [5 empty] | 183 | 23.8257 | 0 | [5 empty] | 183 | 20.757 | 1
[9 empty] | 184 | 22.9125 | 0 | [5 empty] | 184 | 23.2894 | 0 | [5 empty] | 184 | 21.7032 | 1
[9 empty] | 185 | 22.4537 | 0 | [5 empty] | 185 | 21.7388 | 1 | [5 empty] | 185 | 19.2967 | 1
[9 empty] | 186 | 22.3902 | 0 | [5 empty] | 186 | 23.1201 | 0 | [5 empty] | 186 | 19.7901 | 1
[9 empty] | 187 | 22.115 | 0 | [5 empty] | 187 | 26.1201 | 0 | [5 empty] | 187 | 18.4353 | 1
[9 empty] | 188 | 22.2547 | 0 | [5 empty] | 188 | 24.4219 | 0 | [5 empty] | 188 | 18.2014 | 1
[9 empty] | 189 | 19.7382 | 1 | [5 empty] | 189 | 24.7521 | 0 | [5 empty] | 189 | 17.5199 | 1
[9 empty] | 190 | 20.7016 | 1 | [5 empty] | 190 | 24.8628 | 0 | [5 empty] | 190 | 20.0468 | 1
[9 empty] | 191 | 21.448 | 1 | [5 empty] | 191 | 24.4313 | 0 | [5 empty] | 191 | 19.1148 | 1
[9 empty] | 192 | 23.5374 | 0 | [5 empty] | 192 | 23.082 | 0 | [5 empty] | 192 | 20.7373 | 1
[9 empty] | 193 | 21.4565 | 1 | [5 empty] | 193 | 19.5099 | 1 | [5 empty] | 193 | 16.9175 | 1
[9 empty] | 194 | 22.1267 | 0 | [5 empty] | 194 | 24.6321 | 0 | [5 empty] | 194 | 18.0351 | 1
[9 empty] | 195 | 20.3107 | 1 | [5 empty] | 195 | 22.833 | 0 | [5 empty] | 195 | 20.5806 | 1
[9 empty] | 196 | 22.4255 | 0 | [5 empty] | 196 | 22.9458 | 0 | [5 empty] | 196 | 20.3557 | 1
[9 empty] | 197 | 23.1344 | 0 | [5 empty] | 197 | 22.8771 | 0 | [5 empty] | 197 | 22.3449 | 0
[9 empty] | 198 | 20.9901 | 1 | [5 empty] | 198 | 26.4849 | 0 | [5 empty] | 198 | 19.2539 | 1
[9 empty] | 199 | 20.9059 | 1 | [5 empty] | 199 | 24.1613 | 0 | [5 empty] | 199 | 19.4323 | 1
[9 empty] | 200 | 21.1698 | 1 | [5 empty] | 200 | 24.6366 | 0 | [5 empty] | 200 | 19.2864 | 1
[9 empty] | 201 | 22.0205 | 0 | [5 empty] | 201 | 24.5324 | 0 | [5 empty] | 201 | 18.9433 | 1
[9 empty] | 202 | 22.0959 | 0 | [5 empty] | 202 | 24.9055 | 0 | [5 empty] | 202 | 23.4385 | 0
[9 empty] | 203 | 21.6296 | 1 | [5 empty] | 203 | 26.1653 | 0 | [5 empty] | 203 | 21.9398 | 1
[9 empty] | 204 | 20.9085 | 1 | [5 empty] | 204 | 25.0029 | 0 | [5 empty] | 204 | 20.123 | 1
[9 empty] | 205 | 23.4404 | 0 | [5 empty] | 205 | 24.7038 | 0 | [5 empty] | 205 | 19.948 | 1
[9 empty] | 206 | 22.0527 | 0 | [5 empty] | 206 | 23.2596 | 0 | [5 empty] | 206 | 18.2985 | 1
[9 empty] | 207 | 21.0713 | 1 | [5 empty] | 207 | 25.8955 | 0 | [5 empty] | 207 | 21.8352 | 1
[9 empty] | 208 | 23.4961 | 0 | [5 empty] | 208 | 24.4681 | 0 | [5 empty] | 208 | 19.713 | 1
[9 empty] | 209 | 22.5945 | 0 | [5 empty] | 209 | 24.0829 | 0 | [5 empty] | 209 | 18.1547 | 1
[9 empty] | 210 | 21.3162 | 1 | [5 empty] | 210 | 23.8574 | 0 | [5 empty] | 210 | 21.0341 | 1
[9 empty] | 211 | 23.3563 | 0 | [5 empty] | 211 | 22.4349 | 0 | [5 empty] | 211 | 19.2786 | 1
[9 empty] | 212 | 21.8773 | 1 | [5 empty] | 212 | 25.7461 | 0 | [5 empty] | 212 | 19.4195 | 1
[9 empty] | 213 | 24.0833 | 0 | [5 empty] | 213 | 22.2475 | 0 | [5 empty] | 213 | 18.3618 | 1
[9 empty] | 214 | 21.1521 | 1 | [5 empty] | 214 | 22.5446 | 0 | [5 empty] | 214 | 18.9945 | 1
[9 empty] | 215 | 23.0071 | 0 | [5 empty] | 215 | 25.5336 | 0 | [5 empty] | 215 | 21.0625 | 1
[9 empty] | 216 | 20.8454 | 1 | [5 empty] | 216 | 25.8291 | 0 | [5 empty] | 216 | 21.2319 | 1
[9 empty] | 217 | 21.5133 | 1 | [5 empty] | 217 | 25.0387 | 0 | [5 empty] | 217 | 20.7814 | 1
[9 empty] | 218 | 21.8369 | 1 | [5 empty] | 218 | 26.542 | 0 | [5 empty] | 218 | 20.0267 | 1
[9 empty] | 219 | 20.4267 | 1 | [5 empty] | 219 | 25.0791 | 0 | [5 empty] | 219 | 19.9568 | 1
[9 empty] | 220 | 22.134 | 0 | [5 empty] | 220 | 24.5155 | 0 | [5 empty] | 220 | 18.6563 | 1
[9 empty] | 221 | 21.7559 | 1 | [5 empty] | 221 | 24.8526 | 0 | [5 empty] | 221 | 20.4554 | 1
[9 empty] | 222 | 20.005 | 1 | [5 empty] | 222 | 23.0723 | 0 | [5 empty] | 222 | 21.3582 | 1
[9 empty] | 223 | 20.1487 | 1 | [5 empty] | 223 | 25.1548 | 0 | [5 empty] | 223 | 17.4386 | 1
[9 empty] | 224 | 23.1671 | 0 | [5 empty] | 224 | 24.6727 | 0 | [5 empty] | 224 | 18.2414 | 1
[9 empty] | 225 | 20.5381 | 1 | [5 empty] | 225 | 25.3317 | 0 | [5 empty] | 225 | 23.1124 | 0
[9 empty] | 226 | 22.1303 | 0 | [5 empty] | 226 | 22.0838 | 0 | [5 empty] | 226 | 20.3925 | 1
[9 empty] | 227 | 22.2119 | 0 | [5 empty] | 227 | 24.3968 | 0 | [5 empty] | 227 | 20.6491 | 1
[9 empty] | 228 | 22.4577 | 0 | [5 empty] | 228 | 24.4051 | 0 | [5 empty] | 228 | 23.4985 | 0
[9 empty] | 229 | 22.855 | 0 | [5 empty] | 229 | 22.9049 | 0 | [5 empty] | 229 | 19.1636 | 1
[9 empty] | 230 | 22.4286 | 0 | [5 empty] | 230 | 25.7578 | 0 | [5 empty] | 230 | 19.3688 | 1
[9 empty] | 231 | 24.1078 | 0 | [5 empty] | 231 | 24.9504 | 0 | [5 empty] | 231 | 20.4078 | 1
[9 empty] | 232 | 22.581 | 0 | [5 empty] | 232 | 22.7516 | 0 | [5 empty] | 232 | 19.516 | 1
[9 empty] | 233 | 20.7547 | 1 | [5 empty] | 233 | 25.9834 | 0 | [5 empty] | 233 | 19.5926 | 1
[9 empty] | 234 | 21.8918 | 1 | [5 empty] | 234 | 23.4519 | 0 | [5 empty] | 234 | 18.8629 | 1
[9 empty] | 235 | 22.297 | 0 | [5 empty] | 235 | 23.7081 | 0 | [5 empty] | 235 | 18.191 | 1
[9 empty] | 236 | 22.1954 | 0 | [5 empty] | 236 | 23.3396 | 0 | [5 empty] | 236 | 19.7504 | 1
[9 empty] | 237 | 19.7317 | 1 | [5 empty] | 237 | 23.6273 | 0 | [5 empty] | 237 | 18.8146 | 1
[9 empty] | 238 | 20.2318 | 1 | [5 empty] | 238 | 23.1733 | 0 | [5 empty] | 238 | 20.6999 | 1
[9 empty] | 239 | 22.8789 | 0 | [5 empty] | 239 | 22.2703 | 0 | [5 empty] | 239 | 20.1034 | 1
[9 empty] | 240 | 23.5237 | 0 | [5 empty] | 240 | 22.4139 | 0 | [5 empty] | 240 | 17.9762 | 1
[9 empty] | 241 | 22.0631 | 0 | [5 empty] | 241 | 21.9321 | 1 | [5 empty] | 241 | 19.6647 | 1
[9 empty] | 242 | 23.8486 | 0 | [5 empty] | 242 | 22.5867 | 0 | [5 empty] | 242 | 21.2593 | 1
[9 empty] | 243 | 23.4202 | 0 | [5 empty] | 243 | 22.4098 | 0 | [5 empty] | 243 | 18.8771 | 1
[9 empty] | 244 | 22.9447 | 0 | [5 empty] | 244 | 22.3524 | 0 | [5 empty] | 244 | 20.3845 | 1
[9 empty] | 245 | 21.7668 | 1 | [5 empty] | 245 | 24.4415 | 0 | [5 empty] | 245 | 22.1941 | 0
[9 empty] | 246 | 23.0756 | 0 | [5 empty] | 246 | 24.8121 | 0 | [5 empty] | 246 | 18.8249 | 1
[9 empty] | 247 | 22.9215 | 0 | [5 empty] | 247 | 23.6213 | 0 | [5 empty] | 247 | 19.8343 | 1
[9 empty] | 248 | 22.2123 | 0 | [5 empty] | 248 | 25.5702 | 0 | [5 empty] | 248 | 19.8423 | 1
[9 empty] | 249 | 22.8986 | 0 | [5 empty] | 249 | 25.0549 | 0 | [5 empty] | 249 | 18.465 | 1
[9 empty] | 250 | 23.5314 | 0 | [5 empty] | 250 | 23.5055 | 0 | [5 empty] | 250 | 22.0932 | 0
[9 empty] | 251 | 20.7504 | 1 | [5 empty] | 251 | 25.4672 | 0 | [5 empty] | 251 | 20.2699 | 1
[9 empty] | 252 | 22.5094 | 0 | [5 empty] | 252 | 24.2446 | 0 | [5 empty] | 252 | 16.9395 | 1
[9 empty] | 253 | 23.2157 | 0 | [5 empty] | 253 | 24.1795 | 0 | [5 empty] | 253 | 19.1962 | 1
[9 empty] | 254 | 21.608 | 1 | [5 empty] | 254 | 24.6695 | 0 | [5 empty] | 254 | 21.1202 | 1
[9 empty] | 255 | 22.8831 | 0 | [5 empty] | 255 | 24.79 | 0 | [5 empty] | 255 | 18.0669 | 1
[9 empty] | 256 | 22.3891 | 0 | [5 empty] | 256 | 24.9261 | 0 | [5 empty] | 256 | 19.963 | 1
[9 empty] | 257 | 23.9149 | 0 | [5 empty] | 257 | 22.0474 | 0 | [5 empty] | 257 | 18.7575 | 1
[9 empty] | 258 | 22.7114 | 0 | [5 empty] | 258 | 24.1141 | 0 | [5 empty] | 258 | 20.4526 | 1
[9 empty] | 259 | 22.6361 | 0 | [5 empty] | 259 | 23.1509 | 0 | [5 empty] | 259 | 18.9058 | 1
[9 empty] | 260 | 22.9155 | 0 | [5 empty] | 260 | 23.1207 | 0 | [5 empty] | 260 | 21.1434 | 1
[9 empty] | 261 | 21.4363 | 1 | [5 empty] | 261 | 25.905 | 0 | [5 empty] | 261 | 18.1864 | 1
[9 empty] | 262 | 20.6939 | 1 | [5 empty] | 262 | 23.893 | 0 | [5 empty] | 262 | 16.8446 | 1
[9 empty] | 263 | 23.0452 | 0 | [5 empty] | 263 | 26.4359 | 0 | [5 empty] | 263 | 19.1344 | 1
[9 empty] | 264 | 21.5826 | 1 | [5 empty] | 264 | 22.8846 | 0 | [5 empty] | 264 | 19.3493 | 1
[9 empty] | 265 | 23.3192 | 0 | [5 empty] | 265 | 22.2038 | 0 | [5 empty] | 265 | 18.6499 | 1
[9 empty] | 266 | 21.7829 | 1 | [5 empty] | 266 | 25.5224 | 0 | [5 empty] | 266 | 21.1142 | 1
[9 empty] | 267 | 20.1123 | 1 | [5 empty] | 267 | 25.2072 | 0 | [5 empty] | 267 | 19.176 | 1
[9 empty] | 268 | 22.7239 | 0 | [5 empty] | 268 | 24.8524 | 0 | [5 empty] | 268 | 22.0367 | 0
[9 empty] | 269 | 22.9123 | 0 | [5 empty] | 269 | 23.8539 | 0 | [5 empty] | 269 | 20.3551 | 1
[9 empty] | 270 | 20.7515 | 1 | [5 empty] | 270 | 22.2932 | 0 | [5 empty] | 270 | 20.5982 | 1
[9 empty] | 271 | 19.7085 | 1 | [5 empty] | 271 | 23.0484 | 0 | [5 empty] | 271 | 20.4671 | 1
[9 empty] | 272 | 23.3914 | 0 | [5 empty] | 272 | 23.6437 | 0 | [5 empty] | 272 | 22.7035 | 0
[9 empty] | 273 | 20.4569 | 1 | [5 empty] | 273 | 22.6877 | 0 | [5 empty] | 273 | 18.2089 | 1
[9 empty] | 274 | 22.1943 | 0 | [5 empty] | 274 | 25.2278 | 0 | [5 empty] | 274 | 19.0254 | 1
[9 empty] | 275 | 22.2922 | 0 | [5 empty] | 275 | 22.2575 | 0 | [5 empty] | 275 | 21.3216 | 1
[9 empty] | 276 | 20.9435 | 1 | [5 empty] | 276 | 23.4626 | 0 | [5 empty] | 276 | 19.8086 | 1
[9 empty] | 277 | 21.4989 | 1 | [5 empty] | 277 | 23.1003 | 0 | [5 empty] | 277 | 21.9719 | 1
[9 empty] | 278 | 21.8761 | 1 | [5 empty] | 278 | 23.5715 | 0 | [5 empty] | 278 | 17.7668 | 1
[9 empty] | 279 | 21.0513 | 1 | [5 empty] | 279 | 24.6932 | 0 | [5 empty] | 279 | 19.9493 | 1
[9 empty] | 280 | 21.464 | 1 | [5 empty] | 280 | 25.9202 | 0 | [5 empty] | 280 | 19.5128 | 1
[9 empty] | 281 | 20.719 | 1 | [5 empty] | 281 | 24.2266 | 0 | [5 empty] | 281 | 21.6036 | 1
[9 empty] | 282 | 21.6865 | 1 | [5 empty] | 282 | 24.7303 | 0 | [5 empty] | 282 | 18.5761 | 1
[9 empty] | 283 | 24.9097 | 0 | [5 empty] | 283 | 23.7479 | 0 | [5 empty] | 283 | 20.3635 | 1
[9 empty] | 284 | 22.0161 | 0 | [5 empty] | 284 | 24.1906 | 0 | [5 empty] | 284 | 20.6463 | 1
[9 empty] | 285 | 23.7037 | 0 | [5 empty] | 285 | 25.7282 | 0 | [5 empty] | 285 | 17.2813 | 1
[9 empty] | 286 | 20.5458 | 1 | [5 empty] | 286 | 25.7583 | 0 | [5 empty] | 286 | 19.4925 | 1
[9 empty] | 287 | 20.7875 | 1 | [5 empty] | 287 | 24.8903 | 0 | [5 empty] | 287 | 21.506 | 1
[9 empty] | 288 | 23.2001 | 0 | [5 empty] | 288 | 23.381 | 0 | [5 empty] | 288 | 19.4102 | 1
[9 empty] | 289 | 23.8623 | 0 | [5 empty] | 289 | 23.7882 | 0 | [5 empty] | 289 | 17.872 | 1
[9 empty] | 290 | 22.4222 | 0 | [5 empty] | 290 | 25.6252 | 0 | [5 empty] | 290 | 21.623 | 1
[9 empty] | 291 | 20.488 | 1 | [5 empty] | 291 | 25.1714 | 0 | [5 empty] | 291 | 21.2086 | 1
[9 empty] | 292 | 22.2662 | 0 | [5 empty] | 292 | 25.3872 | 0 | [5 empty] | 292 | 18.1831 | 1
[9 empty] | 293 | 20.7628 | 1 | [5 empty] | 293 | 23.0493 | 0 | [5 empty] | 293 | 19.7914 | 1
[9 empty] | 294 | 20.859 | 1 | [5 empty] | 294 | 22.9021 | 0 | [5 empty] | 294 | 21.2001 | 1
[9 empty] | 295 | 24.5265 | 0 | [5 empty] | 295 | 24.0342 | 0 | [5 empty] | 295 | 21.8573 | 1
[9 empty] | 296 | 22.8145 | 0 | [5 empty] | 296 | 23.358 | 0 | [5 empty] | 296 | 19.7642 | 1
[9 empty] | 297 | 23.0011 | 0 | [5 empty] | 297 | 24.9281 | 0 | [5 empty] | 297 | 19.8338 | 1
[9 empty] | 298 | 20.3173 | 1 | [5 empty] | 298 | 22.1781 | 0 | [5 empty] | 298 | 17.9072 | 1
[9 empty] | 299 | 23.6015 | 0 | [5 empty] | 299 | 23.176 | 0 | [5 empty] | 299 | 19.1582 | 1
[9 empty] | 300 | 21.4614 | 1 | [5 empty] | 300 | 22.5282 | 0 | [5 empty] | 300 | 22.2206 | 0
[9 empty] | 301 | 22.2057 | 0 | [5 empty] | 301 | 23.9966 | 0 | [5 empty] | 301 | 18.7781 | 1
[9 empty] | 302 | 22.6376 | 0 | [5 empty] | 302 | 23.8693 | 0 | [5 empty] | 302 | 17.3018 | 1
[9 empty] | 303 | 21.0055 | 1 | [5 empty] | 303 | 22.7461 | 0 | [5 empty] | 303 | 18.8265 | 1
[9 empty] | 304 | 22.266 | 0 | [5 empty] | 304 | 23.6331 | 0 | [5 empty] | 304 | 20.1371 | 1
[9 empty] | 305 | 21.8638 | 1 | [5 empty] | 305 | 22.3838 | 0 | [5 empty] | 305 | 20.6819 | 1
[9 empty] | 306 | 21.0291 | 1 | [5 empty] | 306 | 24.6132 | 0 | [5 empty] | 306 | 18.6722 | 1
[9 empty] | 307 | 20.5703 | 1 | [5 empty] | 307 | 23.3531 | 0 | [5 empty] | 307 | 19.1008 | 1
[9 empty] | 308 | 20.6318 | 1 | [5 empty] | 308 | 26.894 | 0 | [5 empty] | 308 | 20.7731 | 1
[9 empty] | 309 | 23.4117 | 0 | [5 empty] | 309 | 25.7997 | 0 | [5 empty] | 309 | 19.8749 | 1
[9 empty] | 310 | 23.0902 | 0 | [5 empty] | 310 | 26.5516 | 0 | [5 empty] | 310 | 17.576 | 1
[9 empty] | 311 | 21.5642 | 1 | [5 empty] | 311 | 21.3625 | 1 | [5 empty] | 311 | 19.8271 | 1
[9 empty] | 312 | 23.6578 | 0 | [5 empty] | 312 | 22.0579 | 0 | [5 empty] | 312 | 20.2108 | 1
[9 empty] | 313 | 22.5373 | 0 | [5 empty] | 313 | 24.1943 | 0 | [5 empty] | 313 | 18.2551 | 1
[9 empty] | 314 | 22.2803 | 0 | [5 empty] | 314 | 22.4613 | 0 | [5 empty] | 314 | 19.7335 | 1
[9 empty] | 315 | 23.5246 | 0 | [5 empty] | 315 | 24.0261 | 0 | [5 empty] | 315 | 18.2473 | 1
[9 empty] | 316 | 20.72 | 1 | [5 empty] | 316 | 25.3983 | 0 | [5 empty] | 316 | 18.0511 | 1
[9 empty] | 317 | 21.5278 | 1 | [5 empty] | 317 | 24.4755 | 0 | [5 empty] | 317 | 20.4849 | 1
[9 empty] | 318 | 21.7444 | 1 | [5 empty] | 318 | 26.2773 | 0 | [5 empty] | 318 | 20.7128 | 1
[9 empty] | 319 | 21.354 | 1 | [5 empty] | 319 | 23.5143 | 0 | [5 empty] | 319 | 20.2736 | 1
[9 empty] | 320 | 21.6614 | 1 | [5 empty] | 320 | 22.7237 | 0 | [5 empty] | 320 | 18.9156 | 1
[9 empty] | 321 | 22.2091 | 0 | [5 empty] | 321 | 22.2354 | 0 | [5 empty] | 321 | 17.7809 | 1
[9 empty] | 322 | 22.8614 | 0 | [5 empty] | 322 | 23.2176 | 0 | [5 empty] | 322 | 19.1851 | 1
[9 empty] | 323 | 24.3219 | 0 | [5 empty] | 323 | 24.2556 | 0 | [5 empty] | 323 | 20.4592 | 1
[9 empty] | 324 | 20.52 | 1 | [5 empty] | 324 | 24.0117 | 0 | [5 empty] | 324 | 20.3149 | 1
[9 empty] | 325 | 21.7936 | 1 | [5 empty] | 325 | 24.4483 | 0 | [5 empty] | 325 | 22.4224 | 0
[9 empty] | 326 | 22.2806 | 0 | [5 empty] | 326 | 26.998 | 0 | [5 empty] | 326 | 19.3684 | 1
[9 empty] | 327 | 20.1968 | 1 | [5 empty] | 327 | 24.9783 | 0 | [5 empty] | 327 | 19.0148 | 1
[9 empty] | 328 | 21.6542 | 1 | [5 empty] | 328 | 26.2699 | 0 | [5 empty] | 328 | 19.5135 | 1
[9 empty] | 329 | 21.118 | 1 | [5 empty] | 329 | 23.2491 | 0 | [5 empty] | 329 | 18.8687 | 1
[9 empty] | 330 | 22.1356 | 0 | [5 empty] | 330 | 25.3573 | 0 | [5 empty] | 330 | 20.0218 | 1
[9 empty] | 331 | 22.7328 | 0 | [5 empty] | 331 | 24.0225 | 0 | [5 empty] | 331 | 18.6944 | 1
[9 empty] | 332 | 21.0062 | 1 | [5 empty] | 332 | 24.1591 | 0 | [5 empty] | 332 | 18.9245 | 1
[9 empty] | 333 | 19.9952 | 1 | [5 empty] | 333 | 24.9346 | 0 | [5 empty] | 333 | 21.2533 | 1
[9 empty] | 334 | 20.6295 | 1 | [5 empty] | 334 | 25.1561 | 0 | [5 empty] | 334 | 21.9547 | 1
[9 empty] | 335 | 21.206 | 1 | [5 empty] | 335 | 21.8671 | 1 | [5 empty] | 335 | 19.9243 | 1
[9 empty] | 336 | 22.3139 | 0 | [5 empty] | 336 | 26.3004 | 0 | [5 empty] | 336 | 21.0416 | 1
[9 empty] | 337 | 23.5521 | 0 | [5 empty] | 337 | 24.0919 | 0 | [5 empty] | 337 | 20.9027 | 1
[9 empty] | 338 | 22.5264 | 0 | [5 empty] | 338 | 23.8532 | 0 | [5 empty] | 338 | 21.3035 | 1
[9 empty] | 339 | 22.6814 | 0 | [5 empty] | 339 | 23.8069 | 0 | [5 empty] | 339 | 20.6985 | 1
[9 empty] | 340 | 21.1893 | 1 | [5 empty] | 340 | 24.5625 | 0 | [5 empty] | 340 | 18.8355 | 1
[9 empty] | 341 | 24.2008 | 0 | [5 empty] | 341 | 24.5677 | 0 | [5 empty] | 341 | 23.499 | 0
[9 empty] | 342 | 22.0203 | 0 | [5 empty] | 342 | 24.7839 | 0 | [5 empty] | 342 | 17.7075 | 1
[9 empty] | 343 | 22.8001 | 0 | [5 empty] | 343 | 25.8619 | 0 | [5 empty] | 343 | 23.2363 | 0
[9 empty] | 344 | 22.7679 | 0 | [5 empty] | 344 | 22.1412 | 0 | [5 empty] | 344 | 18.6513 | 1
[9 empty] | 345 | 25.4654 | 0 | [5 empty] | 345 | 25.9928 | 0 | [5 empty] | 345 | 19.8902 | 1
[9 empty] | 346 | 23.6611 | 0 | [5 empty] | 346 | 22.9471 | 0 | [5 empty] | 346 | 18.9593 | 1
[9 empty] | 347 | 21.7166 | 1 | [5 empty] | 347 | 25.4864 | 0 | [5 empty] | 347 | 21.3247 | 1
[9 empty] | 348 | 23.3689 | 0 | [5 empty] | 348 | 22.9468 | 0 | [5 empty] | 348 | 20.0463 | 1
[9 empty] | 349 | 22.5551 | 0 | [5 empty] | 349 | 23.0224 | 0 | [5 empty] | 349 | 18.377 | 1
[9 empty] | 350 | 20.0497 | 1 | [5 empty] | 350 | 23.1244 | 0 | [5 empty] | 350 | 19.5289 | 1
[9 empty] | 351 | 19.2191 | 1 | [5 empty] | 351 | 23.9352 | 0 | [5 empty] | 351 | 19.2885 | 1
[9 empty] | 352 | 21.9689 | 1 | [5 empty] | 352 | 24.5798 | 0 | [5 empty] | 352 | 19.6054 | 1
[9 empty] | 353 | 22.4363 | 0 | [5 empty] | 353 | 23.1653 | 0 | [5 empty] | 353 | 18.3632 | 1
[9 empty] | 354 | 23.1129 | 0 | [5 empty] | 354 | 22.2358 | 0 | [5 empty] | 354 | 18.1947 | 1
[9 empty] | 355 | 22.6327 | 0 | [5 empty] | 355 | 25.3122 | 0 | [5 empty] | 355 | 18.7643 | 1
[9 empty] | 356 | 21.836 | 1 | [5 empty] | 356 | 23.1954 | 0 | [5 empty] | 356 | 17.8956 | 1
[9 empty] | 357 | 19.8891 | 1 | [5 empty] | 357 | 25.2788 | 0 | [5 empty] | 357 | 18.5266 | 1
[9 empty] | 358 | 21.5473 | 1 | [5 empty] | 358 | 24.6555 | 0 | [5 empty] | 358 | 19.0139 | 1
[9 empty] | 359 | 21.9161 | 1 | [5 empty] | 359 | 26.3703 | 0 | [5 empty] | 359 | 19.6112 | 1
[9 empty] | 360 | 21.4082 | 1 | [5 empty] | 360 | 25.5928 | 0 | [5 empty] | 360 | 21.4331 | 1
[9 empty] | 361 | 22.9679 | 0 | [5 empty] | 361 | 23.9143 | 0 | [5 empty] | 361 | 20.3132 | 1
[9 empty] | 362 | 19.6829 | 1 | [5 empty] | 362 | 24.089 | 0 | [5 empty] | 362 | 21.1075 | 1
[9 empty] | 363 | 20.9403 | 1 | [5 empty] | 363 | 25.1814 | 0 | [5 empty] | 363 | 20.8535 | 1
[9 empty] | 364 | 21.9424 | 1 | [5 empty] | 364 | 24.9942 | 0 | [5 empty] | 364 | 18.9972 | 1
[9 empty] | 365 | 21.6692 | 1 | [5 empty] | 365 | 24.5082 | 0 | [5 empty] | 365 | 20.8695 | 1
[9 empty] | 366 | 23.2334 | 0 | [5 empty] | 366 | 23.3418 | 0 | [5 empty] | 366 | 19.0834 | 1
[9 empty] | 367 | 21.4551 | 1 | [5 empty] | 367 | 23.7767 | 0 | [5 empty] | 367 | 18.5275 | 1
[9 empty] | 368 | 22.4343 | 0 | [5 empty] | 368 | 22.8301 | 0 | [5 empty] | 368 | 18.2532 | 1
[9 empty] | 369 | 21.3627 | 1 | [5 empty] | 369 | 25.8694 | 0 | [5 empty] | 369 | 20.3674 | 1
[9 empty] | 370 | 21.1874 | 1 | [5 empty] | 370 | 23.8827 | 0 | [5 empty] | 370 | 19.7906 | 1
[9 empty] | 371 | 21.5317 | 1 | [5 empty] | 371 | 24.273 | 0 | [5 empty] | 371 | 18.5748 | 1
[9 empty] | 372 | 20.8935 | 1 | [5 empty] | 372 | 23.9521 | 0 | [5 empty] | 372 | 21.3258 | 1
[9 empty] | 373 | 19.0988 | 1 | [5 empty] | 373 | 24.7306 | 0 | [5 empty] | 373 | 20.0544 | 1
[9 empty] | 374 | 21.3902 | 1 | [5 empty] | 374 | 24.4382 | 0 | [5 empty] | 374 | 17.9959 | 1
[9 empty] | 375 | 21.032 | 1 | [5 empty] | 375 | 22.0214 | 0 | [5 empty] | 375 | 20.5957 | 1
[9 empty] | 376 | 23.4217 | 0 | [5 empty] | 376 | 24.9453 | 0 | [5 empty] | 376 | 18.6581 | 1
[9 empty] | 377 | 21.8134 | 1 | [5 empty] | 377 | 24.625 | 0 | [5 empty] | 377 | 17.2433 | 1
[9 empty] | 378 | 22.8842 | 0 | [5 empty] | 378 | 25.0163 | 0 | [5 empty] | 378 | 18.3449 | 1
[9 empty] | 379 | 23.6003 | 0 | [5 empty] | 379 | 25.1256 | 0 | [5 empty] | 379 | 19.1108 | 1
[9 empty] | 380 | 20.1715 | 1 | [5 empty] | 380 | 24.2548 | 0 | [5 empty] | 380 | 22.1355 | 0
[9 empty] | 381 | 22.6174 | 0 | [5 empty] | 381 | 21.392 | 1 | [5 empty] | 381 | 20.7873 | 1
[9 empty] | 382 | 20.7745 | 1 | [5 empty] | 382 | 23.0823 | 0 | [5 empty] | 382 | 19.1466 | 1
[9 empty] | 383 | 25.2694 | 0 | [5 empty] | 383 | 25.7164 | 0 | [5 empty] | 383 | 21.2778 | 1
[9 empty] | 384 | 23.6447 | 0 | [5 empty] | 384 | 25.5162 | 0 | [5 empty] | 384 | 19.226 | 1
[9 empty] | 385 | 23.5531 | 0 | [5 empty] | 385 | 22.402 | 0 | [5 empty] | 385 | 17.7174 | 1
[9 empty] | 386 | 21.1097 | 1 | [5 empty] | 386 | 25.0445 | 0 | [5 empty] | 386 | 19.1042 | 1
[9 empty] | 387 | 21.069 | 1 | [5 empty] | 387 | 23.2318 | 0 | [5 empty] | 387 | 21.44 | 1
[9 empty] | 388 | 22.6388 | 0 | [5 empty] | 388 | 24.6964 | 0 | [5 empty] | 388 | 19.2142 | 1
[9 empty] | 389 | 22.9469 | 0 | [5 empty] | 389 | 26.7548 | 0 | [5 empty] | 389 | 20.3007 | 1
[9 empty] | 390 | 21.0974 | 1 | [5 empty] | 390 | 21.822 | 1 | [5 empty] | 390 | 17.8625 | 1
[9 empty] | 391 | 22.8088 | 0 | [5 empty] | 391 | 24.4792 | 0 | [5 empty] | 391 | 18.1944 | 1
[9 empty] | 392 | 21.8384 | 1 | [5 empty] | 392 | 24.8565 | 0 | [5 empty] | 392 | 19.7839 | 1
[9 empty] | 393 | 22.2927 | 0 | [5 empty] | 393 | 25.6392 | 0 | [5 empty] | 393 | 20.9933 | 1
[9 empty] | 394 | 20.6628 | 1 | [5 empty] | 394 | 24.6444 | 0 | [5 empty] | 394 | 17.6774 | 1
[9 empty] | 395 | 21.1574 | 1 | [5 empty] | 395 | 23.9089 | 0 | [5 empty] | 395 | 19.1737 | 1
[9 empty] | 396 | 21.7983 | 1 | [5 empty] | 396 | 23.1533 | 0 | [5 empty] | 396 | 18.9978 | 1
[9 empty] | 397 | 22.46 | 0 | [5 empty] | 397 | 23.1109 | 0 | [5 empty] | 397 | 17.2947 | 1
[9 empty] | 398 | 22.2145 | 0 | [5 empty] | 398 | 22.1624 | 0 | [5 empty] | 398 | 21.4659 | 1
[9 empty] | 399 | 20.9211 | 1 | [5 empty] | 399 | 25.4278 | 0 | [5 empty] | 399 | 23.0555 | 0
[9 empty] | 400 | 22.3486 | 0 | [5 empty] | 400 | 22.7019 | 0 | [5 empty] | 400 | 18.7568 | 1
[9 empty] | 401 | 21.8873 | 1 | [5 empty] | 401 | 23.8946 | 0 | [5 empty] | 401 | 18.2183 | 1
[9 empty] | 402 | 21.9805 | 1 | [5 empty] | 402 | 22.09 | 0 | [5 empty] | 402 | 17.7981 | 1
[9 empty] | 403 | 22.8208 | 0 | [5 empty] | 403 | 24.4623 | 0 | [5 empty] | 403 | 17.8112 | 1
[9 empty] | 404 | 21.7042 | 1 | [5 empty] | 404 | 22.7793 | 0 | [5 empty] | 404 | 21.9828 | 1
[9 empty] | 405 | 20.8762 | 1 | [5 empty] | 405 | 22.6619 | 0 | [5 empty] | 405 | 21.476 | 1
[9 empty] | 406 | 19.575 | 1 | [5 empty] | 406 | 23.2305 | 0 | [5 empty] | 406 | 21.8729 | 1
[9 empty] | 407 | 23.0355 | 0 | [5 empty] | 407 | 20.4797 | 1 | [5 empty] | 407 | 21.3348 | 1
[9 empty] | 408 | 22.1024 | 0 | [5 empty] | 408 | 25.1157 | 0 | [5 empty] | 408 | 16.9259 | 1
[9 empty] | 409 | 22.2845 | 0 | [5 empty] | 409 | 26.4925 | 0 | [5 empty] | 409 | 20.0945 | 1
[9 empty] | 410 | 20.5636 | 1 | [5 empty] | 410 | 25.7033 | 0 | [5 empty] | 410 | 17.1805 | 1
[9 empty] | 411 | 21.9066 | 1 | [5 empty] | 411 | 24.8088 | 0 | [5 empty] | 411 | 16.7415 | 1
[9 empty] | 412 | 20.9421 | 1 | [5 empty] | 412 | 25.5115 | 0 | [5 empty] | 412 | 18.2696 | 1
[9 empty] | 413 | 20.6866 | 1 | [5 empty] | 413 | 23.3401 | 0 | [5 empty] | 413 | 19.6134 | 1
[9 empty] | 414 | 21.7936 | 1 | [5 empty] | 414 | 24.0139 | 0 | [5 empty] | 414 | 18.1655 | 1
[9 empty] | 415 | 24.0086 | 0 | [5 empty] | 415 | 23.5098 | 0 | [5 empty] | 415 | 19.9622 | 1
[9 empty] | 416 | 22.8439 | 0 | [5 empty] | 416 | 22.6051 | 0 | [5 empty] | 416 | 20.746 | 1
[9 empty] | 417 | 21.0457 | 1 | [5 empty] | 417 | 25.8103 | 0 | [5 empty] | 417 | 19.6297 | 1
[9 empty] | 418 | 22.2525 | 0 | [5 empty] | 418 | 25.5086 | 0 | [5 empty] | 418 | 19.3067 | 1
[9 empty] | 419 | 23.9285 | 0 | [5 empty] | 419 | 23.7548 | 0 | [5 empty] | 419 | 17.5629 | 1
[9 empty] | 420 | 22.3435 | 0 | [5 empty] | 420 | 25.6607 | 0 | [5 empty] | 420 | 18.6108 | 1
[9 empty] | 421 | 22.0476 | 0 | [5 empty] | 421 | 24.4813 | 0 | [5 empty] | 421 | 20.1723 | 1
[9 empty] | 422 | 21.5604 | 1 | [5 empty] | 422 | 25.0719 | 0 | [5 empty] | 422 | 18.8682 | 1
[9 empty] | 423 | 21.1923 | 1 | [5 empty] | 423 | 23.2555 | 0 | [5 empty] | 423 | 19.4688 | 1
[9 empty] | 424 | 21.7362 | 1 | [5 empty] | 424 | 21.5829 | 1 | [5 empty] | 424 | 18.966 | 1
[9 empty] | 425 | 20.6603 | 1 | [5 empty] | 425 | 23.3128 | 0 | [5 empty] | 425 | 17.3107 | 1
[9 empty] | 426 | 19.4377 | 1 | [5 empty] | 426 | 25.1814 | 0 | [5 empty] | 426 | 19.2488 | 1
[9 empty] | 427 | 21.365 | 1 | [5 empty] | 427 | 25.3217 | 0 | [5 empty] | 427 | 17.6223 | 1
[9 empty] | 428 | 21.2959 | 1 | [5 empty] | 428 | 23.5835 | 0 | [5 empty] | 428 | 19.4517 | 1
[9 empty] | 429 | 22.165 | 0 | [5 empty] | 429 | 25.7784 | 0 | [5 empty] | 429 | 18.8024 | 1
[9 empty] | 430 | 20.7471 | 1 | [5 empty] | 430 | 25.1184 | 0 | [5 empty] | 430 | 17.7679 | 1
[9 empty] | 431 | 21.8101 | 1 | [5 empty] | 431 | 22.6791 | 0 | [5 empty] | 431 | 20.8096 | 1
[9 empty] | 432 | 23.3358 | 0 | [5 empty] | 432 | 26.082 | 0 | [5 empty] | 432 | 20.4501 | 1
[9 empty] | 433 | 22.6749 | 0 | [5 empty] | 433 | 25.0481 | 0 | [5 empty] | 433 | 19.9873 | 1
[9 empty] | 434 | 20.2625 | 1 | [5 empty] | 434 | 23.5703 | 0 | [5 empty] | 434 | 19.5672 | 1
[9 empty] | 435 | 22.7613 | 0 | [5 empty] | 435 | 22.6527 | 0 | [5 empty] | 435 | 17.1985 | 1
[9 empty] | 436 | 23.6914 | 0 | [5 empty] | 436 | 25.6173 | 0 | [5 empty] | 436 | 18.3324 | 1
[9 empty] | 437 | 22.3219 | 0 | [5 empty] | 437 | 24.0285 | 0 | [5 empty] | 437 | 18.9009 | 1
[9 empty] | 438 | 23.1785 | 0 | [5 empty] | 438 | 26.0026 | 0 | [5 empty] | 438 | 19.2247 | 1
[9 empty] | 439 | 20.7278 | 1 | [5 empty] | 439 | 23.2459 | 0 | [5 empty] | 439 | 17.0054 | 1
[9 empty] | 440 | 21.9322 | 1 | [5 empty] | 440 | 25.4282 | 0 | [5 empty] | 440 | 18.1099 | 1
[9 empty] | 441 | 22.8494 | 0 | [5 empty] | 441 | 23.7541 | 0 | [5 empty] | 441 | 20.3663 | 1
[9 empty] | 442 | 22.8373 | 0 | [5 empty] | 442 | 26.0427 | 0 | [5 empty] | 442 | 20.3577 | 1
[9 empty] | 443 | 23.3248 | 0 | [5 empty] | 443 | 23.6441 | 0 | [5 empty] | 443 | 17.5223 | 1
[9 empty] | 444 | 21.3481 | 1 | [5 empty] | 444 | 24.4824 | 0 | [5 empty] | 444 | 18.1998 | 1
[9 empty] | 445 | 21.8865 | 1 | [5 empty] | 445 | 24.9258 | 0 | [5 empty] | 445 | 18.5414 | 1
[9 empty] | 446 | 21.6514 | 1 | [5 empty] | 446 | 24.041 | 0 | [5 empty] | 446 | 19.3333 | 1
[9 empty] | 447 | 24.7516 | 0 | [5 empty] | 447 | 23.3094 | 0 | [5 empty] | 447 | 19.9673 | 1
[9 empty] | 448 | 22.1484 | 0 | [5 empty] | 448 | 23.3482 | 0 | [5 empty] | 448 | 17.5025 | 1
[9 empty] | 449 | 20.3127 | 1 | [5 empty] | 449 | 21.0356 | 1 | [5 empty] | 449 | 18.354 | 1
[9 empty] | 450 | 21.1295 | 1 | [5 empty] | 450 | 24.0273 | 0 | [5 empty] | 450 | 18.318 | 1
[9 empty] | 451 | 20.4183 | 1 | [5 empty] | 451 | 24.3445 | 0 | [5 empty] | 451 | 20.0245 | 1
[9 empty] | 452 | 22.1441 | 0 | [5 empty] | 452 | 22.6788 | 0 | [5 empty] | 452 | 20.4066 | 1
[9 empty] | 453 | 21.0861 | 1 | [5 empty] | 453 | 25.1921 | 0 | [5 empty] | 453 | 19.6811 | 1
[9 empty] | 454 | 20.6319 | 1 | [5 empty] | 454 | 23.9316 | 0 | [5 empty] | 454 | 19.7623 | 1
[9 empty] | 455 | 20.056 | 1 | [5 empty] | 455 | 26.9009 | 0 | [5 empty] | 455 | 19.5303 | 1
[9 empty] | 456 | 21.1638 | 1 | [5 empty] | 456 | 26.3135 | 0 | [5 empty] | 456 | 20.1471 | 1
[9 empty] | 457 | 21.0998 | 1 | [5 empty] | 457 | 23.4017 | 0 | [5 empty] | 457 | 19.9908 | 1
[9 empty] | 458 | 22.9691 | 0 | [5 empty] | 458 | 24.2236 | 0 | [5 empty] | 458 | 19.9249 | 1
[9 empty] | 459 | 21.8108 | 1 | [5 empty] | 459 | 25.1954 | 0 | [5 empty] | 459 | 18.575 | 1
[9 empty] | 460 | 21.6015 | 1 | [5 empty] | 460 | 22.3015 | 0 | [5 empty] | 460 | 21.0129 | 1
[9 empty] | 461 | 22.8628 | 0 | [5 empty] | 461 | 22.4595 | 0 | [5 empty] | 461 | 18.2679 | 1
[9 empty] | 462 | 22.3721 | 0 | [5 empty] | 462 | 23.5609 | 0 | [5 empty] | 462 | 19.46 | 1
[9 empty] | 463 | 22.1676 | 0 | [5 empty] | 463 | 23.656 | 0 | [5 empty] | 463 | 19.6182 | 1
[9 empty] | 464 | 20.8739 | 1 | [5 empty] | 464 | 23.1595 | 0 | [5 empty] | 464 | 18.6816 | 1
[9 empty] | 465 | 22.4848 | 0 | [5 empty] | 465 | 23.3757 | 0 | [5 empty] | 465 | 20.9861 | 1
[9 empty] | 466 | 20.1203 | 1 | [5 empty] | 466 | 24.5264 | 0 | [5 empty] | 466 | 20.5385 | 1
[9 empty] | 467 | 23.52 | 0 | [5 empty] | 467 | 23.5159 | 0 | [5 empty] | 467 | 24.3247 | 0
[9 empty] | 468 | 20.615 | 1 | [5 empty] | 468 | 24.8046 | 0 | [5 empty] | 468 | 20.9742 | 1
[9 empty] | 469 | 20.5337 | 1 | [5 empty] | 469 | 23.6705 | 0 | [5 empty] | 469 | 20.2538 | 1
[9 empty] | 470 | 22.5117 | 0 | [5 empty] | 470 | 23.5858 | 0 | [5 empty] | 470 | 19.567 | 1
[9 empty] | 471 | 22.7613 | 0 | [5 empty] | 471 | 23.9346 | 0 | [5 empty] | 471 | 19.2493 | 1
[9 empty] | 472 | 22.1982 | 0 | [5 empty] | 472 | 25.0048 | 0 | [5 empty] | 472 | 20.1884 | 1
[9 empty] | 473 | 21.9192 | 1 | [5 empty] | 473 | 24.8293 | 0 | [5 empty] | 473 | 19.3869 | 1
[9 empty] | 474 | 20.3773 | 1 | [5 empty] | 474 | 23.2393 | 0 | [5 empty] | 474 | 21.5994 | 1
[9 empty] | 475 | 22.1655 | 0 | [5 empty] | 475 | 25.9372 | 0 | [5 empty] | 475 | 19.6261 | 1
[9 empty] | 476 | 21.2568 | 1 | [5 empty] | 476 | 22.7729 | 0 | [5 empty] | 476 | 18.615 | 1
[9 empty] | 477 | 22.5631 | 0 | [5 empty] | 477 | 22.339 | 0 | [5 empty] | 477 | 17.3203 | 1
[9 empty] | 478 | 21.7425 | 1 | [5 empty] | 478 | 22.2005 | 0 | [5 empty] | 478 | 18.802 | 1
[9 empty] | 479 | 21.8295 | 1 | [5 empty] | 479 | 25.7315 | 0 | [5 empty] | 479 | 19.0655 | 1
[9 empty] | 480 | 21.453 | 1 | [5 empty] | 480 | 23.8222 | 0 | [5 empty] | 480 | 17.2597 | 1
[9 empty] | 481 | 19.7567 | 1 | [5 empty] | 481 | 24.738 | 0 | [5 empty] | 481 | 17.921 | 1
[9 empty] | 482 | 23.4965 | 0 | [5 empty] | 482 | 23.3894 | 0 | [5 empty] | 482 | 20.1389 | 1
[9 empty] | 483 | 19.7168 | 1 | [5 empty] | 483 | 26.0315 | 0 | [5 empty] | 483 | 20.0739 | 1
[9 empty] | 484 | 22.937 | 0 | [5 empty] | 484 | 23.1592 | 0 | [5 empty] | 484 | 17.816 | 1
[9 empty] | 485 | 21.4599 | 1 | [5 empty] | 485 | 23.4967 | 0 | [5 empty] | 485 | 17.8251 | 1
[9 empty] | 486 | 23.8751 | 0 | [5 empty] | 486 | 24.2516 | 0 | [5 empty] | 486 | 20.4571 | 1
[9 empty] | 487 | 20.1967 | 1 | [5 empty] | 487 | 24.1092 | 0 | [5 empty] | 487 | 20.1257 | 1
[9 empty] | 488 | 23.1502 | 0 | [5 empty] | 488 | 23.8152 | 0 | [5 empty] | 488 | 18.7929 | 1
[9 empty] | 489 | 24.4792 | 0 | [5 empty] | 489 | 22.9325 | 0 | [5 empty] | 489 | 21.9406 | 1
[9 empty] | 490 | 21.8664 | 1 | [5 empty] | 490 | 25.4016 | 0 | [5 empty] | 490 | 20.8398 | 1
[9 empty] | 491 | 22.2727 | 0 | [5 empty] | 491 | 24.4366 | 0 | [5 empty] | 491 | 20.5534 | 1
[9 empty] | 492 | 23.8466 | 0 | [5 empty] | 492 | 22.1484 | 0 | [5 empty] | 492 | 20.6441 | 1
[9 empty] | 493 | 23.1682 | 0 | [5 empty] | 493 | 23.4695 | 0 | [5 empty] | 493 | 20.5261 | 1
[9 empty] | 494 | 22.2968 | 0 | [5 empty] | 494 | 23.0919 | 0 | [5 empty] | 494 | 19.0751 | 1
[9 empty] | 495 | 21.8927 | 1 | [5 empty] | 495 | 24.0447 | 0 | [5 empty] | 495 | 23.2268 | 0
[9 empty] | 496 | 20.3998 | 1 | [5 empty] | 496 | 24.9514 | 0 | [5 empty] | 496 | 18.0362 | 1
[9 empty] | 497 | 22.3899 | 0 | [5 empty] | 497 | 23.1196 | 0 | [5 empty] | 497 | 22.2458 | 0
[9 empty] | 498 | 20.8551 | 1 | [5 empty] | 498 | 24.1518 | 0 | [5 empty] | 498 | 18.2824 | 1
[9 empty] | 499 | 22.375 | 0 | [5 empty] | 499 | 24.9216 | 0 | [5 empty] | 499 | 17.998 | 1
[9 empty] | 500 | 19.2978 | 1 | [5 empty] | 500 | 24.5387 | 0 | [5 empty] | 500 | 18.7813 | 1
[9 empty] | 501 | 21.6215 | 1 | [5 empty] | 501 | 26.0784 | 0 | [5 empty] | 501 | 20.6096 | 1
[9 empty] | 502 | 22.8838 | 0 | [5 empty] | 502 | 21.8001 | 1 | [5 empty] | 502 | 20.565 | 1
[9 empty] | 503 | 20.691 | 1 | [5 empty] | 503 | 24.2113 | 0 | [5 empty] | 503 | 18.5013 | 1
[9 empty] | 504 | 21.5737 | 1 | [5 empty] | 504 | 22.9509 | 0 | [5 empty] | 504 | 20.3237 | 1
[9 empty] | 505 | 20.7571 | 1 | [5 empty] | 505 | 24.664 | 0 | [5 empty] | 505 | 20.2375 | 1
[9 empty] | 506 | 21.2025 | 1 | [5 empty] | 506 | 25.1939 | 0 | [5 empty] | 506 | 19.7557 | 1
[9 empty] | 507 | 21.8575 | 1 | [5 empty] | 507 | 23.0073 | 0 | [5 empty] | 507 | 19.1248 | 1
[9 empty] | 508 | 20.8796 | 1 | [5 empty] | 508 | 25.084 | 0 | [5 empty] | 508 | 20.4363 | 1
[9 empty] | 509 | 19.7477 | 1 | [5 empty] | 509 | 24.4267 | 0 | [5 empty] | 509 | 18.8156 | 1
[9 empty] | 510 | 21.3317 | 1 | [5 empty] | 510 | 25.9449 | 0 | [5 empty] | 510 | 20.5683 | 1
[9 empty] | 511 | 24.358 | 0 | [5 empty] | 511 | 24.7949 | 0 | [5 empty] | 511 | 20.5106 | 1
[9 empty] | 512 | 20.2876 | 1 | [5 empty] | 512 | 25.9859 | 0 | [5 empty] | 512 | 20.6558 | 1
[9 empty] | 513 | 23.6343 | 0 | [5 empty] | 513 | 23.3498 | 0 | [5 empty] | 513 | 22.2478 | 0
[9 empty] | 514 | 19.4635 | 1 | [5 empty] | 514 | 25.2568 | 0 | [5 empty] | 514 | 18.7559 | 1
[9 empty] | 515 | 22.0834 | 0 | [5 empty] | 515 | 24.3918 | 0 | [5 empty] | 515 | 18.4708 | 1
[9 empty] | 516 | 21.8867 | 1 | [5 empty] | 516 | 24.0285 | 0 | [5 empty] | 516 | 19.3055 | 1
[9 empty] | 517 | 23.7526 | 0 | [5 empty] | 517 | 22.3778 | 0 | [5 empty] | 517 | 19.3842 | 1
[9 empty] | 518 | 23.6298 | 0 | [5 empty] | 518 | 24.0031 | 0 | [5 empty] | 518 | 20.4302 | 1
[9 empty] | 519 | 22.7331 | 0 | [5 empty] | 519 | 26.1592 | 0 | [5 empty] | 519 | 17.8249 | 1
[9 empty] | 520 | 20.8395 | 1 | [5 empty] | 520 | 24.1157 | 0 | [5 empty] | 520 | 20.5285 | 1
[9 empty] | 521 | 22.5657 | 0 | [5 empty] | 521 | 25.4773 | 0 | [5 empty] | 521 | 20.21 | 1
[9 empty] | 522 | 21.7393 | 1 | [5 empty] | 522 | 23.0849 | 0 | [5 empty] | 522 | 19.0595 | 1
[9 empty] | 523 | 19.3119 | 1 | [5 empty] | 523 | 24.5897 | 0 | [5 empty] | 523 | 19.7536 | 1
[9 empty] | 524 | 24.8202 | 0 | [5 empty] | 524 | 23.0693 | 0 | [5 empty] | 524 | 18.3521 | 1
[9 empty] | 525 | 21.2719 | 1 | [5 empty] | 525 | 23.0537 | 0 | [5 empty] | 525 | 20.1304 | 1
[9 empty] | 526 | 21.8821 | 1 | [5 empty] | 526 | 23.4109 | 0 | [5 empty] | 526 | 20.4258 | 1
[9 empty] | 527 | 22.6811 | 0 | [5 empty] | 527 | 24.8548 | 0 | [5 empty] | 527 | 17.7382 | 1
[9 empty] | 528 | 22.6462 | 0 | [5 empty] | 528 | 25.4724 | 0 | [5 empty] | 528 | 22.7517 | 0
[9 empty] | 529 | 22.6843 | 0 | [5 empty] | 529 | 24.1525 | 0 | [5 empty] | 529 | 20.8588 | 1
[9 empty] | 530 | 20.4423 | 1 | [5 empty] | 530 | 26.5703 | 0 | [5 empty] | 530 | 18.4717 | 1
[9 empty] | 531 | 22.0788 | 0 | [5 empty] | 531 | 25.6251 | 0 | [5 empty] | 531 | 17.9166 | 1
[9 empty] | 532 | 21.9173 | 1 | [5 empty] | 532 | 23.2937 | 0 | [5 empty] | 532 | 21.994 | 1
[9 empty] | 533 | 19.7599 | 1 | [5 empty] | 533 | 24.722 | 0 | [5 empty] | 533 | 18.6774 | 1
[9 empty] | 534 | 24.0274 | 0 | [5 empty] | 534 | 24.9628 | 0 | [5 empty] | 534 | 18.9775 | 1
[9 empty] | 535 | 22.357 | 0 | [5 empty] | 535 | 25.8096 | 0 | [5 empty] | 535 | 21.3191 | 1
[9 empty] | 536 | 22.3893 | 0 | [5 empty] | 536 | 22.5701 | 0 | [5 empty] | 536 | 19.8955 | 1
[9 empty] | 537 | 20.2863 | 1 | [5 empty] | 537 | 23.7054 | 0 | [5 empty] | 537 | 19.4675 | 1
[9 empty] | 538 | 19.8683 | 1 | [5 empty] | 538 | 23.9088 | 0 | [5 empty] | 538 | 19.6172 | 1
[9 empty] | 539 | 20.6764 | 1 | [5 empty] | 539 | 23.7131 | 0 | [5 empty] | 539 | 23.1772 | 0
[9 empty] | 540 | 21.1174 | 1 | [5 empty] | 540 | 23.884 | 0 | [5 empty] | 540 | 20.8208 | 1
[9 empty] | 541 | 21.4893 | 1 | [5 empty] | 541 | 23.082 | 0 | [5 empty] | 541 | 17.677 | 1
[9 empty] | 542 | 22.5035 | 0 | [5 empty] | 542 | 25.0391 | 0 | [5 empty] | 542 | 21.3933 | 1
[9 empty] | 543 | 21.3756 | 1 | [5 empty] | 543 | 23.5983 | 0 | [5 empty] | 543 | 20.3804 | 1
[9 empty] | 544 | 22.582 | 0 | [5 empty] | 544 | 22.9885 | 0 | [5 empty] | 544 | 19.6632 | 1
[9 empty] | 545 | 21.9305 | 1 | [5 empty] | 545 | 22.4045 | 0 | [5 empty] | 545 | 17.2471 | 1
[9 empty] | 546 | 21.7214 | 1 | [5 empty] | 546 | 24.1623 | 0 | [5 empty] | 546 | 18.3779 | 1
[9 empty] | 547 | 21.1089 | 1 | [5 empty] | 547 | 25.4249 | 0 | [5 empty] | 547 | 18.5744 | 1
[9 empty] | 548 | 22.4526 | 0 | [5 empty] | 548 | 24.8024 | 0 | [5 empty] | 548 | 21.9314 | 1
[9 empty] | 549 | 22.1128 | 0 | [5 empty] | 549 | 24.2407 | 0 | [5 empty] | 549 | 19.1558 | 1
[9 empty] | 550 | 21.9036 | 1 | [5 empty] | 550 | 24.4543 | 0 | [5 empty] | 550 | 18.4857 | 1
[9 empty] | 551 | 22.6323 | 0 | [5 empty] | 551 | 26.2473 | 0 | [5 empty] | 551 | 20.5641 | 1
[9 empty] | 552 | 20.4552 | 1 | [5 empty] | 552 | 24.3256 | 0 | [5 empty] | 552 | 20.557 | 1
[9 empty] | 553 | 22.7164 | 0 | [5 empty] | 553 | 24.4321 | 0 | [5 empty] | 553 | 20.4827 | 1
[9 empty] | 554 | 22.0226 | 0 | [5 empty] | 554 | 23.0289 | 0 | [5 empty] | 554 | 22.5989 | 0
[9 empty] | 555 | 22.7834 | 0 | [5 empty] | 555 | 23.7715 | 0 | [5 empty] | 555 | 19.972 | 1
[9 empty] | 556 | 21.3773 | 1 | [5 empty] | 556 | 24.0352 | 0 | [5 empty] | 556 | 20.3295 | 1
[9 empty] | 557 | 22.6936 | 0 | [5 empty] | 557 | 24.8277 | 0 | [5 empty] | 557 | 18.9532 | 1
[9 empty] | 558 | 21.9656 | 1 | [5 empty] | 558 | 24.1556 | 0 | [5 empty] | 558 | 18.5932 | 1
[9 empty] | 559 | 20.5937 | 1 | [5 empty] | 559 | 25.4513 | 0 | [5 empty] | 559 | 19.5639 | 1
[9 empty] | 560 | 20.9021 | 1 | [5 empty] | 560 | 23.8483 | 0 | [5 empty] | 560 | 20.7137 | 1
[9 empty] | 561 | 20.2527 | 1 | [5 empty] | 561 | 23.3929 | 0 | [5 empty] | 561 | 20.0856 | 1
[9 empty] | 562 | 21.8701 | 1 | [5 empty] | 562 | 23.5782 | 0 | [5 empty] | 562 | 18.3913 | 1
[9 empty] | 563 | 22.9803 | 0 | [5 empty] | 563 | 24.0594 | 0 | [5 empty] | 563 | 17.8783 | 1
[9 empty] | 564 | 21.4028 | 1 | [5 empty] | 564 | 23.2255 | 0 | [5 empty] | 564 | 18.4956 | 1
[9 empty] | 565 | 21.8451 | 1 | [5 empty] | 565 | 24.2683 | 0 | [5 empty] | 565 | 17.7543 | 1
[9 empty] | 566 | 20.2854 | 1 | [5 empty] | 566 | 25.4327 | 0 | [5 empty] | 566 | 18.6269 | 1
[9 empty] | 567 | 22.5072 | 0 | [5 empty] | 567 | 24.6591 | 0 | [5 empty] | 567 | 20.5216 | 1
[9 empty] | 568 | 20.6707 | 1 | [5 empty] | 568 | 26.0234 | 0 | [5 empty] | 568 | 20.9797 | 1
[9 empty] | 569 | 21.4643 | 1 | [5 empty] | 569 | 25.7588 | 0 | [5 empty] | 569 | 21.5609 | 1
[9 empty] | 570 | 19.3872 | 1 | [5 empty] | 570 | 21.472 | 1 | [5 empty] | 570 | 20.7734 | 1
[9 empty] | 571 | 22.283 | 0 | [5 empty] | 571 | 23.0388 | 0 | [5 empty] | 571 | 20.0707 | 1
[9 empty] | 572 | 22.5006 | 0 | [5 empty] | 572 | 23.8674 | 0 | [5 empty] | 572 | 20.9721 | 1
[9 empty] | 573 | 21.9829 | 1 | [5 empty] | 573 | 25.5746 | 0 | [5 empty] | 573 | 21.402 | 1
[9 empty] | 574 | 23.0085 | 0 | [5 empty] | 574 | 25.1935 | 0 | [5 empty] | 574 | 19.3469 | 1
[9 empty] | 575 | 23.4255 | 0 | [5 empty] | 575 | 22.1036 | 0 | [5 empty] | 575 | 17.9381 | 1
[9 empty] | 576 | 22.4469 | 0 | [5 empty] | 576 | 24.277 | 0 | [5 empty] | 576 | 21.086 | 1
[9 empty] | 577 | 23.5462 | 0 | [5 empty] | 577 | 24.2536 | 0 | [5 empty] | 577 | 19.0094 | 1
[9 empty] | 578 | 22.0286 | 0 | [5 empty] | 578 | 25.2822 | 0 | [5 empty] | 578 | 21.4455 | 1
[9 empty] | 579 | 23.1849 | 0 | [5 empty] | 579 | 27.741 | 0 | [5 empty] | 579 | 21.3276 | 1
[9 empty] | 580 | 21.4973 | 1 | [5 empty] | 580 | 24.5279 | 0 | [5 empty] | 580 | 22.8635 | 0
[9 empty] | 581 | 21.6415 | 1 | [5 empty] | 581 | 25.262 | 0 | [5 empty] | 581 | 18.8325 | 1
[9 empty] | 582 | 20.9593 | 1 | [5 empty] | 582 | 23.4514 | 0 | [5 empty] | 582 | 18.6023 | 1
[9 empty] | 583 | 23.0636 | 0 | [5 empty] | 583 | 23.5699 | 0 | [5 empty] | 583 | 18.3016 | 1
[9 empty] | 584 | 22.0285 | 0 | [5 empty] | 584 | 23.478 | 0 | [5 empty] | 584 | 17.6334 | 1
[9 empty] | 585 | 21.7195 | 1 | [5 empty] | 585 | 23.8776 | 0 | [5 empty] | 585 | 19.5055 | 1
[9 empty] | 586 | 20.1797 | 1 | [5 empty] | 586 | 26.7578 | 0 | [5 empty] | 586 | 19.3959 | 1
[9 empty] | 587 | 23.434 | 0 | [5 empty] | 587 | 26.141 | 0 | [5 empty] | 587 | 19.8364 | 1
[9 empty] | 588 | 22.2134 | 0 | [5 empty] | 588 | 24.4796 | 0 | [5 empty] | 588 | 19.5279 | 1
[9 empty] | 589 | 23.0883 | 0 | [5 empty] | 589 | 27.1148 | 0 | [5 empty] | 589 | 22.0192 | 0
[9 empty] | 590 | 18.7119 | 1 | [5 empty] | 590 | 23.5934 | 0 | [5 empty] | 590 | 20.0451 | 1
[9 empty] | 591 | 22.8197 | 0 | [5 empty] | 591 | 24.2245 | 0 | [5 empty] | 591 | 19.5105 | 1
[9 empty] | 592 | 21.409 | 1 | [5 empty] | 592 | 25.0641 | 0 | [5 empty] | 592 | 19.9866 | 1
[9 empty] | 593 | 21.7277 | 1 | [5 empty] | 593 | 24.3561 | 0 | [5 empty] | 593 | 19.0438 | 1
[9 empty] | 594 | 21.4346 | 1 | [5 empty] | 594 | 23.4425 | 0 | [5 empty] | 594 | 19.0507 | 1
[9 empty] | 595 | 22.624 | 0 | [5 empty] | 595 | 24.1428 | 0 | [5 empty] | 595 | 19.375 | 1
[9 empty] | 596 | 22.4069 | 0 | [5 empty] | 596 | 23.7941 | 0 | [5 empty] | 596 | 18.821 | 1
[9 empty] | 597 | 22.8058 | 0 | [5 empty] | 597 | 23.0359 | 0 | [5 empty] | 597 | 17.9338 | 1
[9 empty] | 598 | 21.3112 | 1 | [5 empty] | 598 | 25.7832 | 0 | [5 empty] | 598 | 20.5354 | 1
[9 empty] | 599 | 21.5237 | 1 | [5 empty] | 599 | 22.6425 | 0 | [5 empty] | 599 | 19.4221 | 1
[9 empty] | 600 | 21.5654 | 1 | [5 empty] | 600 | 26.8546 | 0 | [5 empty] | 600 | 20.4014 | 1
[9 empty] | 601 | 22.3129 | 0 | [5 empty] | 601 | 25.3784 | 0 | [5 empty] | 601 | 17.865 | 1
[9 empty] | 602 | 21.7153 | 1 | [5 empty] | 602 | 23.096 | 0 | [5 empty] | 602 | 19.9814 | 1
[9 empty] | 603 | 22.7089 | 0 | [5 empty] | 603 | 23.2854 | 0 | [5 empty] | 603 | 19.8667 | 1
[9 empty] | 604 | 22.1627 | 0 | [5 empty] | 604 | 23.5274 | 0 | [5 empty] | 604 | 19.4148 | 1
[9 empty] | 605 | 20.5862 | 1 | [5 empty] | 605 | 24.4754 | 0 | [5 empty] | 605 | 18.3745 | 1
[9 empty] | 606 | 21.3283 | 1 | [5 empty] | 606 | 25.0989 | 0 | [5 empty] | 606 | 20.7796 | 1
[9 empty] | 607 | 24.2344 | 0 | [5 empty] | 607 | 26.4417 | 0 | [5 empty] | 607 | 18.6801 | 1
[9 empty] | 608 | 21.4765 | 1 | [5 empty] | 608 | 23.7481 | 0 | [5 empty] | 608 | 18.1858 | 1
[9 empty] | 609 | 22.3157 | 0 | [5 empty] | 609 | 26.0833 | 0 | [5 empty] | 609 | 18.1433 | 1
[9 empty] | 610 | 22.0227 | 0 | [5 empty] | 610 | 23.7736 | 0 | [5 empty] | 610 | 19.6071 | 1
[9 empty] | 611 | 23.3121 | 0 | [5 empty] | 611 | 23.9677 | 0 | [5 empty] | 611 | 20.2197 | 1
[9 empty] | 612 | 19.6367 | 1 | [5 empty] | 612 | 25.9231 | 0 | [5 empty] | 612 | 18.5923 | 1
[9 empty] | 613 | 22.3582 | 0 | [5 empty] | 613 | 24.2525 | 0 | [5 empty] | 613 | 19.9561 | 1
[9 empty] | 614 | 20.2768 | 1 | [5 empty] | 614 | 24.7511 | 0 | [5 empty] | 614 | 19.4995 | 1
[9 empty] | 615 | 21.1882 | 1 | [5 empty] | 615 | 26.0881 | 0 | [5 empty] | 615 | 21.1385 | 1
[9 empty] | 616 | 22.7669 | 0 | [5 empty] | 616 | 24.6602 | 0 | [5 empty] | 616 | 19.0526 | 1
[9 empty] | 617 | 20.5521 | 1 | [5 empty] | 617 | 22.6229 | 0 | [5 empty] | 617 | 19.7537 | 1
[9 empty] | 618 | 23.307 | 0 | [5 empty] | 618 | 24.6824 | 0 | [5 empty] | 618 | 21.4929 | 1
[9 empty] | 619 | 21.8416 | 1 | [5 empty] | 619 | 25.3482 | 0 | [5 empty] | 619 | 19.6759 | 1
[9 empty] | 620 | 23.6225 | 0 | [5 empty] | 620 | 23.4048 | 0 | [5 empty] | 620 | 19.8324 | 1
[9 empty] | 621 | 23.3994 | 0 | [5 empty] | 621 | 25.2444 | 0 | [5 empty] | 621 | 18.6624 | 1
[9 empty] | 622 | 21.1397 | 1 | [5 empty] | 622 | 26.1483 | 0 | [5 empty] | 622 | 19.5605 | 1
[9 empty] | 623 | 21.9247 | 1 | [5 empty] | 623 | 24.0942 | 0 | [5 empty] | 623 | 19.825 | 1
[9 empty] | 624 | 21.7881 | 1 | [5 empty] | 624 | 24.091 | 0 | [5 empty] | 624 | 21.1625 | 1
[9 empty] | 625 | 20.9425 | 1 | [5 empty] | 625 | 25.8244 | 0 | [5 empty] | 625 | 18.6961 | 1
[9 empty] | 626 | 22.2752 | 0 | [5 empty] | 626 | 23.3394 | 0 | [5 empty] | 626 | 20.8532 | 1
[9 empty] | 627 | 20.1914 | 1 | [5 empty] | 627 | 26.3591 | 0 | [5 empty] | 627 | 20.8892 | 1
[9 empty] | 628 | 20.2758 | 1 | [5 empty] | 628 | 24.4489 | 0 | [5 empty] | 628 | 17.6232 | 1
[9 empty] | 629 | 22.8904 | 0 | [5 empty] | 629 | 24.3056 | 0 | [5 empty] | 629 | 17.9657 | 1
[9 empty] | 630 | 20.3794 | 1 | [5 empty] | 630 | 26.1145 | 0 | [5 empty] | 630 | 19.2357 | 1
[9 empty] | 631 | 19.2195 | 1 | [5 empty] | 631 | 23.0505 | 0 | [5 empty] | 631 | 19.0128 | 1
[9 empty] | 632 | 22.7621 | 0 | [5 empty] | 632 | 24.6085 | 0 | [5 empty] | 632 | 19.6713 | 1
[9 empty] | 633 | 22.0165 | 0 | [5 empty] | 633 | 22.9564 | 0 | [5 empty] | 633 | 18.337 | 1
[9 empty] | 634 | 23.0703 | 0 | [5 empty] | 634 | 22.5134 | 0 | [5 empty] | 634 | 20.0821 | 1
[9 empty] | 635 | 22.5812 | 0 | [5 empty] | 635 | 24.5968 | 0 | [5 empty] | 635 | 18.3054 | 1
[9 empty] | 636 | 21.8934 | 1 | [5 empty] | 636 | 23.9041 | 0 | [5 empty] | 636 | 20.0605 | 1
[9 empty] | 637 | 20.475 | 1 | [5 empty] | 637 | 26.3465 | 0 | [5 empty] | 637 | 19.4327 | 1
[9 empty] | 638 | 22.3838 | 0 | [5 empty] | 638 | 23.9049 | 0 | [5 empty] | 638 | 21.1324 | 1
[9 empty] | 639 | 21.8117 | 1 | [5 empty] | 639 | 24.5806 | 0 | [5 empty] | 639 | 21.0209 | 1
[9 empty] | 640 | 21.6239 | 1 | [5 empty] | 640 | 24.5193 | 0 | [5 empty] | 640 | 18.9958 | 1
[9 empty] | 641 | 21.9298 | 1 | [5 empty] | 641 | 23.2516 | 0 | [5 empty] | 641 | 19.7811 | 1
[9 empty] | 642 | 21.8461 | 1 | [5 empty] | 642 | 23.1028 | 0 | [5 empty] | 642 | 20.0197 | 1
[9 empty] | 643 | 21.1325 | 1 | [5 empty] | 643 | 25.9613 | 0 | [5 empty] | 643 | 18.9829 | 1
[9 empty] | 644 | 21.1666 | 1 | [5 empty] | 644 | 24.0788 | 0 | [5 empty] | 644 | 19.124 | 1
[9 empty] | 645 | 22.2005 | 0 | [5 empty] | 645 | 25.0054 | 0 | [5 empty] | 645 | 21.7366 | 1
[9 empty] | 646 | 20.8684 | 1 | [5 empty] | 646 | 24.4763 | 0 | [5 empty] | 646 | 20.6991 | 1
[9 empty] | 647 | 19.9578 | 1 | [5 empty] | 647 | 22.7274 | 0 | [5 empty] | 647 | 18.0909 | 1
[9 empty] | 648 | 20.4514 | 1 | [5 empty] | 648 | 23.2959 | 0 | [5 empty] | 648 | 18.8786 | 1
[9 empty] | 649 | 23.3511 | 0 | [5 empty] | 649 | 22.5225 | 0 | [5 empty] | 649 | 19.3988 | 1
[9 empty] | 650 | 22.0851 | 0 | [5 empty] | 650 | 23.7013 | 0 | [5 empty] | 650 | 20.4453 | 1
[9 empty] | 651 | 21.3292 | 1 | [5 empty] | 651 | 23.7261 | 0 | [5 empty] | 651 | 19.7251 | 1
[9 empty] | 652 | 23.4664 | 0 | [5 empty] | 652 | 26.4466 | 0 | [5 empty] | 652 | 20.6497 | 1
[9 empty] | 653 | 22.527 | 0 | [5 empty] | 653 | 25.1025 | 0 | [5 empty] | 653 | 17.8821 | 1
[9 empty] | 654 | 21.1255 | 1 | [5 empty] | 654 | 25.3505 | 0 | [5 empty] | 654 | 21.1717 | 1
[9 empty] | 655 | 21.8747 | 1 | [5 empty] | 655 | 23.3075 | 0 | [5 empty] | 655 | 18.0097 | 1
[9 empty] | 656 | 20.5405 | 1 | [5 empty] | 656 | 23.4579 | 0 | [5 empty] | 656 | 21.0148 | 1
[9 empty] | 657 | 22.3575 | 0 | [5 empty] | 657 | 23.9786 | 0 | [5 empty] | 657 | 19.1429 | 1
[9 empty] | 658 | 21.8388 | 1 | [5 empty] | 658 | 22.7031 | 0 | [5 empty] | 658 | 19.3889 | 1
[9 empty] | 659 | 23.2089 | 0 | [5 empty] | 659 | 25.5902 | 0 | [5 empty] | 659 | 20.3577 | 1
[9 empty] | 660 | 23.9051 | 0 | [5 empty] | 660 | 24.824 | 0 | [5 empty] | 660 | 18.7656 | 1
[9 empty] | 661 | 22.0115 | 0 | [5 empty] | 661 | 25.7234 | 0 | [5 empty] | 661 | 18.9896 | 1
[9 empty] | 662 | 21.6701 | 1 | [5 empty] | 662 | 25.5066 | 0 | [5 empty] | 662 | 19.8641 | 1
[9 empty] | 663 | 23.2945 | 0 | [5 empty] | 663 | 25.8836 | 0 | [5 empty] | 663 | 17.8491 | 1
[9 empty] | 664 | 21.9677 | 1 | [5 empty] | 664 | 21.5099 | 1 | [5 empty] | 664 | 17.7813 | 1
[9 empty] | 665 | 21.3203 | 1 | [5 empty] | 665 | 23.9011 | 0 | [5 empty] | 665 | 19.4237 | 1
[9 empty] | 666 | 21.2052 | 1 | [5 empty] | 666 | 24.252 | 0 | [5 empty] | 666 | 19.5136 | 1
[9 empty] | 667 | 22.0193 | 0 | [5 empty] | 667 | 23.8222 | 0 | [5 empty] | 667 | 21.2973 | 1
[9 empty] | 668 | 23.3089 | 0 | [5 empty] | 668 | 21.6822 | 1 | [5 empty] | 668 | 20.1692 | 1
[9 empty] | 669 | 22.0914 | 0 | [5 empty] | 669 | 23.6365 | 0 | [5 empty] | 669 | 21.1821 | 1
[9 empty] | 670 | 21.6632 | 1 | [5 empty] | 670 | 25.0216 | 0 | [5 empty] | 670 | 19.3108 | 1
[9 empty] | 671 | 20.4033 | 1 | [5 empty] | 671 | 23.6787 | 0 | [5 empty] | 671 | 19.367 | 1
[9 empty] | 672 | 19.8831 | 1 | [5 empty] | 672 | 24.3916 | 0 | [5 empty] | 672 | 21.4093 | 1
[9 empty] | 673 | 22.5483 | 0 | [5 empty] | 673 | 25.7326 | 0 | [5 empty] | 673 | 18.3037 | 1
[9 empty] | 674 | 21.5865 | 1 | [5 empty] | 674 | 25.2274 | 0 | [5 empty] | 674 | 19.2337 | 1
[9 empty] | 675 | 20.6872 | 1 | [5 empty] | 675 | 22.7267 | 0 | [5 empty] | 675 | 18.2669 | 1
[9 empty] | 676 | 20.1345 | 1 | [5 empty] | 676 | 25.4294 | 0 | [5 empty] | 676 | 18.5733 | 1
[9 empty] | 677 | 23.0979 | 0 | [5 empty] | 677 | 23.2032 | 0 | [5 empty] | 677 | 18.7591 | 1
[9 empty] | 678 | 21.3233 | 1 | [5 empty] | 678 | 22.8519 | 0 | [5 empty] | 678 | 19.5015 | 1
[9 empty] | 679 | 23.505 | 0 | [5 empty] | 679 | 24.5592 | 0 | [5 empty] | 679 | 21.5884 | 1
[9 empty] | 680 | 23.2691 | 0 | [5 empty] | 680 | 24.3795 | 0 | [5 empty] | 680 | 17.9772 | 1
[9 empty] | 681 | 23.4414 | 0 | [5 empty] | 681 | 25.9592 | 0 | [5 empty] | 681 | 18.2123 | 1
[9 empty] | 682 | 20.585 | 1 | [5 empty] | 682 | 24.9255 | 0 | [5 empty] | 682 | 20.3807 | 1
[9 empty] | 683 | 24.1798 | 0 | [5 empty] | 683 | 24.6008 | 0 | [5 empty] | 683 | 20.2921 | 1
[9 empty] | 684 | 22.2074 | 0 | [5 empty] | 684 | 26.4574 | 0 | [5 empty] | 684 | 21.1603 | 1
[9 empty] | 685 | 22.2254 | 0 | [5 empty] | 685 | 24.9786 | 0 | [5 empty] | 685 | 21.8091 | 1
[9 empty] | 686 | 23.4288 | 0 | [5 empty] | 686 | 23.0638 | 0 | [5 empty] | 686 | 21.1116 | 1
[9 empty] | 687 | 21.9002 | 1 | [5 empty] | 687 | 21.7249 | 1 | [5 empty] | 687 | 19.6536 | 1
[9 empty] | 688 | 19.8763 | 1 | [5 empty] | 688 | 25.1983 | 0 | [5 empty] | 688 | 17.9436 | 1
[9 empty] | 689 | 23.5817 | 0 | [5 empty] | 689 | 23.7987 | 0 | [5 empty] | 689 | 18.8015 | 1
[9 empty] | 690 | 22.4875 | 0 | [5 empty] | 690 | 25.3098 | 0 | [5 empty] | 690 | 19.4061 | 1
[9 empty] | 691 | 20.2154 | 1 | [5 empty] | 691 | 22.2023 | 0 | [5 empty] | 691 | 20.4098 | 1
[9 empty] | 692 | 22.3956 | 0 | [5 empty] | 692 | 22.2481 | 0 | [5 empty] | 692 | 19.0225 | 1
[9 empty] | 693 | 21.9339 | 1 | [5 empty] | 693 | 26.1115 | 0 | [5 empty] | 693 | 19.1416 | 1
[9 empty] | 694 | 20.1833 | 1 | [5 empty] | 694 | 24.3001 | 0 | [5 empty] | 694 | 19.8573 | 1
[9 empty] | 695 | 22.7192 | 0 | [5 empty] | 695 | 25.4123 | 0 | [5 empty] | 695 | 20.2656 | 1
[9 empty] | 696 | 19.6566 | 1 | [5 empty] | 696 | 24.3806 | 0 | [5 empty] | 696 | 19.9784 | 1
[9 empty] | 697 | 20.3367 | 1 | [5 empty] | 697 | 20.5079 | 1 | [5 empty] | 697 | 17.6335 | 1
[9 empty] | 698 | 20.2467 | 1 | [5 empty] | 698 | 25.1835 | 0 | [5 empty] | 698 | 17.5254 | 1
[9 empty] | 699 | 20.2842 | 1 | [5 empty] | 699 | 23.3483 | 0 | [5 empty] | 699 | 17.2392 | 1
[9 empty] | 700 | 22.8271 | 0 | [5 empty] | 700 | 25.9274 | 0 | [5 empty] | 700 | 21.7358 | 1
[9 empty] | 701 | 22.6585 | 0 | [5 empty] | 701 | 24.4148 | 0 | [5 empty] | 701 | 18.986 | 1
[9 empty] | 702 | 21.4625 | 1 | [5 empty] | 702 | 24.2373 | 0 | [5 empty] | 702 | 22.6558 | 0
[9 empty] | 703 | 21.67 | 1 | [5 empty] | 703 | 25.739 | 0 | [5 empty] | 703 | 18.258 | 1
[9 empty] | 704 | 21.552 | 1 | [5 empty] | 704 | 21.5564 | 1 | [5 empty] | 704 | 17.0882 | 1
[9 empty] | 705 | 20.3815 | 1 | [5 empty] | 705 | 25.791 | 0 | [5 empty] | 705 | 20.9261 | 1
[9 empty] | 706 | 20.1565 | 1 | [5 empty] | 706 | 25.6003 | 0 | [5 empty] | 706 | 19.9484 | 1
[9 empty] | 707 | 23.0833 | 0 | [5 empty] | 707 | 23.5534 | 0 | [5 empty] | 707 | 19.2633 | 1
[9 empty] | 708 | 22.2245 | 0 | [5 empty] | 708 | 23.6804 | 0 | [5 empty] | 708 | 21.1373 | 1
[9 empty] | 709 | 21.3284 | 1 | [5 empty] | 709 | 24.2129 | 0 | [5 empty] | 709 | 18.1762 | 1
[9 empty] | 710 | 22.8459 | 0 | [5 empty] | 710 | 24.704 | 0 | [5 empty] | 710 | 18.4902 | 1
[9 empty] | 711 | 19.6694 | 1 | [5 empty] | 711 | 25.564 | 0 | [5 empty] | 711 | 17.7563 | 1
[9 empty] | 712 | 22.9233 | 0 | [5 empty] | 712 | 24.447 | 0 | [5 empty] | 712 | 17.7915 | 1
[9 empty] | 713 | 23.7216 | 0 | [5 empty] | 713 | 23.6864 | 0 | [5 empty] | 713 | 20.3332 | 1
[9 empty] | 714 | 22.6683 | 0 | [5 empty] | 714 | 22.8272 | 0 | [5 empty] | 714 | 19.6625 | 1
[9 empty] | 715 | 22.3652 | 0 | [5 empty] | 715 | 23.5409 | 0 | [5 empty] | 715 | 20.091 | 1
[9 empty] | 716 | 21.4145 | 1 | [5 empty] | 716 | 23.7386 | 0 | [5 empty] | 716 | 19.4966 | 1
[9 empty] | 717 | 23.9587 | 0 | [5 empty] | 717 | 22.6563 | 0 | [5 empty] | 717 | 19.0037 | 1
[9 empty] | 718 | 23.0036 | 0 | [5 empty] | 718 | 24.4623 | 0 | [5 empty] | 718 | 20.0374 | 1
[9 empty] | 719 | 23.429 | 0 | [5 empty] | 719 | 25.1503 | 0 | [5 empty] | 719 | 18.8064 | 1
[9 empty] | 720 | 21.8528 | 1 | [5 empty] | 720 | 25.8988 | 0 | [5 empty] | 720 | 20.1983 | 1
[9 empty] | 721 | 23.4809 | 0 | [5 empty] | 721 | 26.6638 | 0 | [5 empty] | 721 | 21.2351 | 1
[9 empty] | 722 | 20.7848 | 1 | [5 empty] | 722 | 23.0477 | 0 | [5 empty] | 722 | 19.4754 | 1
[9 empty] | 723 | 22.859 | 0 | [5 empty] | 723 | 24.9755 | 0 | [5 empty] | 723 | 19.3322 | 1
[9 empty] | 724 | 23.4742 | 0 | [5 empty] | 724 | 25.2217 | 0 | [5 empty] | 724 | 18.5509 | 1
[9 empty] | 725 | 21.9385 | 1 | [5 empty] | 725 | 24.2467 | 0 | [5 empty] | 725 | 19.8308 | 1
[9 empty] | 726 | 22.4211 | 0 | [5 empty] | 726 | 24.4133 | 0 | [5 empty] | 726 | 19.9559 | 1
[9 empty] | 727 | 22.0879 | 0 | [5 empty] | 727 | 22.7065 | 0 | [5 empty] | 727 | 19.9972 | 1
[9 empty] | 728 | 21.9169 | 1 | [5 empty] | 728 | 25.6814 | 0 | [5 empty] | 728 | 20.8212 | 1
[9 empty] | 729 | 22.2155 | 0 | [5 empty] | 729 | 25.2474 | 0 | [5 empty] | 729 | 21.0309 | 1
[9 empty] | 730 | 22.6696 | 0 | [5 empty] | 730 | 23.4113 | 0 | [5 empty] | 730 | 21.6979 | 1
[9 empty] | 731 | 21.6386 | 1 | [5 empty] | 731 | 23.7507 | 0 | [5 empty] | 731 | 19.9141 | 1
[9 empty] | 732 | 22.9702 | 0 | [5 empty] | 732 | 22.4498 | 0 | [5 empty] | 732 | 20.4238 | 1
[9 empty] | 733 | 21.7462 | 1 | [5 empty] | 733 | 26.3176 | 0 | [5 empty] | 733 | 18.7516 | 1
[9 empty] | 734 | 22.2464 | 0 | [5 empty] | 734 | 23.0059 | 0 | [5 empty] | 734 | 19.4879 | 1
[9 empty] | 735 | 20.3799 | 1 | [5 empty] | 735 | 25.4796 | 0 | [5 empty] | 735 | 19.7569 | 1
[9 empty] | 736 | 22.5603 | 0 | [5 empty] | 736 | 23.1753 | 0 | [5 empty] | 736 | 20.4804 | 1
[9 empty] | 737 | 22.7774 | 0 | [5 empty] | 737 | 24.1399 | 0 | [5 empty] | 737 | 20.732 | 1
[9 empty] | 738 | 21.7794 | 1 | [5 empty] | 738 | 23.9963 | 0 | [5 empty] | 738 | 18.2245 | 1
[9 empty] | 739 | 23.1015 | 0 | [5 empty] | 739 | 23.8735 | 0 | [5 empty] | 739 | 19.8007 | 1
[9 empty] | 740 | 23.7805 | 0 | [5 empty] | 740 | 26.4435 | 0 | [5 empty] | 740 | 19.7981 | 1
[9 empty] | 741 | 20.953 | 1 | [5 empty] | 741 | 24.4393 | 0 | [5 empty] | 741 | 20.5445 | 1
[9 empty] | 742 | 21.7996 | 1 | [5 empty] | 742 | 23.6773 | 0 | [5 empty] | 742 | 19.0159 | 1
[9 empty] | 743 | 22.0696 | 0 | [5 empty] | 743 | 23.9181 | 0 | [5 empty] | 743 | 20.4804 | 1
[9 empty] | 744 | 24.2384 | 0 | [5 empty] | 744 | 22.1654 | 0 | [5 empty] | 744 | 18.3784 | 1
[9 empty] | 745 | 19.9429 | 1 | [5 empty] | 745 | 23.9073 | 0 | [5 empty] | 745 | 20.124 | 1
[9 empty] | 746 | 21.1539 | 1 | [5 empty] | 746 | 23.1129 | 0 | [5 empty] | 746 | 19.5544 | 1
[9 empty] | 747 | 21.9972 | 1 | [5 empty] | 747 | 24.6426 | 0 | [5 empty] | 747 | 21.0301 | 1
[9 empty] | 748 | 22.3642 | 0 | [5 empty] | 748 | 25.8726 | 0 | [5 empty] | 748 | 20.7185 | 1
[9 empty] | 749 | 21.4618 | 1 | [5 empty] | 749 | 23.1004 | 0 | [5 empty] | 749 | 20.718 | 1
[9 empty] | 750 | 21.6897 | 1 | [5 empty] | 750 | 23.9215 | 0 | [5 empty] | 750 | 18.7671 | 1
[9 empty] | 751 | 22.4402 | 0 | [5 empty] | 751 | 23.0438 | 0 | [5 empty] | 751 | 19.1545 | 1
[9 empty] | 752 | 23.1302 | 0 | [5 empty] | 752 | 25.1324 | 0 | [5 empty] | 752 | 20.5048 | 1
[9 empty] | 753 | 22.5965 | 0 | [5 empty] | 753 | 23.5695 | 0 | [5 empty] | 753 | 21.4313 | 1
[9 empty] | 754 | 21.4393 | 1 | [5 empty] | 754 | 25.7866 | 0 | [5 empty] | 754 | 20.9763 | 1
[9 empty] | 755 | 20.6604 | 1 | [5 empty] | 755 | 26.6333 | 0 | [5 empty] | 755 | 20.3791 | 1
[9 empty] | 756 | 21.6591 | 1 | [5 empty] | 756 | 25.2833 | 0 | [5 empty] | 756 | 18.5073 | 1
[9 empty] | 757 | 23.0359 | 0 | [5 empty] | 757 | 24.4655 | 0 | [5 empty] | 757 | 19.2152 | 1
[9 empty] | 758 | 20.1648 | 1 | [5 empty] | 758 | 24.0616 | 0 | [5 empty] | 758 | 21.0617 | 1
[9 empty] | 759 | 23.9808 | 0 | [5 empty] | 759 | 22.7388 | 0 | [5 empty] | 759 | 17.8258 | 1
[9 empty] | 760 | 21.5429 | 1 | [5 empty] | 760 | 24.2172 | 0 | [5 empty] | 760 | 19.678 | 1
[9 empty] | 761 | 20.4491 | 1 | [5 empty] | 761 | 23.2527 | 0 | [5 empty] | 761 | 20.2429 | 1
[9 empty] | 762 | 22.605 | 0 | [5 empty] | 762 | 25.7387 | 0 | [5 empty] | 762 | 20.5668 | 1
[9 empty] | 763 | 23.0258 | 0 | [5 empty] | 763 | 25.1093 | 0 | [5 empty] | 763 | 19.7459 | 1
[9 empty] | 764 | 21.5011 | 1 | [5 empty] | 764 | 23.3824 | 0 | [5 empty] | 764 | 21.7877 | 1
[9 empty] | 765 | 21.7584 | 1 | [5 empty] | 765 | 24.7099 | 0 | [5 empty] | 765 | 22.1938 | 0
[9 empty] | 766 | 21.7321 | 1 | [5 empty] | 766 | 25.6407 | 0 | [5 empty] | 766 | 18.2289 | 1
[9 empty] | 767 | 23.0145 | 0 | [5 empty] | 767 | 23.2454 | 0 | [5 empty] | 767 | 19.7109 | 1
[9 empty] | 768 | 19.8868 | 1 | [5 empty] | 768 | 24.8533 | 0 | [5 empty] | 768 | 21.9772 | 1
[9 empty] | 769 | 22.3691 | 0 | [5 empty] | 769 | 22.0241 | 0 | [5 empty] | 769 | 20.3129 | 1
[9 empty] | 770 | 24.0586 | 0 | [5 empty] | 770 | 23.529 | 0 | [5 empty] | 770 | 21.2535 | 1
[9 empty] | 771 | 22.1127 | 0 | [5 empty] | 771 | 23.6508 | 0 | [5 empty] | 771 | 18.0308 | 1
[9 empty] | 772 | 21.433 | 1 | [5 empty] | 772 | 22.6673 | 0 | [5 empty] | 772 | 20.9812 | 1
[9 empty] | 773 | 20.7925 | 1 | [5 empty] | 773 | 25.9669 | 0 | [5 empty] | 773 | 18.8205 | 1
[9 empty] | 774 | 21.3907 | 1 | [5 empty] | 774 | 22.988 | 0 | [5 empty] | 774 | 18.0189 | 1
[9 empty] | 775 | 22.0465 | 0 | [5 empty] | 775 | 24.6426 | 0 | [5 empty] | 775 | 20.098 | 1
[9 empty] | 776 | 23.0798 | 0 | [5 empty] | 776 | 24.3027 | 0 | [5 empty] | 776 | 20.7283 | 1
[9 empty] | 777 | 23.3045 | 0 | [5 empty] | 777 | 24.0928 | 0 | [5 empty] | 777 | 18.8027 | 1
[9 empty] | 778 | 21.171 | 1 | [5 empty] | 778 | 23.51 | 0 | [5 empty] | 778 | 17.5531 | 1
[9 empty] | 779 | 20.2641 | 1 | [5 empty] | 779 | 22.9442 | 0 | [5 empty] | 779 | 18.553 | 1
[9 empty] | 780 | 22.9715 | 0 | [5 empty] | 780 | 21.2649 | 1 | [5 empty] | 780 | 19.263 | 1
[9 empty] | 781 | 22.4179 | 0 | [5 empty] | 781 | 22.99 | 0 | [5 empty] | 781 | 20.3539 | 1
[9 empty] | 782 | 22.7479 | 0 | [5 empty] | 782 | 24.0929 | 0 | [5 empty] | 782 | 19.0024 | 1
[9 empty] | 783 | 22.4704 | 0 | [5 empty] | 783 | 24.0177 | 0 | [5 empty] | 783 | 16.8486 | 1
[9 empty] | 784 | 22.9611 | 0 | [5 empty] | 784 | 23.7006 | 0 | [5 empty] | 784 | 19.4768 | 1
[9 empty] | 785 | 22.4282 | 0 | [5 empty] | 785 | 24.8594 | 0 | [5 empty] | 785 | 20.2769 | 1
[9 empty] | 786 | 20.3729 | 1 | [5 empty] | 786 | 23.0921 | 0 | [5 empty] | 786 | 22.0747 | 0
[9 empty] | 787 | 23.3107 | 0 | [5 empty] | 787 | 24.2595 | 0 | [5 empty] | 787 | 19.2203 | 1
[9 empty] | 788 | 24.0519 | 0 | [5 empty] | 788 | 24.8681 | 0 | [5 empty] | 788 | 20.0873 | 1
[9 empty] | 789 | 20.775 | 1 | [5 empty] | 789 | 24.6787 | 0 | [5 empty] | 789 | 20.3221 | 1
[9 empty] | 790 | 22.3988 | 0 | [5 empty] | 790 | 25.7107 | 0 | [5 empty] | 790 | 22.2835 | 0
[9 empty] | 791 | 22.0454 | 0 | [5 empty] | 791 | 25.4646 | 0 | [5 empty] | 791 | 18.1124 | 1
[9 empty] | 792 | 20.6839 | 1 | [5 empty] | 792 | 24.6194 | 0 | [5 empty] | 792 | 19.3779 | 1
[9 empty] | 793 | 23.3594 | 0 | [5 empty] | 793 | 24.8821 | 0 | [5 empty] | 793 | 20.8796 | 1
[9 empty] | 794 | 23.0925 | 0 | [5 empty] | 794 | 22.2032 | 0 | [5 empty] | 794 | 18.242 | 1
[9 empty] | 795 | 20.6829 | 1 | [5 empty] | 795 | 22.2097 | 0 | [5 empty] | 795 | 20.4109 | 1
[9 empty] | 796 | 21.1485 | 1 | [5 empty] | 796 | 24.3632 | 0 | [5 empty] | 796 | 20.2358 | 1
[9 empty] | 797 | 22.1295 | 0 | [5 empty] | 797 | 23.1866 | 0 | [5 empty] | 797 | 21.2662 | 1
[9 empty] | 798 | 21.4865 | 1 | [5 empty] | 798 | 23.7604 | 0 | [5 empty] | 798 | 19.7956 | 1
[9 empty] | 799 | 22.1487 | 0 | [5 empty] | 799 | 24.3425 | 0 | [5 empty] | 799 | 21.0978 | 1
[9 empty] | 800 | 22.7581 | 0 | [5 empty] | 800 | 23.3016 | 0 | [5 empty] | 800 | 19.123 | 1
[9 empty] | 801 | 20.8917 | 1 | [5 empty] | 801 | 23.3245 | 0 | [5 empty] | 801 | 18.816 | 1
[9 empty] | 802 | 22.2623 | 0 | [5 empty] | 802 | 25.7739 | 0 | [5 empty] | 802 | 19.4248 | 1
[9 empty] | 803 | 23.0808 | 0 | [5 empty] | 803 | 25.2108 | 0 | [5 empty] | 803 | 20.7405 | 1
[9 empty] | 804 | 21.5541 | 1 | [5 empty] | 804 | 22.6792 | 0 | [5 empty] | 804 | 18.1738 | 1
[9 empty] | 805 | 19.9907 | 1 | [5 empty] | 805 | 25.6268 | 0 | [5 empty] | 805 | 19.1579 | 1
[9 empty] | 806 | 22.6526 | 0 | [5 empty] | 806 | 25.5227 | 0 | [5 empty] | 806 | 19.3485 | 1
[9 empty] | 807 | 22.0962 | 0 | [5 empty] | 807 | 24.9356 | 0 | [5 empty] | 807 | 19.8809 | 1
[9 empty] | 808 | 22.614 | 0 | [5 empty] | 808 | 25.3718 | 0 | [5 empty] | 808 | 19.9833 | 1
[9 empty] | 809 | 23.3075 | 0 | [5 empty] | 809 | 26.0493 | 0 | [5 empty] | 809 | 18.3654 | 1
[9 empty] | 810 | 21.5987 | 1 | [5 empty] | 810 | 23.9447 | 0 | [5 empty] | 810 | 19.2825 | 1
[9 empty] | 811 | 21.3786 | 1 | [5 empty] | 811 | 27.0448 | 0 | [5 empty] | 811 | 21.8739 | 1
[9 empty] | 812 | 20.2517 | 1 | [5 empty] | 812 | 26.5576 | 0 | [5 empty] | 812 | 18.8134 | 1
[9 empty] | 813 | 20.2872 | 1 | [5 empty] | 813 | 25.3968 | 0 | [5 empty] | 813 | 20.6246 | 1
[9 empty] | 814 | 22.8385 | 0 | [5 empty] | 814 | 24.9582 | 0 | [5 empty] | 814 | 19.5608 | 1
[9 empty] | 815 | 23.417 | 0 | [5 empty] | 815 | 23.8808 | 0 | [5 empty] | 815 | 21.6786 | 1
[9 empty] | 816 | 22.0144 | 0 | [5 empty] | 816 | 22.8223 | 0 | [5 empty] | 816 | 21.9343 | 1
[9 empty] | 817 | 22.3937 | 0 | [5 empty] | 817 | 25.9607 | 0 | [5 empty] | 817 | 19.987 | 1
[9 empty] | 818 | 22.8064 | 0 | [5 empty] | 818 | 25.6846 | 0 | [5 empty] | 818 | 21.6914 | 1
[9 empty] | 819 | 21.3069 | 1 | [5 empty] | 819 | 22.2421 | 0 | [5 empty] | 819 | 19.0088 | 1
[9 empty] | 820 | 21.4108 | 1 | [5 empty] | 820 | 23.6118 | 0 | [5 empty] | 820 | 20.102 | 1
[9 empty] | 821 | 22.8848 | 0 | [5 empty] | 821 | 25.0288 | 0 | [5 empty] | 821 | 19.4073 | 1
[9 empty] | 822 | 23.25 | 0 | [5 empty] | 822 | 22.037 | 0 | [5 empty] | 822 | 19.0112 | 1
[9 empty] | 823 | 22.8999 | 0 | [5 empty] | 823 | 24.9189 | 0 | [5 empty] | 823 | 20.0464 | 1
[9 empty] | 824 | 20.9431 | 1 | [5 empty] | 824 | 24.3138 | 0 | [5 empty] | 824 | 20.1522 | 1
[9 empty] | 825 | 20.2198 | 1 | [5 empty] | 825 | 24.4043 | 0 | [5 empty] | 825 | 18.3069 | 1
[9 empty] | 826 | 23.4427 | 0 | [5 empty] | 826 | 24.6883 | 0 | [5 empty] | 826 | 20.8465 | 1
[9 empty] | 827 | 23.3839 | 0 | [5 empty] | 827 | 23.4217 | 0 | [5 empty] | 827 | 18.4462 | 1
[9 empty] | 828 | 21.1268 | 1 | [5 empty] | 828 | 22.5764 | 0 | [5 empty] | 828 | 20.2953 | 1
[9 empty] | 829 | 24.6792 | 0 | [5 empty] | 829 | 23.9985 | 0 | [5 empty] | 829 | 19.4232 | 1
[9 empty] | 830 | 21.1714 | 1 | [5 empty] | 830 | 22.4284 | 0 | [5 empty] | 830 | 20.6817 | 1
[9 empty] | 831 | 20.8496 | 1 | [5 empty] | 831 | 23.05 | 0 | [5 empty] | 831 | 21.2065 | 1
[9 empty] | 832 | 22.1207 | 0 | [5 empty] | 832 | 24.514 | 0 | [5 empty] | 832 | 17.4115 | 1
[9 empty] | 833 | 23.3056 | 0 | [5 empty] | 833 | 22.3924 | 0 | [5 empty] | 833 | 17.795 | 1
[9 empty] | 834 | 19.9548 | 1 | [5 empty] | 834 | 24.6452 | 0 | [5 empty] | 834 | 21.0242 | 1
[9 empty] | 835 | 21.7253 | 1 | [5 empty] | 835 | 23.5094 | 0 | [5 empty] | 835 | 18.5515 | 1
[9 empty] | 836 | 22.7724 | 0 | [5 empty] | 836 | 24.3506 | 0 | [5 empty] | 836 | 18.8767 | 1
[9 empty] | 837 | 20.9789 | 1 | [5 empty] | 837 | 21.0641 | 1 | [5 empty] | 837 | 20.2705 | 1
[9 empty] | 838 | 20.8215 | 1 | [5 empty] | 838 | 22.1792 | 0 | [5 empty] | 838 | 19.8973 | 1
[9 empty] | 839 | 23.5794 | 0 | [5 empty] | 839 | 24.9353 | 0 | [5 empty] | 839 | 20.6886 | 1
[9 empty] | 840 | 20.4947 | 1 | [5 empty] | 840 | 23.4935 | 0 | [5 empty] | 840 | 16.4601 | 1
[9 empty] | 841 | 20.03 | 1 | [5 empty] | 841 | 22.4262 | 0 | [5 empty] | 841 | 20.207 | 1
[9 empty] | 842 | 20.9887 | 1 | [5 empty] | 842 | 25.3638 | 0 | [5 empty] | 842 | 21.7485 | 1
[9 empty] | 843 | 22.0613 | 0 | [5 empty] | 843 | 23.6485 | 0 | [5 empty] | 843 | 17.3211 | 1
[9 empty] | 844 | 20.7852 | 1 | [5 empty] | 844 | 23.0364 | 0 | [5 empty] | 844 | 19.9282 | 1
[9 empty] | 845 | 20.7662 | 1 | [5 empty] | 845 | 24.4155 | 0 | [5 empty] | 845 | 20.544 | 1
[9 empty] | 846 | 21.7536 | 1 | [5 empty] | 846 | 22.357 | 0 | [5 empty] | 846 | 19.6902 | 1
[9 empty] | 847 | 22.2558 | 0 | [5 empty] | 847 | 25.995 | 0 | [5 empty] | 847 | 19.4032 | 1
[9 empty] | 848 | 23.9402 | 0 | [5 empty] | 848 | 24.7655 | 0 | [5 empty] | 848 | 22.3911 | 0
[9 empty] | 849 | 21.7208 | 1 | [5 empty] | 849 | 24.883 | 0 | [5 empty] | 849 | 21.2561 | 1
[9 empty] | 850 | 22.4866 | 0 | [5 empty] | 850 | 24.5173 | 0 | [5 empty] | 850 | 20.4953 | 1
[9 empty] | 851 | 21.7101 | 1 | [5 empty] | 851 | 23.4202 | 0 | [5 empty] | 851 | 18.9927 | 1
[9 empty] | 852 | 21.892 | 1 | [5 empty] | 852 | 25.6623 | 0 | [5 empty] | 852 | 22.7061 | 0
[9 empty] | 853 | 22.5246 | 0 | [5 empty] | 853 | 23.3561 | 0 | [5 empty] | 853 | 20.765 | 1
[9 empty] | 854 | 20.5835 | 1 | [5 empty] | 854 | 22.5432 | 0 | [5 empty] | 854 | 20.5054 | 1
[9 empty] | 855 | 21.4634 | 1 | [5 empty] | 855 | 24.4527 | 0 | [5 empty] | 855 | 20.3634 | 1
[9 empty] | 856 | 22.7704 | 0 | [5 empty] | 856 | 24.2584 | 0 | [5 empty] | 856 | 20.5569 | 1
[9 empty] | 857 | 21.0167 | 1 | [5 empty] | 857 | 26.5838 | 0 | [5 empty] | 857 | 21.0385 | 1
[9 empty] | 858 | 22.7613 | 0 | [5 empty] | 858 | 23.0557 | 0 | [5 empty] | 858 | 17.3788 | 1
[9 empty] | 859 | 23.0398 | 0 | [5 empty] | 859 | 25.4375 | 0 | [5 empty] | 859 | 18.7926 | 1
[9 empty] | 860 | 21.4331 | 1 | [5 empty] | 860 | 24.82 | 0 | [5 empty] | 860 | 21.5986 | 1
[9 empty] | 861 | 22.0616 | 0 | [5 empty] | 861 | 24.9163 | 0 | [5 empty] | 861 | 20.2886 | 1
[9 empty] | 862 | 23.7052 | 0 | [5 empty] | 862 | 25.4142 | 0 | [5 empty] | 862 | 19.5225 | 1
[9 empty] | 863 | 24.4259 | 0 | [5 empty] | 863 | 22.7859 | 0 | [5 empty] | 863 | 20.403 | 1
[9 empty] | 864 | 20.8306 | 1 | [5 empty] | 864 | 24.1167 | 0 | [5 empty] | 864 | 20.1806 | 1
[9 empty] | 865 | 21.1005 | 1 | [5 empty] | 865 | 25.1616 | 0 | [5 empty] | 865 | 18.3864 | 1
[9 empty] | 866 | 20.6174 | 1 | [5 empty] | 866 | 26.0128 | 0 | [5 empty] | 866 | 18.666 | 1
[9 empty] | 867 | 21.8372 | 1 | [5 empty] | 867 | 26.1434 | 0 | [5 empty] | 867 | 18.6992 | 1
[9 empty] | 868 | 21.718 | 1 | [5 empty] | 868 | 21.2275 | 1 | [5 empty] | 868 | 21.1282 | 1
[9 empty] | 869 | 24.0507 | 0 | [5 empty] | 869 | 23.7379 | 0 | [5 empty] | 869 | 19.9886 | 1
[9 empty] | 870 | 23.9707 | 0 | [5 empty] | 870 | 24.8441 | 0 | [5 empty] | 870 | 20.384 | 1
[9 empty] | 871 | 22.2682 | 0 | [5 empty] | 871 | 20.6053 | 1 | [5 empty] | 871 | 22.5434 | 0
[9 empty] | 872 | 22.2255 | 0 | [5 empty] | 872 | 23.9892 | 0 | [5 empty] | 872 | 20.7971 | 1
[9 empty] | 873 | 21.8869 | 1 | [5 empty] | 873 | 26.5052 | 0 | [5 empty] | 873 | 20.2768 | 1
[9 empty] | 874 | 22.9434 | 0 | [5 empty] | 874 | 24.5786 | 0 | [5 empty] | 874 | 21.2244 | 1
[9 empty] | 875 | 20.9553 | 1 | [5 empty] | 875 | 24.3728 | 0 | [5 empty] | 875 | 20.9591 | 1
[9 empty] | 876 | 21.3346 | 1 | [5 empty] | 876 | 25.4476 | 0 | [5 empty] | 876 | 17.9385 | 1
[9 empty] | 877 | 24.4509 | 0 | [5 empty] | 877 | 24.5044 | 0 | [5 empty] | 877 | 17.0727 | 1
[9 empty] | 878 | 22.1742 | 0 | [5 empty] | 878 | 24.2258 | 0 | [5 empty] | 878 | 19.3911 | 1
[9 empty] | 879 | 21.7891 | 1 | [5 empty] | 879 | 25.3832 | 0 | [5 empty] | 879 | 21.5266 | 1
[9 empty] | 880 | 21.1578 | 1 | [5 empty] | 880 | 22.9241 | 0 | [5 empty] | 880 | 18.022 | 1
[9 empty] | 881 | 21.4495 | 1 | [5 empty] | 881 | 22.6278 | 0 | [5 empty] | 881 | 18.7855 | 1
[9 empty] | 882 | 22.433 | 0 | [5 empty] | 882 | 24.8475 | 0 | [5 empty] | 882 | 20.0174 | 1
[9 empty] | 883 | 22.0504 | 0 | [5 empty] | 883 | 25.1 | 0 | [5 empty] | 883 | 18.9162 | 1
[9 empty] | 884 | 22.6232 | 0 | [5 empty] | 884 | 25.424 | 0 | [5 empty] | 884 | 18.416 | 1
[9 empty] | 885 | 24.1152 | 0 | [5 empty] | 885 | 20.1174 | 1 | [5 empty] | 885 | 20.3018 | 1
[9 empty] | 886 | 23.7021 | 0 | [5 empty] | 886 | 24.7286 | 0 | [5 empty] | 886 | 18.8221 | 1
[9 empty] | 887 | 20.5529 | 1 | [5 empty] | 887 | 25.1189 | 0 | [5 empty] | 887 | 20.3822 | 1
[9 empty] | 888 | 21.4517 | 1 | [5 empty] | 888 | 25.615 | 0 | [5 empty] | 888 | 19.591 | 1
[9 empty] | 889 | 22.4036 | 0 | [5 empty] | 889 | 24.5791 | 0 | [5 empty] | 889 | 18.0959 | 1
[9 empty] | 890 | 21.6156 | 1 | [5 empty] | 890 | 23.4182 | 0 | [5 empty] | 890 | 20.2377 | 1
[9 empty] | 891 | 22.1823 | 0 | [5 empty] | 891 | 24.4009 | 0 | [5 empty] | 891 | 19.2455 | 1
[9 empty] | 892 | 21.7414 | 1 | [5 empty] | 892 | 22.2548 | 0 | [5 empty] | 892 | 19.8477 | 1
[9 empty] | 893 | 22.2827 | 0 | [5 empty] | 893 | 24.6758 | 0 | [5 empty] | 893 | 20.9568 | 1
[9 empty] | 894 | 19.1104 | 1 | [5 empty] | 894 | 22.9039 | 0 | [5 empty] | 894 | 16.9963 | 1
[9 empty] | 895 | 20.7044 | 1 | [5 empty] | 895 | 24.0405 | 0 | [5 empty] | 895 | 19.9403 | 1
[9 empty] | 896 | 22.2083 | 0 | [5 empty] | 896 | 25.0451 | 0 | [5 empty] | 896 | 19.1089 | 1
[9 empty] | 897 | 20.8332 | 1 | [5 empty] | 897 | 25.1946 | 0 | [5 empty] | 897 | 19.8293 | 1
[9 empty] | 898 | 23.5902 | 0 | [5 empty] | 898 | 23.6348 | 0 | [5 empty] | 898 | 21.5622 | 1
[9 empty] | 899 | 24.2529 | 0 | [5 empty] | 899 | 24.2822 | 0 | [5 empty] | 899 | 18.4904 | 1
[9 empty] | 900 | 20.3247 | 1 | [5 empty] | 900 | 20.5509 | 1 | [5 empty] | 900 | 19.4838 | 1
[9 empty] | 901 | 23.6769 | 0 | [5 empty] | 901 | 24.3534 | 0 | [5 empty] | 901 | 19.4655 | 1
[9 empty] | 902 | 24.0878 | 0 | [5 empty] | 902 | 21.3138 | 1 | [5 empty] | 902 | 20.9608 | 1
[9 empty] | 903 | 21.4888 | 1 | [5 empty] | 903 | 23.2757 | 0 | [5 empty] | 903 | 21.4122 | 1
[9 empty] | 904 | 22.245 | 0 | [5 empty] | 904 | 24.6428 | 0 | [5 empty] | 904 | 18.6218 | 1
[9 empty] | 905 | 21.32 | 1 | [5 empty] | 905 | 25.5885 | 0 | [5 empty] | 905 | 17.8979 | 1
[9 empty] | 906 | 23.2127 | 0 | [5 empty] | 906 | 24.8178 | 0 | [5 empty] | 906 | 19.8822 | 1
[9 empty] | 907 | 21.3713 | 1 | [5 empty] | 907 | 23.3204 | 0 | [5 empty] | 907 | 19.4006 | 1
[9 empty] | 908 | 21.667 | 1 | [5 empty] | 908 | 24.4765 | 0 | [5 empty] | 908 | 20.2223 | 1
[9 empty] | 909 | 19.6669 | 1 | [5 empty] | 909 | 23.0251 | 0 | [5 empty] | 909 | 19.3477 | 1
[9 empty] | 910 | 20.958 | 1 | [5 empty] | 910 | 26.5587 | 0 | [5 empty] | 910 | 19.152 | 1
[9 empty] | 911 | 22.3076 | 0 | [5 empty] | 911 | 22.4249 | 0 | [5 empty] | 911 | 19.0672 | 1
[9 empty] | 912 | 20.5815 | 1 | [5 empty] | 912 | 24.454 | 0 | [5 empty] | 912 | 19.3339 | 1
[9 empty] | 913 | 21.4248 | 1 | [5 empty] | 913 | 23.6622 | 0 | [5 empty] | 913 | 18.1775 | 1
[9 empty] | 914 | 21.5781 | 1 | [5 empty] | 914 | 21.9413 | 1 | [5 empty] | 914 | 19.1028 | 1
[9 empty] | 915 | 21.8526 | 1 | [5 empty] | 915 | 22.8284 | 0 | [5 empty] | 915 | 21.3025 | 1
[9 empty] | 916 | 21.6949 | 1 | [5 empty] | 916 | 23.506 | 0 | [5 empty] | 916 | 17.9142 | 1
[9 empty] | 917 | 19.3927 | 1 | [5 empty] | 917 | 25.8836 | 0 | [5 empty] | 917 | 19.8611 | 1
[9 empty] | 918 | 22.3076 | 0 | [5 empty] | 918 | 24.9015 | 0 | [5 empty] | 918 | 18.829 | 1
[9 empty] | 919 | 23.3002 | 0 | [5 empty] | 919 | 24.7725 | 0 | [5 empty] | 919 | 19.1306 | 1
[9 empty] | 920 | 22.3155 | 0 | [5 empty] | 920 | 26.0381 | 0 | [5 empty] | 920 | 18.4766 | 1
[9 empty] | 921 | 20.5726 | 1 | [5 empty] | 921 | 27.0733 | 0 | [5 empty] | 921 | 22.4627 | 0
[9 empty] | 922 | 22.4815 | 0 | [5 empty] | 922 | 26.3857 | 0 | [5 empty] | 922 | 21.6636 | 1
[9 empty] | 923 | 22.284 | 0 | [5 empty] | 923 | 24.9414 | 0 | [5 empty] | 923 | 22.0207 | 0
[9 empty] | 924 | 20.0431 | 1 | [5 empty] | 924 | 23.0518 | 0 | [5 empty] | 924 | 20.3664 | 1
[9 empty] | 925 | 22.6377 | 0 | [5 empty] | 925 | 24.6449 | 0 | [5 empty] | 925 | 19.3994 | 1
[9 empty] | 926 | 22.6581 | 0 | [5 empty] | 926 | 25.421 | 0 | [5 empty] | 926 | 19.5126 | 1
[9 empty] | 927 | 22.3853 | 0 | [5 empty] | 927 | 23.1247 | 0 | [5 empty] | 927 | 20.4317 | 1
[9 empty] | 928 | 20.8699 | 1 | [5 empty] | 928 | 24.3309 | 0 | [5 empty] | 928 | 18.7346 | 1
[9 empty] | 929 | 21.5616 | 1 | [5 empty] | 929 | 25.0633 | 0 | [5 empty] | 929 | 20.2164 | 1
[9 empty] | 930 | 21.9201 | 1 | [5 empty] | 930 | 24.5796 | 0 | [5 empty] | 930 | 18.9334 | 1
[9 empty] | 931 | 22.1414 | 0 | [5 empty] | 931 | 25.4528 | 0 | [5 empty] | 931 | 17.191 | 1
[9 empty] | 932 | 22.9972 | 0 | [5 empty] | 932 | 23.2341 | 0 | [5 empty] | 932 | 20.1506 | 1
[9 empty] | 933 | 22.9973 | 0 | [5 empty] | 933 | 26.1073 | 0 | [5 empty] | 933 | 18.6245 | 1
[9 empty] | 934 | 23.4131 | 0 | [5 empty] | 934 | 23.612 | 0 | [5 empty] | 934 | 19.4955 | 1
[9 empty] | 935 | 22.4787 | 0 | [5 empty] | 935 | 23.3821 | 0 | [5 empty] | 935 | 21.2529 | 1
[9 empty] | 936 | 22.7601 | 0 | [5 empty] | 936 | 25.2441 | 0 | [5 empty] | 936 | 17.5782 | 1
[9 empty] | 937 | 20.432 | 1 | [5 empty] | 937 | 24.775 | 0 | [5 empty] | 937 | 20.3622 | 1
[9 empty] | 938 | 24.5501 | 0 | [5 empty] | 938 | 25.1969 | 0 | [5 empty] | 938 | 18.6281 | 1
[9 empty] | 939 | 21.6152 | 1 | [5 empty] | 939 | 21.6236 | 1 | [5 empty] | 939 | 19.8795 | 1
[9 empty] | 940 | 19.8855 | 1 | [5 empty] | 940 | 24.0761 | 0 | [5 empty] | 940 | 21.5169 | 1
[9 empty] | 941 | 21.1549 | 1 | [5 empty] | 941 | 23.6213 | 0 | [5 empty] | 941 | 21.3381 | 1
[9 empty] | 942 | 20.7176 | 1 | [5 empty] | 942 | 23.2243 | 0 | [5 empty] | 942 | 19.1271 | 1
[9 empty] | 943 | 23.0309 | 0 | [5 empty] | 943 | 24.9756 | 0 | [5 empty] | 943 | 18.5912 | 1
[9 empty] | 944 | 21.1777 | 1 | [5 empty] | 944 | 25.8405 | 0 | [5 empty] | 944 | 17.2849 | 1
[9 empty] | 945 | 22.1231 | 0 | [5 empty] | 945 | 21.5639 | 1 | [5 empty] | 945 | 21.5326 | 1
[9 empty] | 946 | 21.3111 | 1 | [5 empty] | 946 | 24.1989 | 0 | [5 empty] | 946 | 21.2062 | 1
[9 empty] | 947 | 20.4435 | 1 | [5 empty] | 947 | 22.5924 | 0 | [5 empty] | 947 | 19.4596 | 1
[9 empty] | 948 | 20.0598 | 1 | [5 empty] | 948 | 25.7491 | 0 | [5 empty] | 948 | 20.4672 | 1
[9 empty] | 949 | 20.4582 | 1 | [5 empty] | 949 | 22.7538 | 0 | [5 empty] | 949 | 20.5012 | 1
[9 empty] | 950 | 22.1293 | 0 | [5 empty] | 950 | 24.7834 | 0 | [5 empty] | 950 | 21.1186 | 1
[9 empty] | 951 | 23.2651 | 0 | [5 empty] | 951 | 22.8219 | 0 | [5 empty] | 951 | 20.5459 | 1
[9 empty] | 952 | 21.4894 | 1 | [5 empty] | 952 | 25.3742 | 0 | [5 empty] | 952 | 20.6406 | 1
[9 empty] | 953 | 21.6313 | 1 | [5 empty] | 953 | 24.9454 | 0 | [5 empty] | 953 | 20.2098 | 1
[9 empty] | 954 | 21.1577 | 1 | [5 empty] | 954 | 23.862 | 0 | [5 empty] | 954 | 21.4415 | 1
[9 empty] | 955 | 22.4838 | 0 | [5 empty] | 955 | 25.584 | 0 | [5 empty] | 955 | 20.0533 | 1
[9 empty] | 956 | 24.2397 | 0 | [5 empty] | 956 | 23.5846 | 0 | [5 empty] | 956 | 20.5482 | 1
[9 empty] | 957 | 21.2687 | 1 | [5 empty] | 957 | 26.1255 | 0 | [5 empty] | 957 | 20.3095 | 1
[9 empty] | 958 | 20.4999 | 1 | [5 empty] | 958 | 24.5651 | 0 | [5 empty] | 958 | 19.0927 | 1
[9 empty] | 959 | 19.9879 | 1 | [5 empty] | 959 | 23.4731 | 0 | [5 empty] | 959 | 18.2235 | 1
[9 empty] | 960 | 21.1158 | 1 | [5 empty] | 960 | 25.8376 | 0 | [5 empty] | 960 | 20.3064 | 1
[9 empty] | 961 | 22.6204 | 0 | [5 empty] | 961 | 25.9167 | 0 | [5 empty] | 961 | 18.6479 | 1
[9 empty] | 962 | 22.2557 | 0 | [5 empty] | 962 | 25.0665 | 0 | [5 empty] | 962 | 20.3029 | 1
[9 empty] | 963 | 23.6672 | 0 | [5 empty] | 963 | 23.2686 | 0 | [5 empty] | 963 | 19.1472 | 1
[9 empty] | 964 | 21.2274 | 1 | [5 empty] | 964 | 25.817 | 0 | [5 empty] | 964 | 21.001 | 1
[9 empty] | 965 | 23.1031 | 0 | [5 empty] | 965 | 24.0758 | 0 | [5 empty] | 965 | 21.6451 | 1
[9 empty] | 966 | 23.4714 | 0 | [5 empty] | 966 | 23.4309 | 0 | [5 empty] | 966 | 21.019 | 1
[9 empty] | 967 | 21.2462 | 1 | [5 empty] | 967 | 22.7287 | 0 | [5 empty] | 967 | 19.9828 | 1
[9 empty] | 968 | 22.8227 | 0 | [5 empty] | 968 | 24.9038 | 0 | [5 empty] | 968 | 21.6524 | 1
[9 empty] | 969 | 22.6141 | 0 | [5 empty] | 969 | 22.6116 | 0 | [5 empty] | 969 | 17.9544 | 1
[9 empty] | 970 | 23.0434 | 0 | [5 empty] | 970 | 21.745 | 1 | [5 empty] | 970 | 19.2588 | 1
[9 empty] | 971 | 22.9761 | 0 | [5 empty] | 971 | 23.0167 | 0 | [5 empty] | 971 | 21.4876 | 1
[9 empty] | 972 | 21.4056 | 1 | [5 empty] | 972 | 24.665 | 0 | [5 empty] | 972 | 20.2654 | 1
[9 empty] | 973 | 23.1843 | 0 | [5 empty] | 973 | 21.7178 | 1 | [5 empty] | 973 | 18.4587 | 1
[9 empty] | 974 | 22.0277 | 0 | [5 empty] | 974 | 23.5673 | 0 | [5 empty] | 974 | 19.9671 | 1
[9 empty] | 975 | 20.4938 | 1 | [5 empty] | 975 | 24.4486 | 0 | [5 empty] | 975 | 20.6391 | 1
[9 empty] | 976 | 23.07 | 0 | [5 empty] | 976 | 22.7615 | 0 | [5 empty] | 976 | 19.1342 | 1
[9 empty] | 977 | 23.2417 | 0 | [5 empty] | 977 | 23.4975 | 0 | [5 empty] | 977 | 18.2375 | 1
[9 empty] | 978 | 22.218 | 0 | [5 empty] | 978 | 23.2645 | 0 | [5 empty] | 978 | 18.8269 | 1
[9 empty] | 979 | 22.046 | 0 | [5 empty] | 979 | 25.5553 | 0 | [5 empty] | 979 | 20.8635 | 1
[9 empty] | 980 | 22.8738 | 0 | [5 empty] | 980 | 26.6844 | 0 | [5 empty] | 980 | 20.0548 | 1
[9 empty] | 981 | 21.5557 | 1 | [5 empty] | 981 | 23.7796 | 0 | [5 empty] | 981 | 18.0218 | 1
[9 empty] | 982 | 22.1716 | 0 | [5 empty] | 982 | 23.7032 | 0 | [5 empty] | 982 | 19.5229 | 1
[9 empty] | 983 | 19.9799 | 1 | [5 empty] | 983 | 24.9082 | 0 | [5 empty] | 983 | 20.5677 | 1
[9 empty] | 984 | 20.2817 | 1 | [5 empty] | 984 | 24.2369 | 0 | [5 empty] | 984 | 21.0869 | 1
[9 empty] | 985 | 22.1613 | 0 | [5 empty] | 985 | 22.7169 | 0 | [5 empty] | 985 | 19.218 | 1
[9 empty] | 986 | 22.6668 | 0 | [5 empty] | 986 | 25.2318 | 0 | [5 empty] | 986 | 20.3733 | 1
[9 empty] | 987 | 21.4466 | 1 | [5 empty] | 987 | 25.572 | 0 | [5 empty] | 987 | 19.9331 | 1
[9 empty] | 988 | 22.5126 | 0 | [5 empty] | 988 | 22.3937 | 0 | [5 empty] | 988 | 18.1776 | 1
[9 empty] | 989 | 22.2003 | 0 | [5 empty] | 989 | 23.8045 | 0 | [5 empty] | 989 | 21.4831 | 1
[9 empty] | 990 | 21.1238 | 1 | [5 empty] | 990 | 24.2288 | 0 | [5 empty] | 990 | 18.5386 | 1
[9 empty] | 991 | 22.6947 | 0 | [5 empty] | 991 | 23.38 | 0 | [5 empty] | 991 | 22.1139 | 0
[9 empty] | 992 | 24.1284 | 0 | [5 empty] | 992 | 24.2452 | 0 | [5 empty] | 992 | 19.8927 | 1
[9 empty] | 993 | 21.4228 | 1 | [5 empty] | 993 | 22.751 | 0 | [5 empty] | 993 | 18.1015 | 1
[9 empty] | 994 | 22.559 | 0 | [5 empty] | 994 | 23.3375 | 0 | [5 empty] | 994 | 21.8308 | 1
[9 empty] | 995 | 20.3671 | 1 | [5 empty] | 995 | 22.6259 | 0 | [5 empty] | 995 | 20.002 | 1
[9 empty] | 996 | 20.4312 | 1 | [5 empty] | 996 | 22.0851 | 0 | [5 empty] | 996 | 18.1601 | 1
[9 empty] | 997 | 21.7646 | 1 | [5 empty] | 997 | 24.0644 | 0 | [5 empty] | 997 | 21.3915 | 1
[9 empty] | 998 | 21.0406 | 1 | [5 empty] | 998 | 23.3392 | 0 | [5 empty] | 998 | 19.9422 | 1
[9 empty] | 999 | 21.3965 | 1 | [5 empty] | 999 | 24.4029 | 0 | [5 empty] | 999 | 20.5785 | 1
[9 empty] | 1000 | 20.1102 | 1 | [5 empty] | 1000 | 23.8445 | 0 | [5 empty] | 1000 | 18.9888 | 1

## Sheet2
Project 2 | 38
[6 empty] | triangular | [7 empty] | right-triangular | [7 empty] | left-triangular
activity | immediate predecessor | a | m | b | rand | start time | duration | finish time | trial | project duration | success | average duration | success rate | start time | duration | finish time | trial | project duration | success | average duration | success rate | start time | duration | finish time | trial | project duration | success | average duration | success rate
A |  | 1 | 4 | 13 | 0.53793 | 0 | 5.9358 | 5.9358 |  | 35.4795 | 1 | 38.004 | 0.528 | 0 | 3.8339 | 3.8339 |  | 45.7678 | 0 | 45.7167 | 0.025 | 0 | 5.2113 | 5.2113 |  | 37.9413 | 1 | 35.8872 | 0.72
B | A | 4 | 7 | 16 | 0.53824 | 5.9358 | 8.9381 | 14.8739 | 1 | 45.5177 | 0 |  |  | 3.8339 | 6.4095 | 10.2434 | 1 | 43.8949 | 0 |  |  | 5.2113 | 14.0232 | 19.2346 | 1 | 32.3664 | 1
C | A | 2 | 2 | 2 | 0.23166 | 5.9358 | 2 | 7.9358 | 2 | 37.6892 | 1 |  |  | 3.8339 | 2 | 5.8339 | 2 | 40.6547 | 0 |  |  | 5.2113 | 2 | 7.2113 | 2 | 33.8396 | 1
D | C | 4 | 6 | 14 | 0.2981 | 7.9358 | 6.5065 | 14.4423 | 3 | 31.8426 | 1 |  |  | 5.8339 | 13.8931 | 19.7269 | 3 | 42.5576 | 0 |  |  | 7.2113 | 10.9828 | 18.1942 | 3 | 32.6205 | 1
E |  | 1 | 3 | 5 | 0.068239 | 0 | 1.7389 | 1.7389 | 4 | 34.6671 | 1 |  |  | 0 | 4.6142 | 4.6142 | 4 | 49.8604 | 0 |  |  | 0 | 1.2357 | 1.2357 | 4 | 38.2112 | 0
F | E | 3 | 5 | 13 | 0.90364 | 1.7389 | 10.2236 | 11.9625 | 5 | 34.9072 | 1 |  |  | 4.6142 | 8.5897 | 13.2039 | 5 | 41.3913 | 0 |  |  | 1.2357 | 8.4918 | 9.7274 | 5 | 37.7068 | 1
G |  | 7 | 10 | 13 | 0.080513 | 0 | 8.2038 | 8.2038 | 6 | 39.8798 | 0 |  |  | 0 | 11.9322 | 11.9322 | 6 | 40.3745 | 0 |  |  | 0 | 9.4923 | 9.4923 | 6 | 33.3517 | 1
H | G | 6 | 7 | 14 | 0.44779 | 8.2038 | 8.4391 | 16.6429 | 7 | 41.3722 | 0 |  |  | 11.9322 | 13.0379 | 24.9701 | 7 | 50.7034 | 0 |  |  | 9.4923 | 7.0089 | 16.5012 | 7 | 31.5568 | 1
I | B,D | 1 | 1 | 1 | 0.63036 | 14.8739 | 1 | 15.8739 | 8 | 32.0381 | 1 |  |  | 19.7269 | 1 | 20.7269 | 8 | 48.6656 | 0 |  |  | 19.2346 | 1 | 20.2346 | 8 | 38.5941 | 0
J | F,H,I | 13 | 16 | 25 | 0.64826 | 16.6429 | 18.8366 | 35.4795 | 9 | 39.0757 | 0 |  |  | 24.9701 | 20.7977 | 45.7678 | 9 | 41.7776 | 0 |  |  | 20.2346 | 17.7068 | 37.9413 | 9 | 38.8786 | 0
[9 empty] | 10 | 41.1893 | 0 | [5 empty] | 10 | 43.0215 | 0 | [5 empty] | 10 | 37.3335 | 1
[9 empty] | 11 | 31.0542 | 1 | [5 empty] | 11 | 43.8456 | 0 | [5 empty] | 11 | 33.8583 | 1
[9 empty] | 12 | 39.2401 | 0 | [5 empty] | 12 | 52.4342 | 0 | [5 empty] | 12 | 36.7377 | 1
[9 empty] | 13 | 35.5315 | 1 | [5 empty] | 13 | 32.9316 | 1 | [5 empty] | 13 | 27.5028 | 1
[9 empty] | 14 | 43.6488 | 0 | [5 empty] | 14 | 51.4121 | 0 | [5 empty] | 14 | 39.8798 | 0
[9 empty] | 15 | 46.9371 | 0 | [5 empty] | 15 | 43.5787 | 0 | [5 empty] | 15 | 33.5125 | 1
[9 empty] | 16 | 31.9192 | 1 | [5 empty] | 16 | 44.3664 | 0 | [5 empty] | 16 | 32.5791 | 1
[9 empty] | 17 | 42.0509 | 0 | [5 empty] | 17 | 54.0042 | 0 | [5 empty] | 17 | 32.5962 | 1
[9 empty] | 18 | 37.4216 | 1 | [5 empty] | 18 | 46.5736 | 0 | [5 empty] | 18 | 33.5091 | 1
[9 empty] | 19 | 35.5384 | 1 | [5 empty] | 19 | 49.5315 | 0 | [5 empty] | 19 | 35.4678 | 1
[9 empty] | 20 | 40.7066 | 0 | [5 empty] | 20 | 46.5736 | 0 | [5 empty] | 20 | 40.1049 | 0
[9 empty] | 21 | 35.7332 | 1 | [5 empty] | 21 | 48.0774 | 0 | [5 empty] | 21 | 35.2934 | 1
[9 empty] | 22 | 38.405 | 0 | [5 empty] | 22 | 44.6184 | 0 | [5 empty] | 22 | 35.3842 | 1
[9 empty] | 23 | 33.1448 | 1 | [5 empty] | 23 | 41.4904 | 0 | [5 empty] | 23 | 40.8881 | 0
[9 empty] | 24 | 37.6412 | 1 | [5 empty] | 24 | 41.4269 | 0 | [5 empty] | 24 | 36.9025 | 1
[9 empty] | 25 | 40.0824 | 0 | [5 empty] | 25 | 50.4907 | 0 | [5 empty] | 25 | 40.7256 | 0
[9 empty] | 26 | 36.3258 | 1 | [5 empty] | 26 | 40.3918 | 0 | [5 empty] | 26 | 34.4848 | 1
[9 empty] | 27 | 45.7058 | 0 | [5 empty] | 27 | 45.6677 | 0 | [5 empty] | 27 | 30.6323 | 1
[9 empty] | 28 | 45.489 | 0 | [5 empty] | 28 | 48.6001 | 0 | [5 empty] | 28 | 37.9593 | 1
[9 empty] | 29 | 39.0829 | 0 | [5 empty] | 29 | 46.3899 | 0 | [5 empty] | 29 | 27.3739 | 1
[9 empty] | 30 | 35.675 | 1 | [5 empty] | 30 | 43.1417 | 0 | [5 empty] | 30 | 33.8099 | 1
[9 empty] | 31 | 39.365 | 0 | [5 empty] | 31 | 49.5822 | 0 | [5 empty] | 31 | 35.5572 | 1
[9 empty] | 32 | 40.0186 | 0 | [5 empty] | 32 | 44.0324 | 0 | [5 empty] | 32 | 30.7363 | 1
[9 empty] | 33 | 36.8228 | 1 | [5 empty] | 33 | 40.9458 | 0 | [5 empty] | 33 | 39.4961 | 0
[9 empty] | 34 | 40.1979 | 0 | [5 empty] | 34 | 44.4809 | 0 | [5 empty] | 34 | 38.8965 | 0
[9 empty] | 35 | 32.9713 | 1 | [5 empty] | 35 | 46.3093 | 0 | [5 empty] | 35 | 40.2929 | 0
[9 empty] | 36 | 36.9634 | 1 | [5 empty] | 36 | 41.4504 | 0 | [5 empty] | 36 | 33.6922 | 1
[9 empty] | 37 | 32.2915 | 1 | [5 empty] | 37 | 42.2012 | 0 | [5 empty] | 37 | 40.2822 | 0
[9 empty] | 38 | 35.0748 | 1 | [5 empty] | 38 | 43.3044 | 0 | [5 empty] | 38 | 30.5619 | 1
[9 empty] | 39 | 35.3015 | 1 | [5 empty] | 39 | 46.5247 | 0 | [5 empty] | 39 | 30.5434 | 1
[9 empty] | 40 | 40.8027 | 0 | [5 empty] | 40 | 42.8232 | 0 | [5 empty] | 40 | 38.5732 | 0
[9 empty] | 41 | 38.9836 | 0 | [5 empty] | 41 | 42.1882 | 0 | [5 empty] | 41 | 37.1087 | 1
[9 empty] | 42 | 34.9991 | 1 | [5 empty] | 42 | 47.2576 | 0 | [5 empty] | 42 | 38.9346 | 0
[9 empty] | 43 | 38.083 | 0 | [5 empty] | 43 | 41.2489 | 0 | [5 empty] | 43 | 39.0933 | 0
[9 empty] | 44 | 35.5862 | 1 | [5 empty] | 44 | 48.8508 | 0 | [5 empty] | 44 | 40.1317 | 0
[9 empty] | 45 | 32.3429 | 1 | [5 empty] | 45 | 47.2512 | 0 | [5 empty] | 45 | 32.4136 | 1
[9 empty] | 46 | 36.6361 | 1 | [5 empty] | 46 | 42.6485 | 0 | [5 empty] | 46 | 38.4509 | 0
[9 empty] | 47 | 38.3566 | 0 | [5 empty] | 47 | 47.9071 | 0 | [5 empty] | 47 | 45.6061 | 0
[9 empty] | 48 | 40.2907 | 0 | [5 empty] | 48 | 50.4458 | 0 | [5 empty] | 48 | 29.1338 | 1
[9 empty] | 49 | 39.0147 | 0 | [5 empty] | 49 | 46.709 | 0 | [5 empty] | 49 | 34.6776 | 1
[9 empty] | 50 | 34.4732 | 1 | [5 empty] | 50 | 50.8851 | 0 | [5 empty] | 50 | 42.1324 | 0
[9 empty] | 51 | 40.7599 | 0 | [5 empty] | 51 | 45.8471 | 0 | [5 empty] | 51 | 37.3725 | 1
[9 empty] | 52 | 37.2558 | 1 | [5 empty] | 52 | 46.5018 | 0 | [5 empty] | 52 | 43.2905 | 0
[9 empty] | 53 | 41.1702 | 0 | [5 empty] | 53 | 46.9477 | 0 | [5 empty] | 53 | 40.2882 | 0
[9 empty] | 54 | 42.3466 | 0 | [5 empty] | 54 | 44.7578 | 0 | [5 empty] | 54 | 34.4858 | 1
[9 empty] | 55 | 33.7891 | 1 | [5 empty] | 55 | 44.5976 | 0 | [5 empty] | 55 | 31.4249 | 1
[9 empty] | 56 | 39.7706 | 0 | [5 empty] | 56 | 49.9505 | 0 | [5 empty] | 56 | 37.6403 | 1
[9 empty] | 57 | 31.7757 | 1 | [5 empty] | 57 | 48.4733 | 0 | [5 empty] | 57 | 42.7408 | 0
[9 empty] | 58 | 34.3924 | 1 | [5 empty] | 58 | 48.7634 | 0 | [5 empty] | 58 | 31.7524 | 1
[9 empty] | 59 | 46.1331 | 0 | [5 empty] | 59 | 46.9173 | 0 | [5 empty] | 59 | 42.2659 | 0
[9 empty] | 60 | 44.7239 | 0 | [5 empty] | 60 | 48.6251 | 0 | [5 empty] | 60 | 41.5606 | 0
[9 empty] | 61 | 31.1555 | 1 | [5 empty] | 61 | 47.7623 | 0 | [5 empty] | 61 | 33.539 | 1
[9 empty] | 62 | 35.6658 | 1 | [5 empty] | 62 | 43.1451 | 0 | [5 empty] | 62 | 31.3105 | 1
[9 empty] | 63 | 32.6374 | 1 | [5 empty] | 63 | 48.2312 | 0 | [5 empty] | 63 | 37.1065 | 1
[9 empty] | 64 | 39.9981 | 0 | [5 empty] | 64 | 39.9763 | 0 | [5 empty] | 64 | 34.1195 | 1
[9 empty] | 65 | 38.6209 | 0 | [5 empty] | 65 | 47.2525 | 0 | [5 empty] | 65 | 35.2175 | 1
[9 empty] | 66 | 43.6073 | 0 | [5 empty] | 66 | 47.0473 | 0 | [5 empty] | 66 | 38.7667 | 0
[9 empty] | 67 | 37.4358 | 1 | [5 empty] | 67 | 43.4877 | 0 | [5 empty] | 67 | 32.3278 | 1
[9 empty] | 68 | 42.2334 | 0 | [5 empty] | 68 | 47.8035 | 0 | [5 empty] | 68 | 39.882 | 0
[9 empty] | 69 | 42.4409 | 0 | [5 empty] | 69 | 41.7948 | 0 | [5 empty] | 69 | 36.5779 | 1
[9 empty] | 70 | 39.0692 | 0 | [5 empty] | 70 | 50.0777 | 0 | [5 empty] | 70 | 39.357 | 0
[9 empty] | 71 | 37.8386 | 1 | [5 empty] | 71 | 51.7328 | 0 | [5 empty] | 71 | 29.3437 | 1
[9 empty] | 72 | 44.0596 | 0 | [5 empty] | 72 | 46.4713 | 0 | [5 empty] | 72 | 29.9742 | 1
[9 empty] | 73 | 37.436 | 1 | [5 empty] | 73 | 47.25 | 0 | [5 empty] | 73 | 42.5172 | 0
[9 empty] | 74 | 36.5886 | 1 | [5 empty] | 74 | 50.3241 | 0 | [5 empty] | 74 | 33.3802 | 1
[9 empty] | 75 | 36.1952 | 1 | [5 empty] | 75 | 47.3401 | 0 | [5 empty] | 75 | 38.9511 | 0
[9 empty] | 76 | 41.9363 | 0 | [5 empty] | 76 | 46.8016 | 0 | [5 empty] | 76 | 39.2664 | 0
[9 empty] | 77 | 38.2923 | 0 | [5 empty] | 77 | 51.034 | 0 | [5 empty] | 77 | 35.0207 | 1
[9 empty] | 78 | 36.726 | 1 | [5 empty] | 78 | 35.6241 | 1 | [5 empty] | 78 | 39.2132 | 0
[9 empty] | 79 | 30.4547 | 1 | [5 empty] | 79 | 42.1638 | 0 | [5 empty] | 79 | 32.9823 | 1
[9 empty] | 80 | 38.3471 | 0 | [5 empty] | 80 | 49.6081 | 0 | [5 empty] | 80 | 39.5071 | 0
[9 empty] | 81 | 35.7406 | 1 | [5 empty] | 81 | 44.7812 | 0 | [5 empty] | 81 | 30.4547 | 1
[9 empty] | 82 | 33.1516 | 1 | [5 empty] | 82 | 47.0446 | 0 | [5 empty] | 82 | 35.2992 | 1
[9 empty] | 83 | 36.3043 | 1 | [5 empty] | 83 | 41.2142 | 0 | [5 empty] | 83 | 35.4378 | 1
[9 empty] | 84 | 39.425 | 0 | [5 empty] | 84 | 52.5025 | 0 | [5 empty] | 84 | 38.7924 | 0
[9 empty] | 85 | 38.7229 | 0 | [5 empty] | 85 | 47.536 | 0 | [5 empty] | 85 | 38.9135 | 0
[9 empty] | 86 | 31.7224 | 1 | [5 empty] | 86 | 45.6805 | 0 | [5 empty] | 86 | 37.2759 | 1
[9 empty] | 87 | 41.9693 | 0 | [5 empty] | 87 | 47.7591 | 0 | [5 empty] | 87 | 41.2987 | 0
[9 empty] | 88 | 34.7666 | 1 | [5 empty] | 88 | 46.1948 | 0 | [5 empty] | 88 | 33.2081 | 1
[9 empty] | 89 | 33.8253 | 1 | [5 empty] | 89 | 40.0781 | 0 | [5 empty] | 89 | 32.2953 | 1
[9 empty] | 90 | 43.45 | 0 | [5 empty] | 90 | 47.2625 | 0 | [5 empty] | 90 | 29.2819 | 1
[9 empty] | 91 | 34.623 | 1 | [5 empty] | 91 | 40.5229 | 0 | [5 empty] | 91 | 35.7204 | 1
[9 empty] | 92 | 40.2512 | 0 | [5 empty] | 92 | 48.3858 | 0 | [5 empty] | 92 | 42.1837 | 0
[9 empty] | 93 | 34.9075 | 1 | [5 empty] | 93 | 46.8494 | 0 | [5 empty] | 93 | 33.8711 | 1
[9 empty] | 94 | 42.3836 | 0 | [5 empty] | 94 | 48.308 | 0 | [5 empty] | 94 | 32.8855 | 1
[9 empty] | 95 | 41.843 | 0 | [5 empty] | 95 | 48.4461 | 0 | [5 empty] | 95 | 38.8097 | 0
[9 empty] | 96 | 32.4368 | 1 | [5 empty] | 96 | 43.1351 | 0 | [5 empty] | 96 | 36.5961 | 1
[9 empty] | 97 | 35.0272 | 1 | [5 empty] | 97 | 43.0149 | 0 | [5 empty] | 97 | 34.5464 | 1
[9 empty] | 98 | 37.0597 | 1 | [5 empty] | 98 | 49.1329 | 0 | [5 empty] | 98 | 38.1909 | 0
[9 empty] | 99 | 41.1721 | 0 | [5 empty] | 99 | 47.3605 | 0 | [5 empty] | 99 | 28.8624 | 1
[9 empty] | 100 | 46.5502 | 0 | [5 empty] | 100 | 45.6635 | 0 | [5 empty] | 100 | 32.1938 | 1
[9 empty] | 101 | 40.7921 | 0 | [5 empty] | 101 | 49.267 | 0 | [5 empty] | 101 | 34.3159 | 1
[9 empty] | 102 | 33.4126 | 1 | [5 empty] | 102 | 43.1202 | 0 | [5 empty] | 102 | 32.8271 | 1
[9 empty] | 103 | 45.4701 | 0 | [5 empty] | 103 | 47.8617 | 0 | [5 empty] | 103 | 33.4296 | 1
[9 empty] | 104 | 37.9819 | 1 | [5 empty] | 104 | 45.0854 | 0 | [5 empty] | 104 | 44.1551 | 0
[9 empty] | 105 | 43.2654 | 0 | [5 empty] | 105 | 44.5543 | 0 | [5 empty] | 105 | 39.903 | 0
[9 empty] | 106 | 36.6089 | 1 | [5 empty] | 106 | 47.8445 | 0 | [5 empty] | 106 | 30.0928 | 1
[9 empty] | 107 | 41.16 | 0 | [5 empty] | 107 | 38.4012 | 0 | [5 empty] | 107 | 36.9616 | 1
[9 empty] | 108 | 37.8076 | 1 | [5 empty] | 108 | 43.5065 | 0 | [5 empty] | 108 | 39.6673 | 0
[9 empty] | 109 | 35.3109 | 1 | [5 empty] | 109 | 46.1034 | 0 | [5 empty] | 109 | 34.1375 | 1
[9 empty] | 110 | 36.7482 | 1 | [5 empty] | 110 | 45.6705 | 0 | [5 empty] | 110 | 35.7946 | 1
[9 empty] | 111 | 41.3679 | 0 | [5 empty] | 111 | 37.007 | 1 | [5 empty] | 111 | 36.7618 | 1
[9 empty] | 112 | 44.8227 | 0 | [5 empty] | 112 | 48.996 | 0 | [5 empty] | 112 | 30.3913 | 1
[9 empty] | 113 | 36.4008 | 1 | [5 empty] | 113 | 42.4869 | 0 | [5 empty] | 113 | 38.461 | 0
[9 empty] | 114 | 38.1115 | 0 | [5 empty] | 114 | 52.5417 | 0 | [5 empty] | 114 | 36.6562 | 1
[9 empty] | 115 | 41.0445 | 0 | [5 empty] | 115 | 50.6081 | 0 | [5 empty] | 115 | 34.6901 | 1
[9 empty] | 116 | 38.3661 | 0 | [5 empty] | 116 | 53.3371 | 0 | [5 empty] | 116 | 43.7119 | 0
[9 empty] | 117 | 37.5214 | 1 | [5 empty] | 117 | 40.0804 | 0 | [5 empty] | 117 | 32.4194 | 1
[9 empty] | 118 | 38.0661 | 0 | [5 empty] | 118 | 47.9614 | 0 | [5 empty] | 118 | 34.7744 | 1
[9 empty] | 119 | 40.6523 | 0 | [5 empty] | 119 | 42.5839 | 0 | [5 empty] | 119 | 38.6714 | 0
[9 empty] | 120 | 35.7097 | 1 | [5 empty] | 120 | 50.4342 | 0 | [5 empty] | 120 | 37.3176 | 1
[9 empty] | 121 | 36.0532 | 1 | [5 empty] | 121 | 36.49 | 1 | [5 empty] | 121 | 37.6718 | 1
[9 empty] | 122 | 41.9921 | 0 | [5 empty] | 122 | 47.0084 | 0 | [5 empty] | 122 | 40.542 | 0
[9 empty] | 123 | 39.6438 | 0 | [5 empty] | 123 | 42.361 | 0 | [5 empty] | 123 | 37.8853 | 1
[9 empty] | 124 | 39.1318 | 0 | [5 empty] | 124 | 46.4714 | 0 | [5 empty] | 124 | 36.0072 | 1
[9 empty] | 125 | 34.4756 | 1 | [5 empty] | 125 | 41.5702 | 0 | [5 empty] | 125 | 36.7342 | 1
[9 empty] | 126 | 38.8852 | 0 | [5 empty] | 126 | 38.0161 | 0 | [5 empty] | 126 | 39.8513 | 0
[9 empty] | 127 | 38.5665 | 0 | [5 empty] | 127 | 48.8812 | 0 | [5 empty] | 127 | 34.9237 | 1
[9 empty] | 128 | 35.8527 | 1 | [5 empty] | 128 | 42.3168 | 0 | [5 empty] | 128 | 40.3861 | 0
[9 empty] | 129 | 33.3154 | 1 | [5 empty] | 129 | 51.7559 | 0 | [5 empty] | 129 | 34.102 | 1
[9 empty] | 130 | 41.5166 | 0 | [5 empty] | 130 | 45.7819 | 0 | [5 empty] | 130 | 37.2417 | 1
[9 empty] | 131 | 34.5752 | 1 | [5 empty] | 131 | 47.5082 | 0 | [5 empty] | 131 | 38.6081 | 0
[9 empty] | 132 | 43.7511 | 0 | [5 empty] | 132 | 49.2006 | 0 | [5 empty] | 132 | 37.458 | 1
[9 empty] | 133 | 33.9891 | 1 | [5 empty] | 133 | 45.4311 | 0 | [5 empty] | 133 | 37.372 | 1
[9 empty] | 134 | 37.9667 | 1 | [5 empty] | 134 | 52.2927 | 0 | [5 empty] | 134 | 36.696 | 1
[9 empty] | 135 | 35.3152 | 1 | [5 empty] | 135 | 47.5524 | 0 | [5 empty] | 135 | 32.07 | 1
[9 empty] | 136 | 43.1839 | 0 | [5 empty] | 136 | 52.4434 | 0 | [5 empty] | 136 | 33.1991 | 1
[9 empty] | 137 | 43.594 | 0 | [5 empty] | 137 | 48.3329 | 0 | [5 empty] | 137 | 41.2232 | 0
[9 empty] | 138 | 37.9495 | 1 | [5 empty] | 138 | 42.8109 | 0 | [5 empty] | 138 | 35.298 | 1
[9 empty] | 139 | 40.5969 | 0 | [5 empty] | 139 | 50.2805 | 0 | [5 empty] | 139 | 42.3489 | 0
[9 empty] | 140 | 37.7685 | 1 | [5 empty] | 140 | 43.7812 | 0 | [5 empty] | 140 | 33.1974 | 1
[9 empty] | 141 | 37.9234 | 1 | [5 empty] | 141 | 52.2029 | 0 | [5 empty] | 141 | 41.9164 | 0
[9 empty] | 142 | 35.7088 | 1 | [5 empty] | 142 | 47.9437 | 0 | [5 empty] | 142 | 34.3226 | 1
[9 empty] | 143 | 38.8022 | 0 | [5 empty] | 143 | 50.0204 | 0 | [5 empty] | 143 | 28.0723 | 1
[9 empty] | 144 | 36.6002 | 1 | [5 empty] | 144 | 49.9363 | 0 | [5 empty] | 144 | 40.4675 | 0
[9 empty] | 145 | 36.8743 | 1 | [5 empty] | 145 | 40.1789 | 0 | [5 empty] | 145 | 32.1312 | 1
[9 empty] | 146 | 35.6321 | 1 | [5 empty] | 146 | 47.6891 | 0 | [5 empty] | 146 | 32.9782 | 1
[9 empty] | 147 | 33.2648 | 1 | [5 empty] | 147 | 49.4963 | 0 | [5 empty] | 147 | 38.1025 | 0
[9 empty] | 148 | 44.8883 | 0 | [5 empty] | 148 | 48.6096 | 0 | [5 empty] | 148 | 39.8598 | 0
[9 empty] | 149 | 45.377 | 0 | [5 empty] | 149 | 50.1336 | 0 | [5 empty] | 149 | 37.8562 | 1
[9 empty] | 150 | 39.2419 | 0 | [5 empty] | 150 | 43.0915 | 0 | [5 empty] | 150 | 33.3686 | 1
[9 empty] | 151 | 35.2432 | 1 | [5 empty] | 151 | 46.1031 | 0 | [5 empty] | 151 | 33.0243 | 1
[9 empty] | 152 | 33.852 | 1 | [5 empty] | 152 | 42.6617 | 0 | [5 empty] | 152 | 37.5394 | 1
[9 empty] | 153 | 41.3887 | 0 | [5 empty] | 153 | 45.071 | 0 | [5 empty] | 153 | 38.5382 | 0
[9 empty] | 154 | 39.973 | 0 | [5 empty] | 154 | 48.5447 | 0 | [5 empty] | 154 | 40.3809 | 0
[9 empty] | 155 | 34.5212 | 1 | [5 empty] | 155 | 48.4462 | 0 | [5 empty] | 155 | 34.7329 | 1
[9 empty] | 156 | 42.765 | 0 | [5 empty] | 156 | 49.0589 | 0 | [5 empty] | 156 | 33.4485 | 1
[9 empty] | 157 | 38.2676 | 0 | [5 empty] | 157 | 45.5844 | 0 | [5 empty] | 157 | 35.5041 | 1
[9 empty] | 158 | 40.8364 | 0 | [5 empty] | 158 | 40.7618 | 0 | [5 empty] | 158 | 35.5088 | 1
[9 empty] | 159 | 37.4368 | 1 | [5 empty] | 159 | 48.7106 | 0 | [5 empty] | 159 | 41.6603 | 0
[9 empty] | 160 | 38.0452 | 0 | [5 empty] | 160 | 43.1259 | 0 | [5 empty] | 160 | 36.2471 | 1
[9 empty] | 161 | 42.734 | 0 | [5 empty] | 161 | 48.4742 | 0 | [5 empty] | 161 | 37.1018 | 1
[9 empty] | 162 | 30.63 | 1 | [5 empty] | 162 | 42.7313 | 0 | [5 empty] | 162 | 39.3782 | 0
[9 empty] | 163 | 33.0841 | 1 | [5 empty] | 163 | 40.2886 | 0 | [5 empty] | 163 | 32.6541 | 1
[9 empty] | 164 | 46.9809 | 0 | [5 empty] | 164 | 45.7811 | 0 | [5 empty] | 164 | 43.9343 | 0
[9 empty] | 165 | 39.5572 | 0 | [5 empty] | 165 | 44.7415 | 0 | [5 empty] | 165 | 38.6499 | 0
[9 empty] | 166 | 35.2069 | 1 | [5 empty] | 166 | 47.2527 | 0 | [5 empty] | 166 | 29.6628 | 1
[9 empty] | 167 | 37.0959 | 1 | [5 empty] | 167 | 40.5078 | 0 | [5 empty] | 167 | 30.5425 | 1
[9 empty] | 168 | 39.3386 | 0 | [5 empty] | 168 | 42.8425 | 0 | [5 empty] | 168 | 37.478 | 1
[9 empty] | 169 | 43.4295 | 0 | [5 empty] | 169 | 40.9345 | 0 | [5 empty] | 169 | 32.8011 | 1
[9 empty] | 170 | 40.5691 | 0 | [5 empty] | 170 | 49.6549 | 0 | [5 empty] | 170 | 38.0822 | 0
[9 empty] | 171 | 36.091 | 1 | [5 empty] | 171 | 48.3999 | 0 | [5 empty] | 171 | 28.207 | 1
[9 empty] | 172 | 39.5002 | 0 | [5 empty] | 172 | 48.6421 | 0 | [5 empty] | 172 | 36.7048 | 1
[9 empty] | 173 | 36.2121 | 1 | [5 empty] | 173 | 43.8847 | 0 | [5 empty] | 173 | 33.4723 | 1
[9 empty] | 174 | 38.7525 | 0 | [5 empty] | 174 | 45.2678 | 0 | [5 empty] | 174 | 29.7129 | 1
[9 empty] | 175 | 36.7689 | 1 | [5 empty] | 175 | 44.3979 | 0 | [5 empty] | 175 | 38.3219 | 0
[9 empty] | 176 | 46.939 | 0 | [5 empty] | 176 | 51.9907 | 0 | [5 empty] | 176 | 39.37 | 0
[9 empty] | 177 | 32.3311 | 1 | [5 empty] | 177 | 46.0401 | 0 | [5 empty] | 177 | 30.8348 | 1
[9 empty] | 178 | 36.8421 | 1 | [5 empty] | 178 | 44.4111 | 0 | [5 empty] | 178 | 37.2445 | 1
[9 empty] | 179 | 36.2129 | 1 | [5 empty] | 179 | 45.1146 | 0 | [5 empty] | 179 | 38.4674 | 0
[9 empty] | 180 | 43.4265 | 0 | [5 empty] | 180 | 49.4429 | 0 | [5 empty] | 180 | 34.58 | 1
[9 empty] | 181 | 36.8693 | 1 | [5 empty] | 181 | 49.3727 | 0 | [5 empty] | 181 | 31.8265 | 1
[9 empty] | 182 | 39.7316 | 0 | [5 empty] | 182 | 50.4716 | 0 | [5 empty] | 182 | 31.871 | 1
[9 empty] | 183 | 34.5737 | 1 | [5 empty] | 183 | 46.3758 | 0 | [5 empty] | 183 | 38.0076 | 0
[9 empty] | 184 | 33.3636 | 1 | [5 empty] | 184 | 42.1895 | 0 | [5 empty] | 184 | 33.8354 | 1
[9 empty] | 185 | 38.5883 | 0 | [5 empty] | 185 | 42.9233 | 0 | [5 empty] | 185 | 34.5919 | 1
[9 empty] | 186 | 37.1691 | 1 | [5 empty] | 186 | 46.3814 | 0 | [5 empty] | 186 | 37.5299 | 1
[9 empty] | 187 | 38.326 | 0 | [5 empty] | 187 | 45.929 | 0 | [5 empty] | 187 | 41.1606 | 0
[9 empty] | 188 | 35.3325 | 1 | [5 empty] | 188 | 47.5428 | 0 | [5 empty] | 188 | 35.6881 | 1
[9 empty] | 189 | 42.75 | 0 | [5 empty] | 189 | 41.7073 | 0 | [5 empty] | 189 | 42.2354 | 0
[9 empty] | 190 | 39.012 | 0 | [5 empty] | 190 | 48.4634 | 0 | [5 empty] | 190 | 32.2792 | 1
[9 empty] | 191 | 40.5037 | 0 | [5 empty] | 191 | 49.4947 | 0 | [5 empty] | 191 | 32.0531 | 1
[9 empty] | 192 | 41.0623 | 0 | [5 empty] | 192 | 45.0199 | 0 | [5 empty] | 192 | 38.8217 | 0
[9 empty] | 193 | 40.6703 | 0 | [5 empty] | 193 | 47.2873 | 0 | [5 empty] | 193 | 38.8386 | 0
[9 empty] | 194 | 37.7122 | 1 | [5 empty] | 194 | 38.528 | 0 | [5 empty] | 194 | 38.4491 | 0
[9 empty] | 195 | 33.9304 | 1 | [5 empty] | 195 | 46.6303 | 0 | [5 empty] | 195 | 33.7102 | 1
[9 empty] | 196 | 35.9535 | 1 | [5 empty] | 196 | 48.2993 | 0 | [5 empty] | 196 | 34.387 | 1
[9 empty] | 197 | 40.6728 | 0 | [5 empty] | 197 | 43.9682 | 0 | [5 empty] | 197 | 34.7675 | 1
[9 empty] | 198 | 35.7473 | 1 | [5 empty] | 198 | 48.357 | 0 | [5 empty] | 198 | 34.9456 | 1
[9 empty] | 199 | 37.4666 | 1 | [5 empty] | 199 | 44.2364 | 0 | [5 empty] | 199 | 37.6537 | 1
[9 empty] | 200 | 44.8336 | 0 | [5 empty] | 200 | 46.3437 | 0 | [5 empty] | 200 | 31.0559 | 1
[9 empty] | 201 | 36.1559 | 1 | [5 empty] | 201 | 42.0499 | 0 | [5 empty] | 201 | 31.9897 | 1
[9 empty] | 202 | 38.4552 | 0 | [5 empty] | 202 | 47.1576 | 0 | [5 empty] | 202 | 36.7081 | 1
[9 empty] | 203 | 42.6831 | 0 | [5 empty] | 203 | 49.5924 | 0 | [5 empty] | 203 | 37.5421 | 1
[9 empty] | 204 | 37.6359 | 1 | [5 empty] | 204 | 45.3528 | 0 | [5 empty] | 204 | 36.0116 | 1
[9 empty] | 205 | 39.8858 | 0 | [5 empty] | 205 | 40.2301 | 0 | [5 empty] | 205 | 28.9901 | 1
[9 empty] | 206 | 37.5426 | 1 | [5 empty] | 206 | 47.1661 | 0 | [5 empty] | 206 | 33.621 | 1
[9 empty] | 207 | 33.4297 | 1 | [5 empty] | 207 | 43.4148 | 0 | [5 empty] | 207 | 35.9647 | 1
[9 empty] | 208 | 38.4415 | 0 | [5 empty] | 208 | 44.6215 | 0 | [5 empty] | 208 | 39.8024 | 0
[9 empty] | 209 | 36.7943 | 1 | [5 empty] | 209 | 43.348 | 0 | [5 empty] | 209 | 37.0988 | 1
[9 empty] | 210 | 33.0963 | 1 | [5 empty] | 210 | 51.6659 | 0 | [5 empty] | 210 | 35.4303 | 1
[9 empty] | 211 | 40.264 | 0 | [5 empty] | 211 | 41.0686 | 0 | [5 empty] | 211 | 34.4742 | 1
[9 empty] | 212 | 34.7111 | 1 | [5 empty] | 212 | 45.704 | 0 | [5 empty] | 212 | 38.5527 | 0
[9 empty] | 213 | 34.2608 | 1 | [5 empty] | 213 | 47.0767 | 0 | [5 empty] | 213 | 35.4544 | 1
[9 empty] | 214 | 35.0107 | 1 | [5 empty] | 214 | 44.6336 | 0 | [5 empty] | 214 | 35.0313 | 1
[9 empty] | 215 | 32.5807 | 1 | [5 empty] | 215 | 40.6444 | 0 | [5 empty] | 215 | 42.1689 | 0
[9 empty] | 216 | 47.5404 | 0 | [5 empty] | 216 | 39.6186 | 0 | [5 empty] | 216 | 40.1854 | 0
[9 empty] | 217 | 41.2783 | 0 | [5 empty] | 217 | 46.1586 | 0 | [5 empty] | 217 | 38.4038 | 0
[9 empty] | 218 | 42.6948 | 0 | [5 empty] | 218 | 47.8698 | 0 | [5 empty] | 218 | 33.2367 | 1
[9 empty] | 219 | 39.0911 | 0 | [5 empty] | 219 | 47.6223 | 0 | [5 empty] | 219 | 32.4279 | 1
[9 empty] | 220 | 33.9546 | 1 | [5 empty] | 220 | 43.6375 | 0 | [5 empty] | 220 | 35.2795 | 1
[9 empty] | 221 | 32.2714 | 1 | [5 empty] | 221 | 45.0689 | 0 | [5 empty] | 221 | 42.4592 | 0
[9 empty] | 222 | 38.6381 | 0 | [5 empty] | 222 | 43.1115 | 0 | [5 empty] | 222 | 36.0207 | 1
[9 empty] | 223 | 35.2583 | 1 | [5 empty] | 223 | 47.0599 | 0 | [5 empty] | 223 | 38.3012 | 0
[9 empty] | 224 | 36.0475 | 1 | [5 empty] | 224 | 41.4439 | 0 | [5 empty] | 224 | 36.7539 | 1
[9 empty] | 225 | 33.8017 | 1 | [5 empty] | 225 | 49.7758 | 0 | [5 empty] | 225 | 32.4 | 1
[9 empty] | 226 | 34.8652 | 1 | [5 empty] | 226 | 47.5276 | 0 | [5 empty] | 226 | 37.5396 | 1
[9 empty] | 227 | 30.4686 | 1 | [5 empty] | 227 | 41.6672 | 0 | [5 empty] | 227 | 33.8508 | 1
[9 empty] | 228 | 39.7846 | 0 | [5 empty] | 228 | 48.5037 | 0 | [5 empty] | 228 | 35.4548 | 1
[9 empty] | 229 | 34.7956 | 1 | [5 empty] | 229 | 47.5803 | 0 | [5 empty] | 229 | 37.0668 | 1
[9 empty] | 230 | 37.6501 | 1 | [5 empty] | 230 | 46.4051 | 0 | [5 empty] | 230 | 41.3462 | 0
[9 empty] | 231 | 37.6201 | 1 | [5 empty] | 231 | 46.3871 | 0 | [5 empty] | 231 | 31.3895 | 1
[9 empty] | 232 | 37.82 | 1 | [5 empty] | 232 | 40.8643 | 0 | [5 empty] | 232 | 43.7232 | 0
[9 empty] | 233 | 37.1682 | 1 | [5 empty] | 233 | 47.1479 | 0 | [5 empty] | 233 | 37.8937 | 1
[9 empty] | 234 | 34.7575 | 1 | [5 empty] | 234 | 43.5432 | 0 | [5 empty] | 234 | 45.4923 | 0
[9 empty] | 235 | 38.1919 | 0 | [5 empty] | 235 | 42.5615 | 0 | [5 empty] | 235 | 29.7026 | 1
[9 empty] | 236 | 42.7498 | 0 | [5 empty] | 236 | 40.1914 | 0 | [5 empty] | 236 | 36.4227 | 1
[9 empty] | 237 | 35.471 | 1 | [5 empty] | 237 | 43.3155 | 0 | [5 empty] | 237 | 39.9095 | 0
[9 empty] | 238 | 37.7401 | 1 | [5 empty] | 238 | 50.1678 | 0 | [5 empty] | 238 | 31.9777 | 1
[9 empty] | 239 | 36.5118 | 1 | [5 empty] | 239 | 48.4546 | 0 | [5 empty] | 239 | 30.617 | 1
[9 empty] | 240 | 42.0236 | 0 | [5 empty] | 240 | 43.037 | 0 | [5 empty] | 240 | 31.9118 | 1
[9 empty] | 241 | 38.9924 | 0 | [5 empty] | 241 | 39.1527 | 0 | [5 empty] | 241 | 32.2595 | 1
[9 empty] | 242 | 44.4506 | 0 | [5 empty] | 242 | 45.0508 | 0 | [5 empty] | 242 | 33.0356 | 1
[9 empty] | 243 | 44.9528 | 0 | [5 empty] | 243 | 48.3579 | 0 | [5 empty] | 243 | 33.9256 | 1
[9 empty] | 244 | 34.6091 | 1 | [5 empty] | 244 | 43.7553 | 0 | [5 empty] | 244 | 32.0648 | 1
[9 empty] | 245 | 46.7759 | 0 | [5 empty] | 245 | 39.9801 | 0 | [5 empty] | 245 | 31.345 | 1
[9 empty] | 246 | 31.018 | 1 | [5 empty] | 246 | 48.765 | 0 | [5 empty] | 246 | 36.8212 | 1
[9 empty] | 247 | 42.7134 | 0 | [5 empty] | 247 | 44.1435 | 0 | [5 empty] | 247 | 36.2667 | 1
[9 empty] | 248 | 34.1738 | 1 | [5 empty] | 248 | 46.1435 | 0 | [5 empty] | 248 | 32.0877 | 1
[9 empty] | 249 | 37.9396 | 1 | [5 empty] | 249 | 44.4048 | 0 | [5 empty] | 249 | 33.3094 | 1
[9 empty] | 250 | 39.1529 | 0 | [5 empty] | 250 | 39.8578 | 0 | [5 empty] | 250 | 36.0729 | 1
[9 empty] | 251 | 39.9016 | 0 | [5 empty] | 251 | 43.6359 | 0 | [5 empty] | 251 | 35.0352 | 1
[9 empty] | 252 | 36.4481 | 1 | [5 empty] | 252 | 38.4007 | 0 | [5 empty] | 252 | 36.5983 | 1
[9 empty] | 253 | 35.3347 | 1 | [5 empty] | 253 | 46.1181 | 0 | [5 empty] | 253 | 33.0783 | 1
[9 empty] | 254 | 36.5442 | 1 | [5 empty] | 254 | 45.0103 | 0 | [5 empty] | 254 | 34.4408 | 1
[9 empty] | 255 | 42.9131 | 0 | [5 empty] | 255 | 44.6279 | 0 | [5 empty] | 255 | 35.1124 | 1
[9 empty] | 256 | 42.376 | 0 | [5 empty] | 256 | 42.8278 | 0 | [5 empty] | 256 | 35.0869 | 1
[9 empty] | 257 | 43.4796 | 0 | [5 empty] | 257 | 48.7131 | 0 | [5 empty] | 257 | 39.779 | 0
[9 empty] | 258 | 34.6039 | 1 | [5 empty] | 258 | 41.4038 | 0 | [5 empty] | 258 | 35.5692 | 1
[9 empty] | 259 | 33.6349 | 1 | [5 empty] | 259 | 50.5118 | 0 | [5 empty] | 259 | 30.3642 | 1
[9 empty] | 260 | 35.2588 | 1 | [5 empty] | 260 | 45.4903 | 0 | [5 empty] | 260 | 30.8653 | 1
[9 empty] | 261 | 33.9402 | 1 | [5 empty] | 261 | 46.3477 | 0 | [5 empty] | 261 | 36.6373 | 1
[9 empty] | 262 | 34.1836 | 1 | [5 empty] | 262 | 45.487 | 0 | [5 empty] | 262 | 30.4721 | 1
[9 empty] | 263 | 37.3073 | 1 | [5 empty] | 263 | 44.7836 | 0 | [5 empty] | 263 | 35.5746 | 1
[9 empty] | 264 | 30.9572 | 1 | [5 empty] | 264 | 43.6037 | 0 | [5 empty] | 264 | 36.5179 | 1
[9 empty] | 265 | 39.2297 | 0 | [5 empty] | 265 | 47.7106 | 0 | [5 empty] | 265 | 39.2158 | 0
[9 empty] | 266 | 42.5365 | 0 | [5 empty] | 266 | 47.6215 | 0 | [5 empty] | 266 | 31.1653 | 1
[9 empty] | 267 | 45.9347 | 0 | [5 empty] | 267 | 42.2466 | 0 | [5 empty] | 267 | 34.3367 | 1
[9 empty] | 268 | 38.9215 | 0 | [5 empty] | 268 | 49.0327 | 0 | [5 empty] | 268 | 41.6275 | 0
[9 empty] | 269 | 36.8693 | 1 | [5 empty] | 269 | 44.6429 | 0 | [5 empty] | 269 | 35.3609 | 1
[9 empty] | 270 | 36.2341 | 1 | [5 empty] | 270 | 44.4122 | 0 | [5 empty] | 270 | 35.1274 | 1
[9 empty] | 271 | 38.7777 | 0 | [5 empty] | 271 | 51.2177 | 0 | [5 empty] | 271 | 37.8423 | 1
[9 empty] | 272 | 34.6465 | 1 | [5 empty] | 272 | 50.6788 | 0 | [5 empty] | 272 | 34.7738 | 1
[9 empty] | 273 | 39.6936 | 0 | [5 empty] | 273 | 45.5348 | 0 | [5 empty] | 273 | 37.5171 | 1
[9 empty] | 274 | 37.4945 | 1 | [5 empty] | 274 | 44.3136 | 0 | [5 empty] | 274 | 33.3951 | 1
[9 empty] | 275 | 38.894 | 0 | [5 empty] | 275 | 47.0413 | 0 | [5 empty] | 275 | 35.3967 | 1
[9 empty] | 276 | 43.609 | 0 | [5 empty] | 276 | 38.208 | 0 | [5 empty] | 276 | 34.4049 | 1
[9 empty] | 277 | 34.6525 | 1 | [5 empty] | 277 | 52.6074 | 0 | [5 empty] | 277 | 37.0879 | 1
[9 empty] | 278 | 36.5437 | 1 | [5 empty] | 278 | 43.9595 | 0 | [5 empty] | 278 | 32.0335 | 1
[9 empty] | 279 | 39.1483 | 0 | [5 empty] | 279 | 53.6639 | 0 | [5 empty] | 279 | 37.6471 | 1
[9 empty] | 280 | 36.3603 | 1 | [5 empty] | 280 | 50.381 | 0 | [5 empty] | 280 | 35.341 | 1
[9 empty] | 281 | 33.4248 | 1 | [5 empty] | 281 | 40.6318 | 0 | [5 empty] | 281 | 33.8156 | 1
[9 empty] | 282 | 38.9684 | 0 | [5 empty] | 282 | 44.232 | 0 | [5 empty] | 282 | 40.6006 | 0
[9 empty] | 283 | 44.3588 | 0 | [5 empty] | 283 | 38.9359 | 0 | [5 empty] | 283 | 35.7292 | 1
[9 empty] | 284 | 43.6785 | 0 | [5 empty] | 284 | 45.7284 | 0 | [5 empty] | 284 | 37.8047 | 1
[9 empty] | 285 | 33.354 | 1 | [5 empty] | 285 | 35.7902 | 1 | [5 empty] | 285 | 35.4891 | 1
[9 empty] | 286 | 35.6179 | 1 | [5 empty] | 286 | 46.5581 | 0 | [5 empty] | 286 | 34.4699 | 1
[9 empty] | 287 | 37.3641 | 1 | [5 empty] | 287 | 43.5355 | 0 | [5 empty] | 287 | 34.458 | 1
[9 empty] | 288 | 40.5224 | 0 | [5 empty] | 288 | 35.5075 | 1 | [5 empty] | 288 | 35.0415 | 1
[9 empty] | 289 | 40.9381 | 0 | [5 empty] | 289 | 42.4221 | 0 | [5 empty] | 289 | 33.9274 | 1
[9 empty] | 290 | 37.0267 | 1 | [5 empty] | 290 | 48.9755 | 0 | [5 empty] | 290 | 32.9885 | 1
[9 empty] | 291 | 37.6165 | 1 | [5 empty] | 291 | 44.3238 | 0 | [5 empty] | 291 | 35.2175 | 1
[9 empty] | 292 | 38.9317 | 0 | [5 empty] | 292 | 42.7305 | 0 | [5 empty] | 292 | 42.4202 | 0
[9 empty] | 293 | 40.8098 | 0 | [5 empty] | 293 | 48.9565 | 0 | [5 empty] | 293 | 30.7034 | 1
[9 empty] | 294 | 33.8629 | 1 | [5 empty] | 294 | 47.8079 | 0 | [5 empty] | 294 | 31.3629 | 1
[9 empty] | 295 | 39.799 | 0 | [5 empty] | 295 | 40.2477 | 0 | [5 empty] | 295 | 32.9064 | 1
[9 empty] | 296 | 33.1995 | 1 | [5 empty] | 296 | 45.1473 | 0 | [5 empty] | 296 | 32.455 | 1
[9 empty] | 297 | 44.9553 | 0 | [5 empty] | 297 | 46.8003 | 0 | [5 empty] | 297 | 29.9046 | 1
[9 empty] | 298 | 35.0539 | 1 | [5 empty] | 298 | 38.0745 | 0 | [5 empty] | 298 | 34.5107 | 1
[9 empty] | 299 | 40.5105 | 0 | [5 empty] | 299 | 46.5955 | 0 | [5 empty] | 299 | 35.7562 | 1
[9 empty] | 300 | 38.7443 | 0 | [5 empty] | 300 | 41.2217 | 0 | [5 empty] | 300 | 32.4065 | 1
[9 empty] | 301 | 39.4853 | 0 | [5 empty] | 301 | 47.2388 | 0 | [5 empty] | 301 | 39.5353 | 0
[9 empty] | 302 | 34.7345 | 1 | [5 empty] | 302 | 44.0221 | 0 | [5 empty] | 302 | 33.2337 | 1
[9 empty] | 303 | 33.0966 | 1 | [5 empty] | 303 | 43.3525 | 0 | [5 empty] | 303 | 35.9152 | 1
[9 empty] | 304 | 38.9235 | 0 | [5 empty] | 304 | 45.2732 | 0 | [5 empty] | 304 | 36.8955 | 1
[9 empty] | 305 | 35.8217 | 1 | [5 empty] | 305 | 42.2761 | 0 | [5 empty] | 305 | 41.3709 | 0
[9 empty] | 306 | 31.3788 | 1 | [5 empty] | 306 | 43.258 | 0 | [5 empty] | 306 | 38.5879 | 0
[9 empty] | 307 | 40.4455 | 0 | [5 empty] | 307 | 47.3362 | 0 | [5 empty] | 307 | 29.902 | 1
[9 empty] | 308 | 40.8319 | 0 | [5 empty] | 308 | 43.1826 | 0 | [5 empty] | 308 | 33.4428 | 1
[9 empty] | 309 | 49.423 | 0 | [5 empty] | 309 | 40.7574 | 0 | [5 empty] | 309 | 35.7429 | 1
[9 empty] | 310 | 44.2331 | 0 | [5 empty] | 310 | 44.7778 | 0 | [5 empty] | 310 | 38.4125 | 0
[9 empty] | 311 | 37.44 | 1 | [5 empty] | 311 | 47.1178 | 0 | [5 empty] | 311 | 32.7568 | 1
[9 empty] | 312 | 36.9718 | 1 | [5 empty] | 312 | 49.7161 | 0 | [5 empty] | 312 | 34.3752 | 1
[9 empty] | 313 | 32.548 | 1 | [5 empty] | 313 | 49.4065 | 0 | [5 empty] | 313 | 29.7158 | 1
[9 empty] | 314 | 39.145 | 0 | [5 empty] | 314 | 48.3817 | 0 | [5 empty] | 314 | 32.0715 | 1
[9 empty] | 315 | 40.0167 | 0 | [5 empty] | 315 | 47.2967 | 0 | [5 empty] | 315 | 46.8291 | 0
[9 empty] | 316 | 44.2231 | 0 | [5 empty] | 316 | 47.4636 | 0 | [5 empty] | 316 | 36.5174 | 1
[9 empty] | 317 | 32.0919 | 1 | [5 empty] | 317 | 49.4631 | 0 | [5 empty] | 317 | 35.1576 | 1
[9 empty] | 318 | 33.4056 | 1 | [5 empty] | 318 | 46.8585 | 0 | [5 empty] | 318 | 34.6988 | 1
[9 empty] | 319 | 43.6929 | 0 | [5 empty] | 319 | 51.6806 | 0 | [5 empty] | 319 | 31.9881 | 1
[9 empty] | 320 | 37.9509 | 1 | [5 empty] | 320 | 44.6054 | 0 | [5 empty] | 320 | 41.3967 | 0
[9 empty] | 321 | 36.552 | 1 | [5 empty] | 321 | 52.8867 | 0 | [5 empty] | 321 | 36.8237 | 1
[9 empty] | 322 | 44.0253 | 0 | [5 empty] | 322 | 49.9846 | 0 | [5 empty] | 322 | 30.9573 | 1
[9 empty] | 323 | 35.4308 | 1 | [5 empty] | 323 | 47.9896 | 0 | [5 empty] | 323 | 41.2947 | 0
[9 empty] | 324 | 34.2096 | 1 | [5 empty] | 324 | 50.3583 | 0 | [5 empty] | 324 | 37.8379 | 1
[9 empty] | 325 | 38.9573 | 0 | [5 empty] | 325 | 46.5015 | 0 | [5 empty] | 325 | 36.9051 | 1
[9 empty] | 326 | 39.533 | 0 | [5 empty] | 326 | 40.4338 | 0 | [5 empty] | 326 | 39.823 | 0
[9 empty] | 327 | 36.583 | 1 | [5 empty] | 327 | 47.1691 | 0 | [5 empty] | 327 | 35.2063 | 1
[9 empty] | 328 | 36.7171 | 1 | [5 empty] | 328 | 37.4639 | 1 | [5 empty] | 328 | 32.2516 | 1
[9 empty] | 329 | 45.8132 | 0 | [5 empty] | 329 | 48.1187 | 0 | [5 empty] | 329 | 29.8246 | 1
[9 empty] | 330 | 36.9903 | 1 | [5 empty] | 330 | 47.7748 | 0 | [5 empty] | 330 | 37.2264 | 1
[9 empty] | 331 | 35.3594 | 1 | [5 empty] | 331 | 45.6484 | 0 | [5 empty] | 331 | 37.175 | 1
[9 empty] | 332 | 38.4532 | 0 | [5 empty] | 332 | 43.3685 | 0 | [5 empty] | 332 | 39.9305 | 0
[9 empty] | 333 | 37.6672 | 1 | [5 empty] | 333 | 50.1909 | 0 | [5 empty] | 333 | 40.0896 | 0
[9 empty] | 334 | 32.3246 | 1 | [5 empty] | 334 | 44.4238 | 0 | [5 empty] | 334 | 34.5439 | 1
[9 empty] | 335 | 35.2038 | 1 | [5 empty] | 335 | 47.3855 | 0 | [5 empty] | 335 | 35.1766 | 1
[9 empty] | 336 | 37.0666 | 1 | [5 empty] | 336 | 47.5544 | 0 | [5 empty] | 336 | 30.9026 | 1
[9 empty] | 337 | 36.3957 | 1 | [5 empty] | 337 | 46.9708 | 0 | [5 empty] | 337 | 31.6803 | 1
[9 empty] | 338 | 32.398 | 1 | [5 empty] | 338 | 49.7456 | 0 | [5 empty] | 338 | 28.8628 | 1
[9 empty] | 339 | 40.2297 | 0 | [5 empty] | 339 | 46.0795 | 0 | [5 empty] | 339 | 32.4541 | 1
[9 empty] | 340 | 42.3199 | 0 | [5 empty] | 340 | 46.7549 | 0 | [5 empty] | 340 | 30.4415 | 1
[9 empty] | 341 | 43.0299 | 0 | [5 empty] | 341 | 47.1039 | 0 | [5 empty] | 341 | 31.0376 | 1
[9 empty] | 342 | 41.9332 | 0 | [5 empty] | 342 | 42.1626 | 0 | [5 empty] | 342 | 33.5325 | 1
[9 empty] | 343 | 36.2592 | 1 | [5 empty] | 343 | 43.8196 | 0 | [5 empty] | 343 | 35.7771 | 1
[9 empty] | 344 | 41.0547 | 0 | [5 empty] | 344 | 47.658 | 0 | [5 empty] | 344 | 35.0405 | 1
[9 empty] | 345 | 33.1913 | 1 | [5 empty] | 345 | 50.9231 | 0 | [5 empty] | 345 | 40.1019 | 0
[9 empty] | 346 | 36.7317 | 1 | [5 empty] | 346 | 47.9981 | 0 | [5 empty] | 346 | 38.8169 | 0
[9 empty] | 347 | 35.739 | 1 | [5 empty] | 347 | 47.377 | 0 | [5 empty] | 347 | 40.4123 | 0
[9 empty] | 348 | 45.4578 | 0 | [5 empty] | 348 | 51.6247 | 0 | [5 empty] | 348 | 37.4298 | 1
[9 empty] | 349 | 34.6543 | 1 | [5 empty] | 349 | 45.3692 | 0 | [5 empty] | 349 | 33.9813 | 1
[9 empty] | 350 | 39.6278 | 0 | [5 empty] | 350 | 51.0132 | 0 | [5 empty] | 350 | 31.3563 | 1
[9 empty] | 351 | 35.8828 | 1 | [5 empty] | 351 | 42.4294 | 0 | [5 empty] | 351 | 36.8226 | 1
[9 empty] | 352 | 46.8019 | 0 | [5 empty] | 352 | 47.4987 | 0 | [5 empty] | 352 | 34.6704 | 1
[9 empty] | 353 | 38.1023 | 0 | [5 empty] | 353 | 45.121 | 0 | [5 empty] | 353 | 36.9351 | 1
[9 empty] | 354 | 33.5524 | 1 | [5 empty] | 354 | 49.3129 | 0 | [5 empty] | 354 | 34.8513 | 1
[9 empty] | 355 | 42.6721 | 0 | [5 empty] | 355 | 50.8867 | 0 | [5 empty] | 355 | 30.4159 | 1
[9 empty] | 356 | 34.467 | 1 | [5 empty] | 356 | 46.5376 | 0 | [5 empty] | 356 | 29.881 | 1
[9 empty] | 357 | 33.9668 | 1 | [5 empty] | 357 | 35.6264 | 1 | [5 empty] | 357 | 33.5266 | 1
[9 empty] | 358 | 39.739 | 0 | [5 empty] | 358 | 46.4665 | 0 | [5 empty] | 358 | 35.9416 | 1
[9 empty] | 359 | 39.4574 | 0 | [5 empty] | 359 | 42.0701 | 0 | [5 empty] | 359 | 31.9401 | 1
[9 empty] | 360 | 32.4813 | 1 | [5 empty] | 360 | 54.1423 | 0 | [5 empty] | 360 | 41.2108 | 0
[9 empty] | 361 | 42.3353 | 0 | [5 empty] | 361 | 47.5509 | 0 | [5 empty] | 361 | 40.9806 | 0
[9 empty] | 362 | 34.9142 | 1 | [5 empty] | 362 | 50.1642 | 0 | [5 empty] | 362 | 34.1567 | 1
[9 empty] | 363 | 36.4086 | 1 | [5 empty] | 363 | 46.7187 | 0 | [5 empty] | 363 | 30.7079 | 1
[9 empty] | 364 | 39.5355 | 0 | [5 empty] | 364 | 45.7809 | 0 | [5 empty] | 364 | 27.5104 | 1
[9 empty] | 365 | 40.1297 | 0 | [5 empty] | 365 | 52.3698 | 0 | [5 empty] | 365 | 32.4135 | 1
[9 empty] | 366 | 37.1953 | 1 | [5 empty] | 366 | 37.9754 | 1 | [5 empty] | 366 | 29.298 | 1
[9 empty] | 367 | 41.5876 | 0 | [5 empty] | 367 | 47.755 | 0 | [5 empty] | 367 | 33.39 | 1
[9 empty] | 368 | 40.0172 | 0 | [5 empty] | 368 | 42.5104 | 0 | [5 empty] | 368 | 37.3755 | 1
[9 empty] | 369 | 41.4536 | 0 | [5 empty] | 369 | 42.2022 | 0 | [5 empty] | 369 | 33.7114 | 1
[9 empty] | 370 | 38.4541 | 0 | [5 empty] | 370 | 44.4777 | 0 | [5 empty] | 370 | 33.7203 | 1
[9 empty] | 371 | 36.5638 | 1 | [5 empty] | 371 | 51.3334 | 0 | [5 empty] | 371 | 31.342 | 1
[9 empty] | 372 | 38.0525 | 0 | [5 empty] | 372 | 41.654 | 0 | [5 empty] | 372 | 38.7207 | 0
[9 empty] | 373 | 40.8788 | 0 | [5 empty] | 373 | 46.017 | 0 | [5 empty] | 373 | 33.3278 | 1
[9 empty] | 374 | 36.7657 | 1 | [5 empty] | 374 | 48.1546 | 0 | [5 empty] | 374 | 35.6001 | 1
[9 empty] | 375 | 36.499 | 1 | [5 empty] | 375 | 42.6004 | 0 | [5 empty] | 375 | 37.7241 | 1
[9 empty] | 376 | 37.7274 | 1 | [5 empty] | 376 | 51.4058 | 0 | [5 empty] | 376 | 40.1475 | 0
[9 empty] | 377 | 38.6512 | 0 | [5 empty] | 377 | 51.5305 | 0 | [5 empty] | 377 | 44.2691 | 0
[9 empty] | 378 | 37.935 | 1 | [5 empty] | 378 | 47.9514 | 0 | [5 empty] | 378 | 31.7855 | 1
[9 empty] | 379 | 33.3332 | 1 | [5 empty] | 379 | 43.0344 | 0 | [5 empty] | 379 | 35.499 | 1
[9 empty] | 380 | 34.1767 | 1 | [5 empty] | 380 | 46.9067 | 0 | [5 empty] | 380 | 33.7188 | 1
[9 empty] | 381 | 37.9131 | 1 | [5 empty] | 381 | 44.121 | 0 | [5 empty] | 381 | 40.7012 | 0
[9 empty] | 382 | 34.4984 | 1 | [5 empty] | 382 | 47.0874 | 0 | [5 empty] | 382 | 37.7621 | 1
[9 empty] | 383 | 36.615 | 1 | [5 empty] | 383 | 43.7103 | 0 | [5 empty] | 383 | 40.5853 | 0
[9 empty] | 384 | 35.8708 | 1 | [5 empty] | 384 | 48.2453 | 0 | [5 empty] | 384 | 38.5483 | 0
[9 empty] | 385 | 36.5257 | 1 | [5 empty] | 385 | 47.6622 | 0 | [5 empty] | 385 | 43.7051 | 0
[9 empty] | 386 | 37.0464 | 1 | [5 empty] | 386 | 39.2103 | 0 | [5 empty] | 386 | 32.6034 | 1
[9 empty] | 387 | 42.4986 | 0 | [5 empty] | 387 | 45.3096 | 0 | [5 empty] | 387 | 35.2603 | 1
[9 empty] | 388 | 33.8851 | 1 | [5 empty] | 388 | 44.4627 | 0 | [5 empty] | 388 | 40.66 | 0
[9 empty] | 389 | 34.1165 | 1 | [5 empty] | 389 | 47.6748 | 0 | [5 empty] | 389 | 38.6342 | 0
[9 empty] | 390 | 42.9418 | 0 | [5 empty] | 390 | 51.6539 | 0 | [5 empty] | 390 | 34.6758 | 1
[9 empty] | 391 | 42.3131 | 0 | [5 empty] | 391 | 43.5997 | 0 | [5 empty] | 391 | 36.2709 | 1
[9 empty] | 392 | 41.5477 | 0 | [5 empty] | 392 | 50.0038 | 0 | [5 empty] | 392 | 41.8465 | 0
[9 empty] | 393 | 36.3937 | 1 | [5 empty] | 393 | 49.5875 | 0 | [5 empty] | 393 | 36.504 | 1
[9 empty] | 394 | 39.2181 | 0 | [5 empty] | 394 | 44.7468 | 0 | [5 empty] | 394 | 32.8816 | 1
[9 empty] | 395 | 37.9476 | 1 | [5 empty] | 395 | 48.5213 | 0 | [5 empty] | 395 | 36.2489 | 1
[9 empty] | 396 | 36.6121 | 1 | [5 empty] | 396 | 42.7786 | 0 | [5 empty] | 396 | 37.5563 | 1
[9 empty] | 397 | 37.7907 | 1 | [5 empty] | 397 | 49.6158 | 0 | [5 empty] | 397 | 36.0929 | 1
[9 empty] | 398 | 43.4212 | 0 | [5 empty] | 398 | 41.6619 | 0 | [5 empty] | 398 | 36.7986 | 1
[9 empty] | 399 | 37.8459 | 1 | [5 empty] | 399 | 49.0018 | 0 | [5 empty] | 399 | 41.1182 | 0
[9 empty] | 400 | 37.9782 | 1 | [5 empty] | 400 | 47.7666 | 0 | [5 empty] | 400 | 35.0091 | 1
[9 empty] | 401 | 34.3299 | 1 | [5 empty] | 401 | 49.3842 | 0 | [5 empty] | 401 | 35.4741 | 1
[9 empty] | 402 | 34.974 | 1 | [5 empty] | 402 | 48.3456 | 0 | [5 empty] | 402 | 37.9307 | 1
[9 empty] | 403 | 40.0713 | 0 | [5 empty] | 403 | 47.4708 | 0 | [5 empty] | 403 | 31.9626 | 1
[9 empty] | 404 | 36.1896 | 1 | [5 empty] | 404 | 47.8137 | 0 | [5 empty] | 404 | 40.1998 | 0
[9 empty] | 405 | 38.7841 | 0 | [5 empty] | 405 | 44.6643 | 0 | [5 empty] | 405 | 33.8072 | 1
[9 empty] | 406 | 41.2166 | 0 | [5 empty] | 406 | 41.0203 | 0 | [5 empty] | 406 | 33.1452 | 1
[9 empty] | 407 | 43.8834 | 0 | [5 empty] | 407 | 46.8728 | 0 | [5 empty] | 407 | 37.5243 | 1
[9 empty] | 408 | 38.5572 | 0 | [5 empty] | 408 | 47.9498 | 0 | [5 empty] | 408 | 29.5818 | 1
[9 empty] | 409 | 36.3187 | 1 | [5 empty] | 409 | 47.711 | 0 | [5 empty] | 409 | 38.2517 | 0
[9 empty] | 410 | 31.801 | 1 | [5 empty] | 410 | 43.0225 | 0 | [5 empty] | 410 | 37.5516 | 1
[9 empty] | 411 | 37.1476 | 1 | [5 empty] | 411 | 44.413 | 0 | [5 empty] | 411 | 37.141 | 1
[9 empty] | 412 | 38.7814 | 0 | [5 empty] | 412 | 40.0956 | 0 | [5 empty] | 412 | 29.9704 | 1
[9 empty] | 413 | 43.7397 | 0 | [5 empty] | 413 | 40.6799 | 0 | [5 empty] | 413 | 31.2511 | 1
[9 empty] | 414 | 38.8643 | 0 | [5 empty] | 414 | 40.4804 | 0 | [5 empty] | 414 | 37.9992 | 1
[9 empty] | 415 | 38.7361 | 0 | [5 empty] | 415 | 44.9228 | 0 | [5 empty] | 415 | 39.5098 | 0
[9 empty] | 416 | 33.8334 | 1 | [5 empty] | 416 | 48.3204 | 0 | [5 empty] | 416 | 37.209 | 1
[9 empty] | 417 | 38.6561 | 0 | [5 empty] | 417 | 48.5472 | 0 | [5 empty] | 417 | 38.4873 | 0
[9 empty] | 418 | 45.4655 | 0 | [5 empty] | 418 | 43.7361 | 0 | [5 empty] | 418 | 33.4232 | 1
[9 empty] | 419 | 42.1575 | 0 | [5 empty] | 419 | 47.9289 | 0 | [5 empty] | 419 | 32.9365 | 1
[9 empty] | 420 | 34.126 | 1 | [5 empty] | 420 | 40.901 | 0 | [5 empty] | 420 | 41.939 | 0
[9 empty] | 421 | 34.1295 | 1 | [5 empty] | 421 | 43.8497 | 0 | [5 empty] | 421 | 35.4316 | 1
[9 empty] | 422 | 47.5246 | 0 | [5 empty] | 422 | 45.0314 | 0 | [5 empty] | 422 | 34.5867 | 1
[9 empty] | 423 | 39.0077 | 0 | [5 empty] | 423 | 38.2236 | 0 | [5 empty] | 423 | 37.3365 | 1
[9 empty] | 424 | 41.3484 | 0 | [5 empty] | 424 | 49.2925 | 0 | [5 empty] | 424 | 32.9869 | 1
[9 empty] | 425 | 38.4327 | 0 | [5 empty] | 425 | 49.6643 | 0 | [5 empty] | 425 | 37.8063 | 1
[9 empty] | 426 | 41.0965 | 0 | [5 empty] | 426 | 41.4454 | 0 | [5 empty] | 426 | 33.1322 | 1
[9 empty] | 427 | 36.7506 | 1 | [5 empty] | 427 | 50.5469 | 0 | [5 empty] | 427 | 37.1209 | 1
[9 empty] | 428 | 38.848 | 0 | [5 empty] | 428 | 39.2318 | 0 | [5 empty] | 428 | 32.05 | 1
[9 empty] | 429 | 39.6515 | 0 | [5 empty] | 429 | 46.6228 | 0 | [5 empty] | 429 | 36.6903 | 1
[9 empty] | 430 | 36.4791 | 1 | [5 empty] | 430 | 51.1606 | 0 | [5 empty] | 430 | 43.9491 | 0
[9 empty] | 431 | 35.534 | 1 | [5 empty] | 431 | 50.4167 | 0 | [5 empty] | 431 | 35.9088 | 1
[9 empty] | 432 | 41.8732 | 0 | [5 empty] | 432 | 45.7525 | 0 | [5 empty] | 432 | 34.9765 | 1
[9 empty] | 433 | 39.6473 | 0 | [5 empty] | 433 | 46.848 | 0 | [5 empty] | 433 | 37.7471 | 1
[9 empty] | 434 | 43.3034 | 0 | [5 empty] | 434 | 44.5562 | 0 | [5 empty] | 434 | 35.8693 | 1
[9 empty] | 435 | 36.7694 | 1 | [5 empty] | 435 | 42.0739 | 0 | [5 empty] | 435 | 35.6719 | 1
[9 empty] | 436 | 35.4598 | 1 | [5 empty] | 436 | 47.8259 | 0 | [5 empty] | 436 | 32.7316 | 1
[9 empty] | 437 | 35.6197 | 1 | [5 empty] | 437 | 49.9373 | 0 | [5 empty] | 437 | 33.5029 | 1
[9 empty] | 438 | 39.1188 | 0 | [5 empty] | 438 | 47.7416 | 0 | [5 empty] | 438 | 32.8456 | 1
[9 empty] | 439 | 37.7331 | 1 | [5 empty] | 439 | 41.478 | 0 | [5 empty] | 439 | 30.3446 | 1
[9 empty] | 440 | 33.5666 | 1 | [5 empty] | 440 | 46.7552 | 0 | [5 empty] | 440 | 33.1257 | 1
[9 empty] | 441 | 34.7297 | 1 | [5 empty] | 441 | 39.3121 | 0 | [5 empty] | 441 | 37.2021 | 1
[9 empty] | 442 | 37.107 | 1 | [5 empty] | 442 | 49.7621 | 0 | [5 empty] | 442 | 35.4024 | 1
[9 empty] | 443 | 38.3509 | 0 | [5 empty] | 443 | 47.9343 | 0 | [5 empty] | 443 | 33.7352 | 1
[9 empty] | 444 | 45.4121 | 0 | [5 empty] | 444 | 48.7486 | 0 | [5 empty] | 444 | 36.5741 | 1
[9 empty] | 445 | 38.9497 | 0 | [5 empty] | 445 | 51.2587 | 0 | [5 empty] | 445 | 32.0107 | 1
[9 empty] | 446 | 36.4563 | 1 | [5 empty] | 446 | 50.2311 | 0 | [5 empty] | 446 | 37.9084 | 1
[9 empty] | 447 | 38.6387 | 0 | [5 empty] | 447 | 48.0672 | 0 | [5 empty] | 447 | 37.0742 | 1
[9 empty] | 448 | 35.4016 | 1 | [5 empty] | 448 | 43.6265 | 0 | [5 empty] | 448 | 37.1503 | 1
[9 empty] | 449 | 39.6394 | 0 | [5 empty] | 449 | 41.1991 | 0 | [5 empty] | 449 | 39.3651 | 0
[9 empty] | 450 | 42.3435 | 0 | [5 empty] | 450 | 47.0157 | 0 | [5 empty] | 450 | 31.0412 | 1
[9 empty] | 451 | 37.9068 | 1 | [5 empty] | 451 | 50.9142 | 0 | [5 empty] | 451 | 32.6169 | 1
[9 empty] | 452 | 36.8555 | 1 | [5 empty] | 452 | 48.2265 | 0 | [5 empty] | 452 | 40.1138 | 0
[9 empty] | 453 | 36.3814 | 1 | [5 empty] | 453 | 41.024 | 0 | [5 empty] | 453 | 40.7909 | 0
[9 empty] | 454 | 38.4761 | 0 | [5 empty] | 454 | 49.5807 | 0 | [5 empty] | 454 | 39.3469 | 0
[9 empty] | 455 | 37.1678 | 1 | [5 empty] | 455 | 38.75 | 0 | [5 empty] | 455 | 35.0666 | 1
[9 empty] | 456 | 39.9485 | 0 | [5 empty] | 456 | 49.3554 | 0 | [5 empty] | 456 | 39.0667 | 0
[9 empty] | 457 | 42.8322 | 0 | [5 empty] | 457 | 50.6279 | 0 | [5 empty] | 457 | 33.4027 | 1
[9 empty] | 458 | 36.2383 | 1 | [5 empty] | 458 | 47.4661 | 0 | [5 empty] | 458 | 37.4321 | 1
[9 empty] | 459 | 33.8296 | 1 | [5 empty] | 459 | 43.2311 | 0 | [5 empty] | 459 | 32.7643 | 1
[9 empty] | 460 | 39.7052 | 0 | [5 empty] | 460 | 40.737 | 0 | [5 empty] | 460 | 38.2263 | 0
[9 empty] | 461 | 43.2565 | 0 | [5 empty] | 461 | 47.5458 | 0 | [5 empty] | 461 | 34.7374 | 1
[9 empty] | 462 | 38.2069 | 0 | [5 empty] | 462 | 51.4773 | 0 | [5 empty] | 462 | 33.5019 | 1
[9 empty] | 463 | 34.9207 | 1 | [5 empty] | 463 | 46.7116 | 0 | [5 empty] | 463 | 38.9124 | 0
[9 empty] | 464 | 34.6893 | 1 | [5 empty] | 464 | 47.5414 | 0 | [5 empty] | 464 | 34.8772 | 1
[9 empty] | 465 | 29.889 | 1 | [5 empty] | 465 | 37.9669 | 1 | [5 empty] | 465 | 37.9159 | 1
[9 empty] | 466 | 35.8725 | 1 | [5 empty] | 466 | 47.0491 | 0 | [5 empty] | 466 | 36.168 | 1
[9 empty] | 467 | 38.0888 | 0 | [5 empty] | 467 | 48.3167 | 0 | [5 empty] | 467 | 33.6921 | 1
[9 empty] | 468 | 40.8418 | 0 | [5 empty] | 468 | 48.0632 | 0 | [5 empty] | 468 | 37.9017 | 1
[9 empty] | 469 | 38.78 | 0 | [5 empty] | 469 | 46.9218 | 0 | [5 empty] | 469 | 42.6591 | 0
[9 empty] | 470 | 35.2782 | 1 | [5 empty] | 470 | 49.7132 | 0 | [5 empty] | 470 | 35.8321 | 1
[9 empty] | 471 | 42.2052 | 0 | [5 empty] | 471 | 44.8336 | 0 | [5 empty] | 471 | 33.8321 | 1
[9 empty] | 472 | 36.5487 | 1 | [5 empty] | 472 | 41.9901 | 0 | [5 empty] | 472 | 32.8311 | 1
[9 empty] | 473 | 39.46 | 0 | [5 empty] | 473 | 38.4231 | 0 | [5 empty] | 473 | 29.8947 | 1
[9 empty] | 474 | 41.1081 | 0 | [5 empty] | 474 | 43.8222 | 0 | [5 empty] | 474 | 31.0459 | 1
[9 empty] | 475 | 33.6879 | 1 | [5 empty] | 475 | 41.7373 | 0 | [5 empty] | 475 | 37.7929 | 1
[9 empty] | 476 | 37.504 | 1 | [5 empty] | 476 | 48.9492 | 0 | [5 empty] | 476 | 33.2504 | 1
[9 empty] | 477 | 43.386 | 0 | [5 empty] | 477 | 40.7574 | 0 | [5 empty] | 477 | 40.1724 | 0
[9 empty] | 478 | 40.7282 | 0 | [5 empty] | 478 | 43.3295 | 0 | [5 empty] | 478 | 34.7421 | 1
[9 empty] | 479 | 36.1523 | 1 | [5 empty] | 479 | 50.0758 | 0 | [5 empty] | 479 | 31.2994 | 1
[9 empty] | 480 | 38.9891 | 0 | [5 empty] | 480 | 44.4776 | 0 | [5 empty] | 480 | 39.8287 | 0
[9 empty] | 481 | 42.2493 | 0 | [5 empty] | 481 | 45.5705 | 0 | [5 empty] | 481 | 39.7952 | 0
[9 empty] | 482 | 31.0307 | 1 | [5 empty] | 482 | 46.1828 | 0 | [5 empty] | 482 | 35.4924 | 1
[9 empty] | 483 | 36.2507 | 1 | [5 empty] | 483 | 48.1266 | 0 | [5 empty] | 483 | 35.1437 | 1
[9 empty] | 484 | 32.4356 | 1 | [5 empty] | 484 | 47.713 | 0 | [5 empty] | 484 | 34.7547 | 1
[9 empty] | 485 | 35.0136 | 1 | [5 empty] | 485 | 42.2991 | 0 | [5 empty] | 485 | 29.7029 | 1
[9 empty] | 486 | 40.3416 | 0 | [5 empty] | 486 | 50.3573 | 0 | [5 empty] | 486 | 42.798 | 0
[9 empty] | 487 | 33.7648 | 1 | [5 empty] | 487 | 48.1378 | 0 | [5 empty] | 487 | 38.5025 | 0
[9 empty] | 488 | 36.2566 | 1 | [5 empty] | 488 | 48.4451 | 0 | [5 empty] | 488 | 34.5221 | 1
[9 empty] | 489 | 39.6103 | 0 | [5 empty] | 489 | 46.9443 | 0 | [5 empty] | 489 | 32.4858 | 1
[9 empty] | 490 | 34.97 | 1 | [5 empty] | 490 | 50.3811 | 0 | [5 empty] | 490 | 34.1857 | 1
[9 empty] | 491 | 37.5175 | 1 | [5 empty] | 491 | 40.6666 | 0 | [5 empty] | 491 | 34.8913 | 1
[9 empty] | 492 | 35.918 | 1 | [5 empty] | 492 | 48.5795 | 0 | [5 empty] | 492 | 32.4477 | 1
[9 empty] | 493 | 34.5369 | 1 | [5 empty] | 493 | 48.8705 | 0 | [5 empty] | 493 | 36.5469 | 1
[9 empty] | 494 | 39.0288 | 0 | [5 empty] | 494 | 51.0821 | 0 | [5 empty] | 494 | 35.1957 | 1
[9 empty] | 495 | 34.1573 | 1 | [5 empty] | 495 | 46.7898 | 0 | [5 empty] | 495 | 32.5467 | 1
[9 empty] | 496 | 37.4432 | 1 | [5 empty] | 496 | 46.6618 | 0 | [5 empty] | 496 | 38.0744 | 0
[9 empty] | 497 | 37.8819 | 1 | [5 empty] | 497 | 50.3777 | 0 | [5 empty] | 497 | 38.7436 | 0
[9 empty] | 498 | 36.075 | 1 | [5 empty] | 498 | 43.2392 | 0 | [5 empty] | 498 | 33.4709 | 1
[9 empty] | 499 | 38.8625 | 0 | [5 empty] | 499 | 52.1212 | 0 | [5 empty] | 499 | 38.538 | 0
[9 empty] | 500 | 37.9464 | 1 | [5 empty] | 500 | 50.8986 | 0 | [5 empty] | 500 | 35.7765 | 1
[9 empty] | 501 | 41.6807 | 0 | [5 empty] | 501 | 50.1272 | 0 | [5 empty] | 501 | 29.5635 | 1
[9 empty] | 502 | 37.5361 | 1 | [5 empty] | 502 | 38.8419 | 0 | [5 empty] | 502 | 33.9659 | 1
[9 empty] | 503 | 32.9453 | 1 | [5 empty] | 503 | 46.2983 | 0 | [5 empty] | 503 | 35.4056 | 1
[9 empty] | 504 | 38.8491 | 0 | [5 empty] | 504 | 43.3716 | 0 | [5 empty] | 504 | 38.622 | 0
[9 empty] | 505 | 34.3369 | 1 | [5 empty] | 505 | 43.1713 | 0 | [5 empty] | 505 | 38.2676 | 0
[9 empty] | 506 | 38.3565 | 0 | [5 empty] | 506 | 50.9042 | 0 | [5 empty] | 506 | 41.3277 | 0
[9 empty] | 507 | 35.2363 | 1 | [5 empty] | 507 | 45.1335 | 0 | [5 empty] | 507 | 31.5715 | 1
[9 empty] | 508 | 43.5024 | 0 | [5 empty] | 508 | 46.3793 | 0 | [5 empty] | 508 | 34.4346 | 1
[9 empty] | 509 | 36.4623 | 1 | [5 empty] | 509 | 49.2181 | 0 | [5 empty] | 509 | 30.8943 | 1
[9 empty] | 510 | 32.5284 | 1 | [5 empty] | 510 | 50.6515 | 0 | [5 empty] | 510 | 31.1255 | 1
[9 empty] | 511 | 36.1549 | 1 | [5 empty] | 511 | 47.6304 | 0 | [5 empty] | 511 | 42.7623 | 0
[9 empty] | 512 | 34.3145 | 1 | [5 empty] | 512 | 39.3134 | 0 | [5 empty] | 512 | 36.037 | 1
[9 empty] | 513 | 31.9217 | 1 | [5 empty] | 513 | 36.9743 | 1 | [5 empty] | 513 | 30.7577 | 1
[9 empty] | 514 | 39.9462 | 0 | [5 empty] | 514 | 51.138 | 0 | [5 empty] | 514 | 34.0237 | 1
[9 empty] | 515 | 36.9316 | 1 | [5 empty] | 515 | 50.2243 | 0 | [5 empty] | 515 | 34.9322 | 1
[9 empty] | 516 | 34.7829 | 1 | [5 empty] | 516 | 45.9195 | 0 | [5 empty] | 516 | 35.1402 | 1
[9 empty] | 517 | 38.2946 | 0 | [5 empty] | 517 | 50.5832 | 0 | [5 empty] | 517 | 42.2823 | 0
[9 empty] | 518 | 37.5358 | 1 | [5 empty] | 518 | 43.2187 | 0 | [5 empty] | 518 | 41.5511 | 0
[9 empty] | 519 | 33.7392 | 1 | [5 empty] | 519 | 52.2348 | 0 | [5 empty] | 519 | 33.1345 | 1
[9 empty] | 520 | 41.0836 | 0 | [5 empty] | 520 | 41.3528 | 0 | [5 empty] | 520 | 30.6048 | 1
[9 empty] | 521 | 35.2002 | 1 | [5 empty] | 521 | 53.1649 | 0 | [5 empty] | 521 | 34.0456 | 1
[9 empty] | 522 | 40.0491 | 0 | [5 empty] | 522 | 46.4408 | 0 | [5 empty] | 522 | 37.0895 | 1
[9 empty] | 523 | 36.0426 | 1 | [5 empty] | 523 | 41.4722 | 0 | [5 empty] | 523 | 28.3297 | 1
[9 empty] | 524 | 42.6919 | 0 | [5 empty] | 524 | 44.8452 | 0 | [5 empty] | 524 | 38.7761 | 0
[9 empty] | 525 | 42.1059 | 0 | [5 empty] | 525 | 41.1649 | 0 | [5 empty] | 525 | 39.0483 | 0
[9 empty] | 526 | 35.3153 | 1 | [5 empty] | 526 | 47.0581 | 0 | [5 empty] | 526 | 34.5678 | 1
[9 empty] | 527 | 40.4687 | 0 | [5 empty] | 527 | 46.9186 | 0 | [5 empty] | 527 | 34.5786 | 1
[9 empty] | 528 | 34.7716 | 1 | [5 empty] | 528 | 45.0056 | 0 | [5 empty] | 528 | 37.0167 | 1
[9 empty] | 529 | 32.384 | 1 | [5 empty] | 529 | 42.0948 | 0 | [5 empty] | 529 | 33.6303 | 1
[9 empty] | 530 | 39.9322 | 0 | [5 empty] | 530 | 42.2763 | 0 | [5 empty] | 530 | 32.4464 | 1
[9 empty] | 531 | 38.4064 | 0 | [5 empty] | 531 | 37.2617 | 1 | [5 empty] | 531 | 35.9845 | 1
[9 empty] | 532 | 39.2866 | 0 | [5 empty] | 532 | 44.751 | 0 | [5 empty] | 532 | 31.1313 | 1
[9 empty] | 533 | 40.6666 | 0 | [5 empty] | 533 | 43.2371 | 0 | [5 empty] | 533 | 39.5749 | 0
[9 empty] | 534 | 32.5009 | 1 | [5 empty] | 534 | 49.1948 | 0 | [5 empty] | 534 | 34.693 | 1
[9 empty] | 535 | 31.4136 | 1 | [5 empty] | 535 | 37.4792 | 1 | [5 empty] | 535 | 30.9767 | 1
[9 empty] | 536 | 33.8482 | 1 | [5 empty] | 536 | 44.5921 | 0 | [5 empty] | 536 | 41.4439 | 0
[9 empty] | 537 | 36.5029 | 1 | [5 empty] | 537 | 49.5167 | 0 | [5 empty] | 537 | 29.8251 | 1
[9 empty] | 538 | 40.3138 | 0 | [5 empty] | 538 | 38.8314 | 0 | [5 empty] | 538 | 33.5576 | 1
[9 empty] | 539 | 37.336 | 1 | [5 empty] | 539 | 49.2605 | 0 | [5 empty] | 539 | 32.2646 | 1
[9 empty] | 540 | 35.4957 | 1 | [5 empty] | 540 | 46.4998 | 0 | [5 empty] | 540 | 33.8377 | 1
[9 empty] | 541 | 45.8099 | 0 | [5 empty] | 541 | 46.7232 | 0 | [5 empty] | 541 | 39.4958 | 0
[9 empty] | 542 | 36.7705 | 1 | [5 empty] | 542 | 47.9957 | 0 | [5 empty] | 542 | 30.9621 | 1
[9 empty] | 543 | 35.9518 | 1 | [5 empty] | 543 | 48.0355 | 0 | [5 empty] | 543 | 34.0134 | 1
[9 empty] | 544 | 35.9681 | 1 | [5 empty] | 544 | 50.4058 | 0 | [5 empty] | 544 | 44.716 | 0
[9 empty] | 545 | 32.6403 | 1 | [5 empty] | 545 | 47.365 | 0 | [5 empty] | 545 | 38.8873 | 0
[9 empty] | 546 | 36.0706 | 1 | [5 empty] | 546 | 46.825 | 0 | [5 empty] | 546 | 41.9482 | 0
[9 empty] | 547 | 40.2954 | 0 | [5 empty] | 547 | 45.6015 | 0 | [5 empty] | 547 | 33.6841 | 1
[9 empty] | 548 | 41.9007 | 0 | [5 empty] | 548 | 45.6544 | 0 | [5 empty] | 548 | 30.6774 | 1
[9 empty] | 549 | 35.7639 | 1 | [5 empty] | 549 | 49.3674 | 0 | [5 empty] | 549 | 36.5249 | 1
[9 empty] | 550 | 33.2512 | 1 | [5 empty] | 550 | 47.7869 | 0 | [5 empty] | 550 | 35.3662 | 1
[9 empty] | 551 | 38.2251 | 0 | [5 empty] | 551 | 49.4574 | 0 | [5 empty] | 551 | 33.2486 | 1
[9 empty] | 552 | 38.8738 | 0 | [5 empty] | 552 | 47.4953 | 0 | [5 empty] | 552 | 35.4082 | 1
[9 empty] | 553 | 36.9784 | 1 | [5 empty] | 553 | 43.2235 | 0 | [5 empty] | 553 | 40.6523 | 0
[9 empty] | 554 | 33.3063 | 1 | [5 empty] | 554 | 48.239 | 0 | [5 empty] | 554 | 37.7459 | 1
[9 empty] | 555 | 39.7817 | 0 | [5 empty] | 555 | 49.554 | 0 | [5 empty] | 555 | 33.793 | 1
[9 empty] | 556 | 41.5362 | 0 | [5 empty] | 556 | 50.0735 | 0 | [5 empty] | 556 | 43.2989 | 0
[9 empty] | 557 | 35.9401 | 1 | [5 empty] | 557 | 39.9596 | 0 | [5 empty] | 557 | 35.2651 | 1
[9 empty] | 558 | 34.1452 | 1 | [5 empty] | 558 | 46.2538 | 0 | [5 empty] | 558 | 34.7184 | 1
[9 empty] | 559 | 35.393 | 1 | [5 empty] | 559 | 41.5007 | 0 | [5 empty] | 559 | 34.7541 | 1
[9 empty] | 560 | 43.9414 | 0 | [5 empty] | 560 | 48.4215 | 0 | [5 empty] | 560 | 35.4014 | 1
[9 empty] | 561 | 38.403 | 0 | [5 empty] | 561 | 48.2348 | 0 | [5 empty] | 561 | 38.7038 | 0
[9 empty] | 562 | 36.4421 | 1 | [5 empty] | 562 | 41.0758 | 0 | [5 empty] | 562 | 34.3031 | 1
[9 empty] | 563 | 35.3245 | 1 | [5 empty] | 563 | 37.0659 | 1 | [5 empty] | 563 | 33.4219 | 1
[9 empty] | 564 | 39.542 | 0 | [5 empty] | 564 | 45.4541 | 0 | [5 empty] | 564 | 39.2923 | 0
[9 empty] | 565 | 37.6977 | 1 | [5 empty] | 565 | 40.8835 | 0 | [5 empty] | 565 | 35.4838 | 1
[9 empty] | 566 | 38.3735 | 0 | [5 empty] | 566 | 43.7241 | 0 | [5 empty] | 566 | 40.0469 | 0
[9 empty] | 567 | 33.1144 | 1 | [5 empty] | 567 | 48.1923 | 0 | [5 empty] | 567 | 35.7985 | 1
[9 empty] | 568 | 34.5342 | 1 | [5 empty] | 568 | 49.8984 | 0 | [5 empty] | 568 | 44.9638 | 0
[9 empty] | 569 | 34.7246 | 1 | [5 empty] | 569 | 42.7763 | 0 | [5 empty] | 569 | 33.6607 | 1
[9 empty] | 570 | 35.4683 | 1 | [5 empty] | 570 | 42.6163 | 0 | [5 empty] | 570 | 39.3376 | 0
[9 empty] | 571 | 42.161 | 0 | [5 empty] | 571 | 49.5421 | 0 | [5 empty] | 571 | 31.3348 | 1
[9 empty] | 572 | 42.0092 | 0 | [5 empty] | 572 | 42.9107 | 0 | [5 empty] | 572 | 33.6903 | 1
[9 empty] | 573 | 36.7917 | 1 | [5 empty] | 573 | 43.4684 | 0 | [5 empty] | 573 | 36.7334 | 1
[9 empty] | 574 | 35.8604 | 1 | [5 empty] | 574 | 41.4938 | 0 | [5 empty] | 574 | 31.9776 | 1
[9 empty] | 575 | 37.302 | 1 | [5 empty] | 575 | 42.9433 | 0 | [5 empty] | 575 | 30.1349 | 1
[9 empty] | 576 | 39.6228 | 0 | [5 empty] | 576 | 47.497 | 0 | [5 empty] | 576 | 41.1211 | 0
[9 empty] | 577 | 33.7429 | 1 | [5 empty] | 577 | 52.6507 | 0 | [5 empty] | 577 | 39.0505 | 0
[9 empty] | 578 | 36.1338 | 1 | [5 empty] | 578 | 42.9956 | 0 | [5 empty] | 578 | 33.9413 | 1
[9 empty] | 579 | 39.4678 | 0 | [5 empty] | 579 | 46.6271 | 0 | [5 empty] | 579 | 33.4993 | 1
[9 empty] | 580 | 41.9872 | 0 | [5 empty] | 580 | 39.5303 | 0 | [5 empty] | 580 | 31.3302 | 1
[9 empty] | 581 | 33.6995 | 1 | [5 empty] | 581 | 51.3037 | 0 | [5 empty] | 581 | 33.0541 | 1
[9 empty] | 582 | 39.0865 | 0 | [5 empty] | 582 | 42.2986 | 0 | [5 empty] | 582 | 40.245 | 0
[9 empty] | 583 | 36.7308 | 1 | [5 empty] | 583 | 44.4223 | 0 | [5 empty] | 583 | 33.6457 | 1
[9 empty] | 584 | 33.6067 | 1 | [5 empty] | 584 | 47.0701 | 0 | [5 empty] | 584 | 37.9146 | 1
[9 empty] | 585 | 34.6619 | 1 | [5 empty] | 585 | 47.9315 | 0 | [5 empty] | 585 | 35.4159 | 1
[9 empty] | 586 | 34.4167 | 1 | [5 empty] | 586 | 41.8445 | 0 | [5 empty] | 586 | 31.4941 | 1
[9 empty] | 587 | 41.6248 | 0 | [5 empty] | 587 | 47.5264 | 0 | [5 empty] | 587 | 44.1775 | 0
[9 empty] | 588 | 35.9473 | 1 | [5 empty] | 588 | 38.8542 | 0 | [5 empty] | 588 | 32.207 | 1
[9 empty] | 589 | 33.9647 | 1 | [5 empty] | 589 | 49.8049 | 0 | [5 empty] | 589 | 37.8785 | 1
[9 empty] | 590 | 42.1736 | 0 | [5 empty] | 590 | 34.7519 | 1 | [5 empty] | 590 | 37.0706 | 1
[9 empty] | 591 | 33.1724 | 1 | [5 empty] | 591 | 38.6687 | 0 | [5 empty] | 591 | 38.8721 | 0
[9 empty] | 592 | 34.4532 | 1 | [5 empty] | 592 | 45.8476 | 0 | [5 empty] | 592 | 40.0265 | 0
[9 empty] | 593 | 46.113 | 0 | [5 empty] | 593 | 47.4843 | 0 | [5 empty] | 593 | 42.9498 | 0
[9 empty] | 594 | 31.7618 | 1 | [5 empty] | 594 | 45.9924 | 0 | [5 empty] | 594 | 36.1725 | 1
[9 empty] | 595 | 43.9315 | 0 | [5 empty] | 595 | 49.6411 | 0 | [5 empty] | 595 | 30.2366 | 1
[9 empty] | 596 | 39.0635 | 0 | [5 empty] | 596 | 48.6555 | 0 | [5 empty] | 596 | 31.8778 | 1
[9 empty] | 597 | 35.6642 | 1 | [5 empty] | 597 | 43.9236 | 0 | [5 empty] | 597 | 42.8067 | 0
[9 empty] | 598 | 34.0659 | 1 | [5 empty] | 598 | 48.7949 | 0 | [5 empty] | 598 | 33.044 | 1
[9 empty] | 599 | 47.1794 | 0 | [5 empty] | 599 | 48.6006 | 0 | [5 empty] | 599 | 44.2813 | 0
[9 empty] | 600 | 39.3977 | 0 | [5 empty] | 600 | 41.0534 | 0 | [5 empty] | 600 | 38.8122 | 0
[9 empty] | 601 | 33.9387 | 1 | [5 empty] | 601 | 44.933 | 0 | [5 empty] | 601 | 29.3416 | 1
[9 empty] | 602 | 43.4094 | 0 | [5 empty] | 602 | 38.1826 | 0 | [5 empty] | 602 | 33.4129 | 1
[9 empty] | 603 | 40.0867 | 0 | [5 empty] | 603 | 47.7447 | 0 | [5 empty] | 603 | 35.9778 | 1
[9 empty] | 604 | 38.9995 | 0 | [5 empty] | 604 | 45.8946 | 0 | [5 empty] | 604 | 33.7678 | 1
[9 empty] | 605 | 38.3954 | 0 | [5 empty] | 605 | 50.0758 | 0 | [5 empty] | 605 | 33.3193 | 1
[9 empty] | 606 | 37.9676 | 1 | [5 empty] | 606 | 44.2693 | 0 | [5 empty] | 606 | 28.831 | 1
[9 empty] | 607 | 34.1482 | 1 | [5 empty] | 607 | 46.0586 | 0 | [5 empty] | 607 | 34.5263 | 1
[9 empty] | 608 | 39.123 | 0 | [5 empty] | 608 | 49.4889 | 0 | [5 empty] | 608 | 35.5609 | 1
[9 empty] | 609 | 37.9228 | 1 | [5 empty] | 609 | 50.8082 | 0 | [5 empty] | 609 | 35.708 | 1
[9 empty] | 610 | 42.1652 | 0 | [5 empty] | 610 | 37.7489 | 1 | [5 empty] | 610 | 31.9526 | 1
[9 empty] | 611 | 35.3868 | 1 | [5 empty] | 611 | 50.3669 | 0 | [5 empty] | 611 | 44.1399 | 0
[9 empty] | 612 | 33.8732 | 1 | [5 empty] | 612 | 49.5073 | 0 | [5 empty] | 612 | 40.2825 | 0
[9 empty] | 613 | 38.9728 | 0 | [5 empty] | 613 | 44.8774 | 0 | [5 empty] | 613 | 32.3229 | 1
[9 empty] | 614 | 35.99 | 1 | [5 empty] | 614 | 45.4971 | 0 | [5 empty] | 614 | 43.0064 | 0
[9 empty] | 615 | 42.3084 | 0 | [5 empty] | 615 | 42.938 | 0 | [5 empty] | 615 | 34.5604 | 1
[9 empty] | 616 | 35.3235 | 1 | [5 empty] | 616 | 48.9705 | 0 | [5 empty] | 616 | 42.6761 | 0
[9 empty] | 617 | 39.4575 | 0 | [5 empty] | 617 | 47.4065 | 0 | [5 empty] | 617 | 30.3381 | 1
[9 empty] | 618 | 34.4212 | 1 | [5 empty] | 618 | 45.3599 | 0 | [5 empty] | 618 | 40.6193 | 0
[9 empty] | 619 | 40.6436 | 0 | [5 empty] | 619 | 49.2244 | 0 | [5 empty] | 619 | 27.2982 | 1
[9 empty] | 620 | 40.0902 | 0 | [5 empty] | 620 | 51.4606 | 0 | [5 empty] | 620 | 38.6814 | 0
[9 empty] | 621 | 35.1006 | 1 | [5 empty] | 621 | 46.8768 | 0 | [5 empty] | 621 | 33.1844 | 1
[9 empty] | 622 | 37.4167 | 1 | [5 empty] | 622 | 42.4499 | 0 | [5 empty] | 622 | 35.3692 | 1
[9 empty] | 623 | 37.8206 | 1 | [5 empty] | 623 | 48.5575 | 0 | [5 empty] | 623 | 37.8565 | 1
[9 empty] | 624 | 34.9233 | 1 | [5 empty] | 624 | 44.2408 | 0 | [5 empty] | 624 | 33.4842 | 1
[9 empty] | 625 | 35.4501 | 1 | [5 empty] | 625 | 44.8699 | 0 | [5 empty] | 625 | 40.0938 | 0
[9 empty] | 626 | 42.793 | 0 | [5 empty] | 626 | 34.6565 | 1 | [5 empty] | 626 | 31.7043 | 1
[9 empty] | 627 | 35.2109 | 1 | [5 empty] | 627 | 41.887 | 0 | [5 empty] | 627 | 32.2711 | 1
[9 empty] | 628 | 37.27 | 1 | [5 empty] | 628 | 44.2706 | 0 | [5 empty] | 628 | 29.2062 | 1
[9 empty] | 629 | 36.4627 | 1 | [5 empty] | 629 | 44.2336 | 0 | [5 empty] | 629 | 37.5782 | 1
[9 empty] | 630 | 40.8369 | 0 | [5 empty] | 630 | 42.2828 | 0 | [5 empty] | 630 | 31.1296 | 1
[9 empty] | 631 | 43.2768 | 0 | [5 empty] | 631 | 48.9742 | 0 | [5 empty] | 631 | 32.8509 | 1
[9 empty] | 632 | 37.4097 | 1 | [5 empty] | 632 | 42.9548 | 0 | [5 empty] | 632 | 38.0897 | 0
[9 empty] | 633 | 38.711 | 0 | [5 empty] | 633 | 47.8226 | 0 | [5 empty] | 633 | 35.5077 | 1
[9 empty] | 634 | 34.5422 | 1 | [5 empty] | 634 | 45.6262 | 0 | [5 empty] | 634 | 37.6208 | 1
[9 empty] | 635 | 39.644 | 0 | [5 empty] | 635 | 43.5123 | 0 | [5 empty] | 635 | 37.6133 | 1
[9 empty] | 636 | 37.5151 | 1 | [5 empty] | 636 | 49.2805 | 0 | [5 empty] | 636 | 33.1475 | 1
[9 empty] | 637 | 35.6477 | 1 | [5 empty] | 637 | 50.8449 | 0 | [5 empty] | 637 | 33.8382 | 1
[9 empty] | 638 | 42.8887 | 0 | [5 empty] | 638 | 42.1096 | 0 | [5 empty] | 638 | 41.9259 | 0
[9 empty] | 639 | 38.092 | 0 | [5 empty] | 639 | 51.0172 | 0 | [5 empty] | 639 | 29.8757 | 1
[9 empty] | 640 | 37.4046 | 1 | [5 empty] | 640 | 42.0138 | 0 | [5 empty] | 640 | 35.7268 | 1
[9 empty] | 641 | 33.0945 | 1 | [5 empty] | 641 | 46.6828 | 0 | [5 empty] | 641 | 41.7222 | 0
[9 empty] | 642 | 37.001 | 1 | [5 empty] | 642 | 45.7149 | 0 | [5 empty] | 642 | 41.2527 | 0
[9 empty] | 643 | 37.95 | 1 | [5 empty] | 643 | 43.2767 | 0 | [5 empty] | 643 | 37.879 | 1
[9 empty] | 644 | 39.0462 | 0 | [5 empty] | 644 | 49.0199 | 0 | [5 empty] | 644 | 50.1431 | 0
[9 empty] | 645 | 33.2676 | 1 | [5 empty] | 645 | 46.8644 | 0 | [5 empty] | 645 | 36.6942 | 1
[9 empty] | 646 | 35.4467 | 1 | [5 empty] | 646 | 46.7617 | 0 | [5 empty] | 646 | 36.522 | 1
[9 empty] | 647 | 37.59 | 1 | [5 empty] | 647 | 42.7691 | 0 | [5 empty] | 647 | 39.5669 | 0
[9 empty] | 648 | 35.0658 | 1 | [5 empty] | 648 | 39.9774 | 0 | [5 empty] | 648 | 33.4852 | 1
[9 empty] | 649 | 38.9164 | 0 | [5 empty] | 649 | 49.0809 | 0 | [5 empty] | 649 | 36.2335 | 1
[9 empty] | 650 | 33.7182 | 1 | [5 empty] | 650 | 45.4344 | 0 | [5 empty] | 650 | 33.1339 | 1
[9 empty] | 651 | 37.5229 | 1 | [5 empty] | 651 | 46.9383 | 0 | [5 empty] | 651 | 35.1066 | 1
[9 empty] | 652 | 38.2845 | 0 | [5 empty] | 652 | 50.0806 | 0 | [5 empty] | 652 | 36.7295 | 1
[9 empty] | 653 | 36.4849 | 1 | [5 empty] | 653 | 38.1352 | 0 | [5 empty] | 653 | 33.8005 | 1
[9 empty] | 654 | 34.1104 | 1 | [5 empty] | 654 | 41.1654 | 0 | [5 empty] | 654 | 41.5445 | 0
[9 empty] | 655 | 35.1516 | 1 | [5 empty] | 655 | 40.1193 | 0 | [5 empty] | 655 | 35.2776 | 1
[9 empty] | 656 | 43.23 | 0 | [5 empty] | 656 | 44.417 | 0 | [5 empty] | 656 | 37.9973 | 1
[9 empty] | 657 | 34.5457 | 1 | [5 empty] | 657 | 47.3163 | 0 | [5 empty] | 657 | 29.0292 | 1
[9 empty] | 658 | 39.2059 | 0 | [5 empty] | 658 | 45.387 | 0 | [5 empty] | 658 | 34.9461 | 1
[9 empty] | 659 | 40.6314 | 0 | [5 empty] | 659 | 45.4201 | 0 | [5 empty] | 659 | 37.5609 | 1
[9 empty] | 660 | 31.0588 | 1 | [5 empty] | 660 | 48.6701 | 0 | [5 empty] | 660 | 32.9331 | 1
[9 empty] | 661 | 40.5976 | 0 | [5 empty] | 661 | 46.2654 | 0 | [5 empty] | 661 | 35.1171 | 1
[9 empty] | 662 | 45.6857 | 0 | [5 empty] | 662 | 36.1555 | 1 | [5 empty] | 662 | 44.4419 | 0
[9 empty] | 663 | 45.2616 | 0 | [5 empty] | 663 | 43.1998 | 0 | [5 empty] | 663 | 40.8715 | 0
[9 empty] | 664 | 34.5099 | 1 | [5 empty] | 664 | 45.699 | 0 | [5 empty] | 664 | 41.4434 | 0
[9 empty] | 665 | 37.6242 | 1 | [5 empty] | 665 | 45.5982 | 0 | [5 empty] | 665 | 33.4048 | 1
[9 empty] | 666 | 41.4104 | 0 | [5 empty] | 666 | 50.0522 | 0 | [5 empty] | 666 | 29.6536 | 1
[9 empty] | 667 | 38.8757 | 0 | [5 empty] | 667 | 48.6455 | 0 | [5 empty] | 667 | 31.2396 | 1
[9 empty] | 668 | 42.4754 | 0 | [5 empty] | 668 | 45.1313 | 0 | [5 empty] | 668 | 33.1523 | 1
[9 empty] | 669 | 33.3526 | 1 | [5 empty] | 669 | 48.7054 | 0 | [5 empty] | 669 | 37.7599 | 1
[9 empty] | 670 | 36.2413 | 1 | [5 empty] | 670 | 51.2681 | 0 | [5 empty] | 670 | 37.6922 | 1
[9 empty] | 671 | 42.9443 | 0 | [5 empty] | 671 | 43.3484 | 0 | [5 empty] | 671 | 39.054 | 0
[9 empty] | 672 | 40.3945 | 0 | [5 empty] | 672 | 44.3667 | 0 | [5 empty] | 672 | 35.1705 | 1
[9 empty] | 673 | 41.943 | 0 | [5 empty] | 673 | 47.5621 | 0 | [5 empty] | 673 | 40.1978 | 0
[9 empty] | 674 | 40.181 | 0 | [5 empty] | 674 | 50.3413 | 0 | [5 empty] | 674 | 39.259 | 0
[9 empty] | 675 | 37.9942 | 1 | [5 empty] | 675 | 47.8356 | 0 | [5 empty] | 675 | 38.4483 | 0
[9 empty] | 676 | 41.5801 | 0 | [5 empty] | 676 | 43.3301 | 0 | [5 empty] | 676 | 42.4718 | 0
[9 empty] | 677 | 41.2379 | 0 | [5 empty] | 677 | 54.1503 | 0 | [5 empty] | 677 | 32.0741 | 1
[9 empty] | 678 | 33.736 | 1 | [5 empty] | 678 | 43.3055 | 0 | [5 empty] | 678 | 35.1517 | 1
[9 empty] | 679 | 36.4119 | 1 | [5 empty] | 679 | 43.6603 | 0 | [5 empty] | 679 | 34.7307 | 1
[9 empty] | 680 | 32.9735 | 1 | [5 empty] | 680 | 43.6138 | 0 | [5 empty] | 680 | 36.4461 | 1
[9 empty] | 681 | 38.5994 | 0 | [5 empty] | 681 | 43.6914 | 0 | [5 empty] | 681 | 35.7149 | 1
[9 empty] | 682 | 36.7055 | 1 | [5 empty] | 682 | 47.56 | 0 | [5 empty] | 682 | 41.1634 | 0
[9 empty] | 683 | 33.3994 | 1 | [5 empty] | 683 | 46.9101 | 0 | [5 empty] | 683 | 35.5601 | 1
[9 empty] | 684 | 36.9106 | 1 | [5 empty] | 684 | 46.3519 | 0 | [5 empty] | 684 | 34.9543 | 1
[9 empty] | 685 | 37.188 | 1 | [5 empty] | 685 | 42.1176 | 0 | [5 empty] | 685 | 36.5559 | 1
[9 empty] | 686 | 38.6381 | 0 | [5 empty] | 686 | 42.0108 | 0 | [5 empty] | 686 | 35.2586 | 1
[9 empty] | 687 | 42.0742 | 0 | [5 empty] | 687 | 46.9087 | 0 | [5 empty] | 687 | 36.5928 | 1
[9 empty] | 688 | 34.9912 | 1 | [5 empty] | 688 | 41.7616 | 0 | [5 empty] | 688 | 40.0578 | 0
[9 empty] | 689 | 37.4937 | 1 | [5 empty] | 689 | 46.0459 | 0 | [5 empty] | 689 | 42.08 | 0
[9 empty] | 690 | 37.0226 | 1 | [5 empty] | 690 | 41.6175 | 0 | [5 empty] | 690 | 37.8923 | 1
[9 empty] | 691 | 41.8413 | 0 | [5 empty] | 691 | 45.9996 | 0 | [5 empty] | 691 | 37.1618 | 1
[9 empty] | 692 | 32.6537 | 1 | [5 empty] | 692 | 48.1829 | 0 | [5 empty] | 692 | 37.4583 | 1
[9 empty] | 693 | 35.369 | 1 | [5 empty] | 693 | 48.0061 | 0 | [5 empty] | 693 | 44.1473 | 0
[9 empty] | 694 | 36.6074 | 1 | [5 empty] | 694 | 48.0126 | 0 | [5 empty] | 694 | 40.7715 | 0
[9 empty] | 695 | 34.825 | 1 | [5 empty] | 695 | 47.5079 | 0 | [5 empty] | 695 | 37.5051 | 1
[9 empty] | 696 | 37.2104 | 1 | [5 empty] | 696 | 37.7549 | 1 | [5 empty] | 696 | 32.6626 | 1
[9 empty] | 697 | 36.517 | 1 | [5 empty] | 697 | 43.0334 | 0 | [5 empty] | 697 | 41.8252 | 0
[9 empty] | 698 | 39.4756 | 0 | [5 empty] | 698 | 49.272 | 0 | [5 empty] | 698 | 36.8085 | 1
[9 empty] | 699 | 37.6388 | 1 | [5 empty] | 699 | 52.8687 | 0 | [5 empty] | 699 | 30.6577 | 1
[9 empty] | 700 | 34.528 | 1 | [5 empty] | 700 | 37.8969 | 1 | [5 empty] | 700 | 38.9783 | 0
[9 empty] | 701 | 42.1635 | 0 | [5 empty] | 701 | 37.5394 | 1 | [5 empty] | 701 | 37.7389 | 1
[9 empty] | 702 | 40.3515 | 0 | [5 empty] | 702 | 46.4775 | 0 | [5 empty] | 702 | 30.6779 | 1
[9 empty] | 703 | 36.2799 | 1 | [5 empty] | 703 | 50.963 | 0 | [5 empty] | 703 | 40.9966 | 0
[9 empty] | 704 | 36.127 | 1 | [5 empty] | 704 | 52.7251 | 0 | [5 empty] | 704 | 35.6011 | 1
[9 empty] | 705 | 35.1838 | 1 | [5 empty] | 705 | 46.3972 | 0 | [5 empty] | 705 | 33.8263 | 1
[9 empty] | 706 | 43.1346 | 0 | [5 empty] | 706 | 45.0078 | 0 | [5 empty] | 706 | 41.7776 | 0
[9 empty] | 707 | 35.4092 | 1 | [5 empty] | 707 | 46.5248 | 0 | [5 empty] | 707 | 39.3388 | 0
[9 empty] | 708 | 41.3302 | 0 | [5 empty] | 708 | 48.258 | 0 | [5 empty] | 708 | 30.8183 | 1
[9 empty] | 709 | 38.9312 | 0 | [5 empty] | 709 | 50.7412 | 0 | [5 empty] | 709 | 40.3089 | 0
[9 empty] | 710 | 37.1978 | 1 | [5 empty] | 710 | 45.8301 | 0 | [5 empty] | 710 | 38.8135 | 0
[9 empty] | 711 | 39.1447 | 0 | [5 empty] | 711 | 48.8853 | 0 | [5 empty] | 711 | 34.6027 | 1
[9 empty] | 712 | 36.3895 | 1 | [5 empty] | 712 | 40.3941 | 0 | [5 empty] | 712 | 33.2289 | 1
[9 empty] | 713 | 41.2156 | 0 | [5 empty] | 713 | 41.0768 | 0 | [5 empty] | 713 | 42.0104 | 0
[9 empty] | 714 | 41.6214 | 0 | [5 empty] | 714 | 42.0086 | 0 | [5 empty] | 714 | 37.1178 | 1
[9 empty] | 715 | 33.7449 | 1 | [5 empty] | 715 | 48.1592 | 0 | [5 empty] | 715 | 37.3487 | 1
[9 empty] | 716 | 37.9147 | 1 | [5 empty] | 716 | 51.6874 | 0 | [5 empty] | 716 | 31.2925 | 1
[9 empty] | 717 | 38.3186 | 0 | [5 empty] | 717 | 52.1604 | 0 | [5 empty] | 717 | 32.7268 | 1
[9 empty] | 718 | 39.5408 | 0 | [5 empty] | 718 | 46.978 | 0 | [5 empty] | 718 | 33.606 | 1
[9 empty] | 719 | 36.5245 | 1 | [5 empty] | 719 | 38.5691 | 0 | [5 empty] | 719 | 41.6961 | 0
[9 empty] | 720 | 34.7511 | 1 | [5 empty] | 720 | 43.0651 | 0 | [5 empty] | 720 | 38.9188 | 0
[9 empty] | 721 | 41.7636 | 0 | [5 empty] | 721 | 46.4493 | 0 | [5 empty] | 721 | 40.8804 | 0
[9 empty] | 722 | 35.0401 | 1 | [5 empty] | 722 | 45.6182 | 0 | [5 empty] | 722 | 39.2962 | 0
[9 empty] | 723 | 36.3049 | 1 | [5 empty] | 723 | 40.775 | 0 | [5 empty] | 723 | 36.6913 | 1
[9 empty] | 724 | 43.4945 | 0 | [5 empty] | 724 | 45.7569 | 0 | [5 empty] | 724 | 34.4391 | 1
[9 empty] | 725 | 40.2071 | 0 | [5 empty] | 725 | 39.6891 | 0 | [5 empty] | 725 | 36.061 | 1
[9 empty] | 726 | 43.0778 | 0 | [5 empty] | 726 | 51.133 | 0 | [5 empty] | 726 | 42.526 | 0
[9 empty] | 727 | 39.0766 | 0 | [5 empty] | 727 | 44.4013 | 0 | [5 empty] | 727 | 30.9776 | 1
[9 empty] | 728 | 37.1432 | 1 | [5 empty] | 728 | 45.8418 | 0 | [5 empty] | 728 | 30.9812 | 1
[9 empty] | 729 | 33.7998 | 1 | [5 empty] | 729 | 46.313 | 0 | [5 empty] | 729 | 33.7039 | 1
[9 empty] | 730 | 37.37 | 1 | [5 empty] | 730 | 42.6409 | 0 | [5 empty] | 730 | 43.2758 | 0
[9 empty] | 731 | 40.1359 | 0 | [5 empty] | 731 | 43.7641 | 0 | [5 empty] | 731 | 37.177 | 1
[9 empty] | 732 | 38.7631 | 0 | [5 empty] | 732 | 46.6429 | 0 | [5 empty] | 732 | 29.2462 | 1
[9 empty] | 733 | 36.7101 | 1 | [5 empty] | 733 | 38.6798 | 0 | [5 empty] | 733 | 31.7623 | 1
[9 empty] | 734 | 39.6652 | 0 | [5 empty] | 734 | 44.391 | 0 | [5 empty] | 734 | 36.5675 | 1
[9 empty] | 735 | 37.9211 | 1 | [5 empty] | 735 | 53.579 | 0 | [5 empty] | 735 | 36.1281 | 1
[9 empty] | 736 | 39.0243 | 0 | [5 empty] | 736 | 42.5469 | 0 | [5 empty] | 736 | 33.7198 | 1
[9 empty] | 737 | 36.8412 | 1 | [5 empty] | 737 | 42.8375 | 0 | [5 empty] | 737 | 33.0496 | 1
[9 empty] | 738 | 39.2182 | 0 | [5 empty] | 738 | 42.1831 | 0 | [5 empty] | 738 | 33.352 | 1
[9 empty] | 739 | 31.4414 | 1 | [5 empty] | 739 | 49.6331 | 0 | [5 empty] | 739 | 43.1666 | 0
[9 empty] | 740 | 36.0598 | 1 | [5 empty] | 740 | 43.8423 | 0 | [5 empty] | 740 | 35.2364 | 1
[9 empty] | 741 | 34.1184 | 1 | [5 empty] | 741 | 45.8237 | 0 | [5 empty] | 741 | 36.8842 | 1
[9 empty] | 742 | 35.0393 | 1 | [5 empty] | 742 | 40.1004 | 0 | [5 empty] | 742 | 31.0668 | 1
[9 empty] | 743 | 33.6482 | 1 | [5 empty] | 743 | 44.7287 | 0 | [5 empty] | 743 | 33.7811 | 1
[9 empty] | 744 | 40.8373 | 0 | [5 empty] | 744 | 46.1072 | 0 | [5 empty] | 744 | 32.4064 | 1
[9 empty] | 745 | 37.5932 | 1 | [5 empty] | 745 | 42.6372 | 0 | [5 empty] | 745 | 34.0919 | 1
[9 empty] | 746 | 43.1348 | 0 | [5 empty] | 746 | 41.9183 | 0 | [5 empty] | 746 | 39.1005 | 0
[9 empty] | 747 | 42.7125 | 0 | [5 empty] | 747 | 47.4628 | 0 | [5 empty] | 747 | 35.3445 | 1
[9 empty] | 748 | 38.2991 | 0 | [5 empty] | 748 | 46.7031 | 0 | [5 empty] | 748 | 39.1783 | 0
[9 empty] | 749 | 35.9141 | 1 | [5 empty] | 749 | 46.943 | 0 | [5 empty] | 749 | 31.8033 | 1
[9 empty] | 750 | 40.3698 | 0 | [5 empty] | 750 | 43.0048 | 0 | [5 empty] | 750 | 37.0496 | 1
[9 empty] | 751 | 40.1426 | 0 | [5 empty] | 751 | 47.5883 | 0 | [5 empty] | 751 | 34.2409 | 1
[9 empty] | 752 | 37.745 | 1 | [5 empty] | 752 | 43.7642 | 0 | [5 empty] | 752 | 42.3897 | 0
[9 empty] | 753 | 34.5507 | 1 | [5 empty] | 753 | 47.0048 | 0 | [5 empty] | 753 | 34.3334 | 1
[9 empty] | 754 | 32.2909 | 1 | [5 empty] | 754 | 45.5303 | 0 | [5 empty] | 754 | 30.5807 | 1
[9 empty] | 755 | 37.663 | 1 | [5 empty] | 755 | 43.1013 | 0 | [5 empty] | 755 | 27.7986 | 1
[9 empty] | 756 | 36.3208 | 1 | [5 empty] | 756 | 36.5349 | 1 | [5 empty] | 756 | 32.7254 | 1
[9 empty] | 757 | 42.3481 | 0 | [5 empty] | 757 | 48.9867 | 0 | [5 empty] | 757 | 41.8741 | 0
[9 empty] | 758 | 34.4256 | 1 | [5 empty] | 758 | 48.2575 | 0 | [5 empty] | 758 | 30.8564 | 1
[9 empty] | 759 | 35.8509 | 1 | [5 empty] | 759 | 48.948 | 0 | [5 empty] | 759 | 39.3112 | 0
[9 empty] | 760 | 41.1439 | 0 | [5 empty] | 760 | 49.2883 | 0 | [5 empty] | 760 | 36.3795 | 1
[9 empty] | 761 | 36.5985 | 1 | [5 empty] | 761 | 39.9924 | 0 | [5 empty] | 761 | 34.516 | 1
[9 empty] | 762 | 36.6285 | 1 | [5 empty] | 762 | 48.1158 | 0 | [5 empty] | 762 | 36.8906 | 1
[9 empty] | 763 | 35.4929 | 1 | [5 empty] | 763 | 45.8863 | 0 | [5 empty] | 763 | 36.9028 | 1
[9 empty] | 764 | 41.4633 | 0 | [5 empty] | 764 | 39.4624 | 0 | [5 empty] | 764 | 35.4621 | 1
[9 empty] | 765 | 40.8028 | 0 | [5 empty] | 765 | 46.4071 | 0 | [5 empty] | 765 | 35.1449 | 1
[9 empty] | 766 | 37.3867 | 1 | [5 empty] | 766 | 46.45 | 0 | [5 empty] | 766 | 31.4404 | 1
[9 empty] | 767 | 41.4381 | 0 | [5 empty] | 767 | 45.4929 | 0 | [5 empty] | 767 | 32.8263 | 1
[9 empty] | 768 | 38.0068 | 0 | [5 empty] | 768 | 45.5054 | 0 | [5 empty] | 768 | 34.9295 | 1
[9 empty] | 769 | 39.0026 | 0 | [5 empty] | 769 | 45.9194 | 0 | [5 empty] | 769 | 37.5158 | 1
[9 empty] | 770 | 42.3823 | 0 | [5 empty] | 770 | 47.8852 | 0 | [5 empty] | 770 | 29.9922 | 1
[9 empty] | 771 | 40.2195 | 0 | [5 empty] | 771 | 44.2637 | 0 | [5 empty] | 771 | 39.6874 | 0
[9 empty] | 772 | 44.4989 | 0 | [5 empty] | 772 | 49.2158 | 0 | [5 empty] | 772 | 35.7882 | 1
[9 empty] | 773 | 46.4215 | 0 | [5 empty] | 773 | 43.7697 | 0 | [5 empty] | 773 | 29.809 | 1
[9 empty] | 774 | 35.9327 | 1 | [5 empty] | 774 | 38.8941 | 0 | [5 empty] | 774 | 30.8383 | 1
[9 empty] | 775 | 40.0272 | 0 | [5 empty] | 775 | 48.8768 | 0 | [5 empty] | 775 | 34.3828 | 1
[9 empty] | 776 | 36.4564 | 1 | [5 empty] | 776 | 48.3135 | 0 | [5 empty] | 776 | 33.5203 | 1
[9 empty] | 777 | 35.227 | 1 | [5 empty] | 777 | 48.4617 | 0 | [5 empty] | 777 | 33.0874 | 1
[9 empty] | 778 | 39.0431 | 0 | [5 empty] | 778 | 46.9877 | 0 | [5 empty] | 778 | 37.9209 | 1
[9 empty] | 779 | 37.4491 | 1 | [5 empty] | 779 | 48.6372 | 0 | [5 empty] | 779 | 36.0149 | 1
[9 empty] | 780 | 42.8222 | 0 | [5 empty] | 780 | 39.6647 | 0 | [5 empty] | 780 | 38.9611 | 0
[9 empty] | 781 | 36.45 | 1 | [5 empty] | 781 | 54.0356 | 0 | [5 empty] | 781 | 35.0778 | 1
[9 empty] | 782 | 38.2559 | 0 | [5 empty] | 782 | 51.4487 | 0 | [5 empty] | 782 | 42.6459 | 0
[9 empty] | 783 | 39.7339 | 0 | [5 empty] | 783 | 44.7874 | 0 | [5 empty] | 783 | 40.6012 | 0
[9 empty] | 784 | 36.6426 | 1 | [5 empty] | 784 | 45.6327 | 0 | [5 empty] | 784 | 37.6817 | 1
[9 empty] | 785 | 36.5753 | 1 | [5 empty] | 785 | 46.2129 | 0 | [5 empty] | 785 | 37.0028 | 1
[9 empty] | 786 | 39.5546 | 0 | [5 empty] | 786 | 49.8548 | 0 | [5 empty] | 786 | 42.8259 | 0
[9 empty] | 787 | 32.4849 | 1 | [5 empty] | 787 | 46.499 | 0 | [5 empty] | 787 | 33.9793 | 1
[9 empty] | 788 | 41.3032 | 0 | [5 empty] | 788 | 50.4837 | 0 | [5 empty] | 788 | 32.7961 | 1
[9 empty] | 789 | 31.7543 | 1 | [5 empty] | 789 | 49.3537 | 0 | [5 empty] | 789 | 43.8086 | 0
[9 empty] | 790 | 36.9336 | 1 | [5 empty] | 790 | 41.3443 | 0 | [5 empty] | 790 | 32.1916 | 1
[9 empty] | 791 | 38.8854 | 0 | [5 empty] | 791 | 43.885 | 0 | [5 empty] | 791 | 38.851 | 0
[9 empty] | 792 | 36.551 | 1 | [5 empty] | 792 | 41.2847 | 0 | [5 empty] | 792 | 36.6061 | 1
[9 empty] | 793 | 40.6979 | 0 | [5 empty] | 793 | 46.4953 | 0 | [5 empty] | 793 | 30.7244 | 1
[9 empty] | 794 | 30.5763 | 1 | [5 empty] | 794 | 48.2987 | 0 | [5 empty] | 794 | 30.3128 | 1
[9 empty] | 795 | 37.3566 | 1 | [5 empty] | 795 | 44.6048 | 0 | [5 empty] | 795 | 34.6744 | 1
[9 empty] | 796 | 34.6727 | 1 | [5 empty] | 796 | 46.4451 | 0 | [5 empty] | 796 | 30.4651 | 1
[9 empty] | 797 | 31.8057 | 1 | [5 empty] | 797 | 46.8459 | 0 | [5 empty] | 797 | 36.8979 | 1
[9 empty] | 798 | 41.9061 | 0 | [5 empty] | 798 | 46.8894 | 0 | [5 empty] | 798 | 37.7529 | 1
[9 empty] | 799 | 32.9662 | 1 | [5 empty] | 799 | 40.0347 | 0 | [5 empty] | 799 | 30.8897 | 1
[9 empty] | 800 | 34.0438 | 1 | [5 empty] | 800 | 44.6211 | 0 | [5 empty] | 800 | 34.8434 | 1
[9 empty] | 801 | 37.4886 | 1 | [5 empty] | 801 | 48.8195 | 0 | [5 empty] | 801 | 28.2281 | 1
[9 empty] | 802 | 35.0663 | 1 | [5 empty] | 802 | 39.545 | 0 | [5 empty] | 802 | 35.5479 | 1
[9 empty] | 803 | 40.4598 | 0 | [5 empty] | 803 | 42.3354 | 0 | [5 empty] | 803 | 35.8857 | 1
[9 empty] | 804 | 35.2589 | 1 | [5 empty] | 804 | 51.8781 | 0 | [5 empty] | 804 | 33.2459 | 1
[9 empty] | 805 | 40.6473 | 0 | [5 empty] | 805 | 43.3102 | 0 | [5 empty] | 805 | 40.2649 | 0
[9 empty] | 806 | 34.2311 | 1 | [5 empty] | 806 | 46.9668 | 0 | [5 empty] | 806 | 35.0615 | 1
[9 empty] | 807 | 37.3134 | 1 | [5 empty] | 807 | 42.977 | 0 | [5 empty] | 807 | 39.3671 | 0
[9 empty] | 808 | 33.0409 | 1 | [5 empty] | 808 | 46.9828 | 0 | [5 empty] | 808 | 35.0252 | 1
[9 empty] | 809 | 38.4419 | 0 | [5 empty] | 809 | 38.3498 | 0 | [5 empty] | 809 | 35.591 | 1
[9 empty] | 810 | 41.8601 | 0 | [5 empty] | 810 | 45.3727 | 0 | [5 empty] | 810 | 41.9119 | 0
[9 empty] | 811 | 35.8041 | 1 | [5 empty] | 811 | 47.6443 | 0 | [5 empty] | 811 | 34.71 | 1
[9 empty] | 812 | 40.0565 | 0 | [5 empty] | 812 | 41.4911 | 0 | [5 empty] | 812 | 35.5814 | 1
[9 empty] | 813 | 40.9671 | 0 | [5 empty] | 813 | 48.9868 | 0 | [5 empty] | 813 | 34.6089 | 1
[9 empty] | 814 | 43.4359 | 0 | [5 empty] | 814 | 41.3209 | 0 | [5 empty] | 814 | 33.7842 | 1
[9 empty] | 815 | 39.4575 | 0 | [5 empty] | 815 | 46.2678 | 0 | [5 empty] | 815 | 30.2651 | 1
[9 empty] | 816 | 33.3546 | 1 | [5 empty] | 816 | 38.1746 | 0 | [5 empty] | 816 | 37.4432 | 1
[9 empty] | 817 | 34.072 | 1 | [5 empty] | 817 | 48.3066 | 0 | [5 empty] | 817 | 34.5329 | 1
[9 empty] | 818 | 40.4931 | 0 | [5 empty] | 818 | 41.9241 | 0 | [5 empty] | 818 | 34.2238 | 1
[9 empty] | 819 | 39.6706 | 0 | [5 empty] | 819 | 42.757 | 0 | [5 empty] | 819 | 30.0799 | 1
[9 empty] | 820 | 34.2555 | 1 | [5 empty] | 820 | 48.165 | 0 | [5 empty] | 820 | 35.075 | 1
[9 empty] | 821 | 37.2505 | 1 | [5 empty] | 821 | 43.0842 | 0 | [5 empty] | 821 | 32.7965 | 1
[9 empty] | 822 | 30.4661 | 1 | [5 empty] | 822 | 47.4167 | 0 | [5 empty] | 822 | 39.8167 | 0
[9 empty] | 823 | 39.7732 | 0 | [5 empty] | 823 | 47.7432 | 0 | [5 empty] | 823 | 33.8755 | 1
[9 empty] | 824 | 37.3103 | 1 | [5 empty] | 824 | 42.591 | 0 | [5 empty] | 824 | 39.8348 | 0
[9 empty] | 825 | 41.8334 | 0 | [5 empty] | 825 | 40.437 | 0 | [5 empty] | 825 | 33.1024 | 1
[9 empty] | 826 | 42.7108 | 0 | [5 empty] | 826 | 39.8761 | 0 | [5 empty] | 826 | 32.1148 | 1
[9 empty] | 827 | 42.3144 | 0 | [5 empty] | 827 | 44.396 | 0 | [5 empty] | 827 | 35.8052 | 1
[9 empty] | 828 | 44.7319 | 0 | [5 empty] | 828 | 47.4998 | 0 | [5 empty] | 828 | 35.868 | 1
[9 empty] | 829 | 47.4143 | 0 | [5 empty] | 829 | 41.7976 | 0 | [5 empty] | 829 | 30.4734 | 1
[9 empty] | 830 | 33.377 | 1 | [5 empty] | 830 | 46.6666 | 0 | [5 empty] | 830 | 36.6573 | 1
[9 empty] | 831 | 41.4738 | 0 | [5 empty] | 831 | 48.5777 | 0 | [5 empty] | 831 | 38.9655 | 0
[9 empty] | 832 | 39.1516 | 0 | [5 empty] | 832 | 48.6729 | 0 | [5 empty] | 832 | 39.4358 | 0
[9 empty] | 833 | 40.6746 | 0 | [5 empty] | 833 | 46.6937 | 0 | [5 empty] | 833 | 40.0717 | 0
[9 empty] | 834 | 33.2645 | 1 | [5 empty] | 834 | 45.482 | 0 | [5 empty] | 834 | 33.8225 | 1
[9 empty] | 835 | 39.8565 | 0 | [5 empty] | 835 | 43.0439 | 0 | [5 empty] | 835 | 39.9571 | 0
[9 empty] | 836 | 34.012 | 1 | [5 empty] | 836 | 38.1316 | 0 | [5 empty] | 836 | 31.8276 | 1
[9 empty] | 837 | 34.0428 | 1 | [5 empty] | 837 | 48.2258 | 0 | [5 empty] | 837 | 38.5265 | 0
[9 empty] | 838 | 31.9843 | 1 | [5 empty] | 838 | 49.4065 | 0 | [5 empty] | 838 | 39.4753 | 0
[9 empty] | 839 | 43.9547 | 0 | [5 empty] | 839 | 50.5268 | 0 | [5 empty] | 839 | 36.6998 | 1
[9 empty] | 840 | 42.8345 | 0 | [5 empty] | 840 | 42.9968 | 0 | [5 empty] | 840 | 35.1151 | 1
[9 empty] | 841 | 34.6427 | 1 | [5 empty] | 841 | 48.9243 | 0 | [5 empty] | 841 | 35.7376 | 1
[9 empty] | 842 | 41.3921 | 0 | [5 empty] | 842 | 47.2289 | 0 | [5 empty] | 842 | 40.8539 | 0
[9 empty] | 843 | 39.9365 | 0 | [5 empty] | 843 | 46.2892 | 0 | [5 empty] | 843 | 32.6571 | 1
[9 empty] | 844 | 36.8357 | 1 | [5 empty] | 844 | 43.6154 | 0 | [5 empty] | 844 | 29.8578 | 1
[9 empty] | 845 | 39.2753 | 0 | [5 empty] | 845 | 50.5283 | 0 | [5 empty] | 845 | 37.8104 | 1
[9 empty] | 846 | 37.876 | 1 | [5 empty] | 846 | 45.7585 | 0 | [5 empty] | 846 | 32.9182 | 1
[9 empty] | 847 | 36.359 | 1 | [5 empty] | 847 | 40.8283 | 0 | [5 empty] | 847 | 34.2477 | 1
[9 empty] | 848 | 36.9829 | 1 | [5 empty] | 848 | 52.474 | 0 | [5 empty] | 848 | 42.982 | 0
[9 empty] | 849 | 35.9248 | 1 | [5 empty] | 849 | 50.2553 | 0 | [5 empty] | 849 | 31.0014 | 1
[9 empty] | 850 | 35.2572 | 1 | [5 empty] | 850 | 50.6049 | 0 | [5 empty] | 850 | 33.0839 | 1
[9 empty] | 851 | 39.0505 | 0 | [5 empty] | 851 | 47.8151 | 0 | [5 empty] | 851 | 36.5109 | 1
[9 empty] | 852 | 33.9291 | 1 | [5 empty] | 852 | 41.2733 | 0 | [5 empty] | 852 | 32.4847 | 1
[9 empty] | 853 | 36.8021 | 1 | [5 empty] | 853 | 39.5476 | 0 | [5 empty] | 853 | 40.8903 | 0
[9 empty] | 854 | 37.7309 | 1 | [5 empty] | 854 | 49.3193 | 0 | [5 empty] | 854 | 39.511 | 0
[9 empty] | 855 | 43.8426 | 0 | [5 empty] | 855 | 47.4232 | 0 | [5 empty] | 855 | 35.8875 | 1
[9 empty] | 856 | 37.6062 | 1 | [5 empty] | 856 | 52.3187 | 0 | [5 empty] | 856 | 38.1915 | 0
[9 empty] | 857 | 38.3144 | 0 | [5 empty] | 857 | 45.908 | 0 | [5 empty] | 857 | 34.1256 | 1
[9 empty] | 858 | 36.9365 | 1 | [5 empty] | 858 | 46.3249 | 0 | [5 empty] | 858 | 31.5486 | 1
[9 empty] | 859 | 42.5953 | 0 | [5 empty] | 859 | 48.78 | 0 | [5 empty] | 859 | 39.2464 | 0
[9 empty] | 860 | 39.3674 | 0 | [5 empty] | 860 | 46.1094 | 0 | [5 empty] | 860 | 40.5875 | 0
[9 empty] | 861 | 43.8838 | 0 | [5 empty] | 861 | 49.8902 | 0 | [5 empty] | 861 | 31.4995 | 1
[9 empty] | 862 | 35.6687 | 1 | [5 empty] | 862 | 47.5804 | 0 | [5 empty] | 862 | 38.0509 | 0
[9 empty] | 863 | 49.0896 | 0 | [5 empty] | 863 | 46.2384 | 0 | [5 empty] | 863 | 45.5825 | 0
[9 empty] | 864 | 34.0421 | 1 | [5 empty] | 864 | 42.2801 | 0 | [5 empty] | 864 | 33.1308 | 1
[9 empty] | 865 | 42.548 | 0 | [5 empty] | 865 | 47.9042 | 0 | [5 empty] | 865 | 34.3834 | 1
[9 empty] | 866 | 37.1164 | 1 | [5 empty] | 866 | 45.0685 | 0 | [5 empty] | 866 | 41.5641 | 0
[9 empty] | 867 | 38.1924 | 0 | [5 empty] | 867 | 44.2886 | 0 | [5 empty] | 867 | 28.6328 | 1
[9 empty] | 868 | 37.2726 | 1 | [5 empty] | 868 | 48.4404 | 0 | [5 empty] | 868 | 38.1214 | 0
[9 empty] | 869 | 39.945 | 0 | [5 empty] | 869 | 44.5241 | 0 | [5 empty] | 869 | 41.4971 | 0
[9 empty] | 870 | 42.3307 | 0 | [5 empty] | 870 | 49.6313 | 0 | [5 empty] | 870 | 32.6267 | 1
[9 empty] | 871 | 40.5757 | 0 | [5 empty] | 871 | 43.1837 | 0 | [5 empty] | 871 | 31.4702 | 1
[9 empty] | 872 | 37.6824 | 1 | [5 empty] | 872 | 48.9 | 0 | [5 empty] | 872 | 33.263 | 1
[9 empty] | 873 | 35.5249 | 1 | [5 empty] | 873 | 43.0019 | 0 | [5 empty] | 873 | 33.6611 | 1
[9 empty] | 874 | 41.694 | 0 | [5 empty] | 874 | 42.1363 | 0 | [5 empty] | 874 | 43.1923 | 0
[9 empty] | 875 | 40.095 | 0 | [5 empty] | 875 | 44.9029 | 0 | [5 empty] | 875 | 41.5387 | 0
[9 empty] | 876 | 34.4653 | 1 | [5 empty] | 876 | 48.2041 | 0 | [5 empty] | 876 | 37.1147 | 1
[9 empty] | 877 | 36.9125 | 1 | [5 empty] | 877 | 43.1048 | 0 | [5 empty] | 877 | 32.8028 | 1
[9 empty] | 878 | 34.8927 | 1 | [5 empty] | 878 | 45.8143 | 0 | [5 empty] | 878 | 35.9845 | 1
[9 empty] | 879 | 40.9599 | 0 | [5 empty] | 879 | 47.0212 | 0 | [5 empty] | 879 | 37.1311 | 1
[9 empty] | 880 | 38.6691 | 0 | [5 empty] | 880 | 51.1519 | 0 | [5 empty] | 880 | 38.8919 | 0
[9 empty] | 881 | 36.2941 | 1 | [5 empty] | 881 | 47.3324 | 0 | [5 empty] | 881 | 40.4495 | 0
[9 empty] | 882 | 40.073 | 0 | [5 empty] | 882 | 48.1796 | 0 | [5 empty] | 882 | 32.746 | 1
[9 empty] | 883 | 30.7698 | 1 | [5 empty] | 883 | 41.3817 | 0 | [5 empty] | 883 | 37.7339 | 1
[9 empty] | 884 | 40.9042 | 0 | [5 empty] | 884 | 47.7174 | 0 | [5 empty] | 884 | 36.0687 | 1
[9 empty] | 885 | 35.1129 | 1 | [5 empty] | 885 | 42.9712 | 0 | [5 empty] | 885 | 37.7176 | 1
[9 empty] | 886 | 33.6584 | 1 | [5 empty] | 886 | 50.9796 | 0 | [5 empty] | 886 | 43.1077 | 0
[9 empty] | 887 | 38.6739 | 0 | [5 empty] | 887 | 43.2975 | 0 | [5 empty] | 887 | 36.2678 | 1
[9 empty] | 888 | 38.0781 | 0 | [5 empty] | 888 | 41.5394 | 0 | [5 empty] | 888 | 34.2265 | 1
[9 empty] | 889 | 34.9693 | 1 | [5 empty] | 889 | 43.5227 | 0 | [5 empty] | 889 | 29.1834 | 1
[9 empty] | 890 | 37.6495 | 1 | [5 empty] | 890 | 47.3813 | 0 | [5 empty] | 890 | 40.235 | 0
[9 empty] | 891 | 32.6263 | 1 | [5 empty] | 891 | 42.7775 | 0 | [5 empty] | 891 | 34.7975 | 1
[9 empty] | 892 | 37.6211 | 1 | [5 empty] | 892 | 37.2005 | 1 | [5 empty] | 892 | 33.2736 | 1
[9 empty] | 893 | 40.2674 | 0 | [5 empty] | 893 | 42.4568 | 0 | [5 empty] | 893 | 36.5546 | 1
[9 empty] | 894 | 38.0078 | 0 | [5 empty] | 894 | 49.9524 | 0 | [5 empty] | 894 | 42.9723 | 0
[9 empty] | 895 | 38.1558 | 0 | [5 empty] | 895 | 47.3009 | 0 | [5 empty] | 895 | 37.6393 | 1
[9 empty] | 896 | 34.6323 | 1 | [5 empty] | 896 | 47.2431 | 0 | [5 empty] | 896 | 32.256 | 1
[9 empty] | 897 | 40.5079 | 0 | [5 empty] | 897 | 48.9538 | 0 | [5 empty] | 897 | 34.9282 | 1
[9 empty] | 898 | 39.826 | 0 | [5 empty] | 898 | 44.3502 | 0 | [5 empty] | 898 | 39.2926 | 0
[9 empty] | 899 | 38.8624 | 0 | [5 empty] | 899 | 41.2483 | 0 | [5 empty] | 899 | 29.6191 | 1
[9 empty] | 900 | 34.8594 | 1 | [5 empty] | 900 | 47.685 | 0 | [5 empty] | 900 | 45.7232 | 0
[9 empty] | 901 | 43.8226 | 0 | [5 empty] | 901 | 48.4411 | 0 | [5 empty] | 901 | 31.0431 | 1
[9 empty] | 902 | 36.6081 | 1 | [5 empty] | 902 | 47.2778 | 0 | [5 empty] | 902 | 32.9213 | 1
[9 empty] | 903 | 36.1708 | 1 | [5 empty] | 903 | 52.6856 | 0 | [5 empty] | 903 | 35.0192 | 1
[9 empty] | 904 | 36.3287 | 1 | [5 empty] | 904 | 48.0612 | 0 | [5 empty] | 904 | 35.7132 | 1
[9 empty] | 905 | 37.8626 | 1 | [5 empty] | 905 | 46.2821 | 0 | [5 empty] | 905 | 37.4596 | 1
[9 empty] | 906 | 38.0701 | 0 | [5 empty] | 906 | 51.1223 | 0 | [5 empty] | 906 | 41.9407 | 0
[9 empty] | 907 | 36.5123 | 1 | [5 empty] | 907 | 44.2097 | 0 | [5 empty] | 907 | 30.5487 | 1
[9 empty] | 908 | 38.2629 | 0 | [5 empty] | 908 | 48.0063 | 0 | [5 empty] | 908 | 32.4905 | 1
[9 empty] | 909 | 39.7437 | 0 | [5 empty] | 909 | 47.9069 | 0 | [5 empty] | 909 | 34.1502 | 1
[9 empty] | 910 | 38.0631 | 0 | [5 empty] | 910 | 40.5225 | 0 | [5 empty] | 910 | 38.7767 | 0
[9 empty] | 911 | 41.7347 | 0 | [5 empty] | 911 | 47.5551 | 0 | [5 empty] | 911 | 31.21 | 1
[9 empty] | 912 | 40.8597 | 0 | [5 empty] | 912 | 47.0941 | 0 | [5 empty] | 912 | 38.0324 | 0
[9 empty] | 913 | 42.5994 | 0 | [5 empty] | 913 | 38.3993 | 0 | [5 empty] | 913 | 31.0435 | 1
[9 empty] | 914 | 33.3821 | 1 | [5 empty] | 914 | 45.0892 | 0 | [5 empty] | 914 | 41.4631 | 0
[9 empty] | 915 | 31.3533 | 1 | [5 empty] | 915 | 46.0584 | 0 | [5 empty] | 915 | 31.3193 | 1
[9 empty] | 916 | 39.1904 | 0 | [5 empty] | 916 | 51.5426 | 0 | [5 empty] | 916 | 35.7889 | 1
[9 empty] | 917 | 35.6663 | 1 | [5 empty] | 917 | 46.0487 | 0 | [5 empty] | 917 | 34.9765 | 1
[9 empty] | 918 | 38.0095 | 0 | [5 empty] | 918 | 43.9236 | 0 | [5 empty] | 918 | 39.0431 | 0
[9 empty] | 919 | 32.3811 | 1 | [5 empty] | 919 | 51.5537 | 0 | [5 empty] | 919 | 38.3703 | 0
[9 empty] | 920 | 30.3748 | 1 | [5 empty] | 920 | 42.3528 | 0 | [5 empty] | 920 | 32.2812 | 1
[9 empty] | 921 | 39.4674 | 0 | [5 empty] | 921 | 44.1933 | 0 | [5 empty] | 921 | 39.6019 | 0
[9 empty] | 922 | 47.1354 | 0 | [5 empty] | 922 | 52.8715 | 0 | [5 empty] | 922 | 37.8215 | 1
[9 empty] | 923 | 33.4971 | 1 | [5 empty] | 923 | 46.2209 | 0 | [5 empty] | 923 | 33.9144 | 1
[9 empty] | 924 | 41.4048 | 0 | [5 empty] | 924 | 40.9696 | 0 | [5 empty] | 924 | 39.8882 | 0
[9 empty] | 925 | 39.8277 | 0 | [5 empty] | 925 | 45.7832 | 0 | [5 empty] | 925 | 30.9578 | 1
[9 empty] | 926 | 34.2003 | 1 | [5 empty] | 926 | 44.0078 | 0 | [5 empty] | 926 | 36.4245 | 1
[9 empty] | 927 | 39.5036 | 0 | [5 empty] | 927 | 47.4295 | 0 | [5 empty] | 927 | 36.0801 | 1
[9 empty] | 928 | 40.3942 | 0 | [5 empty] | 928 | 45.8614 | 0 | [5 empty] | 928 | 38.084 | 0
[9 empty] | 929 | 36.6405 | 1 | [5 empty] | 929 | 46.5279 | 0 | [5 empty] | 929 | 36.4213 | 1
[9 empty] | 930 | 35.2406 | 1 | [5 empty] | 930 | 45.627 | 0 | [5 empty] | 930 | 36.6538 | 1
[9 empty] | 931 | 41.9372 | 0 | [5 empty] | 931 | 46.2237 | 0 | [5 empty] | 931 | 32.3484 | 1
[9 empty] | 932 | 40.3059 | 0 | [5 empty] | 932 | 43.2908 | 0 | [5 empty] | 932 | 39.7682 | 0
[9 empty] | 933 | 38.0549 | 0 | [5 empty] | 933 | 50.5119 | 0 | [5 empty] | 933 | 45.1381 | 0
[9 empty] | 934 | 36.323 | 1 | [5 empty] | 934 | 48.812 | 0 | [5 empty] | 934 | 37.5894 | 1
[9 empty] | 935 | 42.9502 | 0 | [5 empty] | 935 | 44.6768 | 0 | [5 empty] | 935 | 35.8827 | 1
[9 empty] | 936 | 35.5305 | 1 | [5 empty] | 936 | 40.4798 | 0 | [5 empty] | 936 | 31.4285 | 1
[9 empty] | 937 | 34.9981 | 1 | [5 empty] | 937 | 44.823 | 0 | [5 empty] | 937 | 39.1855 | 0
[9 empty] | 938 | 39.0938 | 0 | [5 empty] | 938 | 46.3091 | 0 | [5 empty] | 938 | 31.5231 | 1
[9 empty] | 939 | 35.8739 | 1 | [5 empty] | 939 | 40.7192 | 0 | [5 empty] | 939 | 35.4257 | 1
[9 empty] | 940 | 37.7726 | 1 | [5 empty] | 940 | 44.4932 | 0 | [5 empty] | 940 | 32.8803 | 1
[9 empty] | 941 | 39.8898 | 0 | [5 empty] | 941 | 46.6334 | 0 | [5 empty] | 941 | 34.7965 | 1
[9 empty] | 942 | 36.1553 | 1 | [5 empty] | 942 | 50.8672 | 0 | [5 empty] | 942 | 40.4938 | 0
[9 empty] | 943 | 42.3674 | 0 | [5 empty] | 943 | 50.6144 | 0 | [5 empty] | 943 | 38.7794 | 0
[9 empty] | 944 | 43.4983 | 0 | [5 empty] | 944 | 44.986 | 0 | [5 empty] | 944 | 29.4656 | 1
[9 empty] | 945 | 39.046 | 0 | [5 empty] | 945 | 45.853 | 0 | [5 empty] | 945 | 40.3661 | 0
[9 empty] | 946 | 39.526 | 0 | [5 empty] | 946 | 43.176 | 0 | [5 empty] | 946 | 39.6974 | 0
[9 empty] | 947 | 38.8528 | 0 | [5 empty] | 947 | 47.1514 | 0 | [5 empty] | 947 | 42.1695 | 0
[9 empty] | 948 | 42.3961 | 0 | [5 empty] | 948 | 37.4318 | 1 | [5 empty] | 948 | 34.9643 | 1
[9 empty] | 949 | 35.411 | 1 | [5 empty] | 949 | 42.8189 | 0 | [5 empty] | 949 | 35.6547 | 1
[9 empty] | 950 | 37.4932 | 1 | [5 empty] | 950 | 48.6919 | 0 | [5 empty] | 950 | 39.424 | 0
[9 empty] | 951 | 45.7681 | 0 | [5 empty] | 951 | 44.4896 | 0 | [5 empty] | 951 | 37.4457 | 1
[9 empty] | 952 | 43.1167 | 0 | [5 empty] | 952 | 45.4766 | 0 | [5 empty] | 952 | 38.3102 | 0
[9 empty] | 953 | 34.8377 | 1 | [5 empty] | 953 | 45.5931 | 0 | [5 empty] | 953 | 35.9405 | 1
[9 empty] | 954 | 40.6252 | 0 | [5 empty] | 954 | 41.6772 | 0 | [5 empty] | 954 | 39.4095 | 0
[9 empty] | 955 | 38.5604 | 0 | [5 empty] | 955 | 44.2972 | 0 | [5 empty] | 955 | 34.8389 | 1
[9 empty] | 956 | 40.705 | 0 | [5 empty] | 956 | 45.8581 | 0 | [5 empty] | 956 | 33.6576 | 1
[9 empty] | 957 | 34.7977 | 1 | [5 empty] | 957 | 41.5463 | 0 | [5 empty] | 957 | 31.3572 | 1
[9 empty] | 958 | 39.2326 | 0 | [5 empty] | 958 | 44.0591 | 0 | [5 empty] | 958 | 36.9 | 1
[9 empty] | 959 | 37.3586 | 1 | [5 empty] | 959 | 42.9214 | 0 | [5 empty] | 959 | 34.9488 | 1
[9 empty] | 960 | 41.237 | 0 | [5 empty] | 960 | 47.9675 | 0 | [5 empty] | 960 | 36.6095 | 1
[9 empty] | 961 | 38.775 | 0 | [5 empty] | 961 | 42.8438 | 0 | [5 empty] | 961 | 37.2745 | 1
[9 empty] | 962 | 39.9198 | 0 | [5 empty] | 962 | 46.3712 | 0 | [5 empty] | 962 | 28.0959 | 1
[9 empty] | 963 | 33.6529 | 1 | [5 empty] | 963 | 45.9797 | 0 | [5 empty] | 963 | 37.7744 | 1
[9 empty] | 964 | 35.6094 | 1 | [5 empty] | 964 | 49.5125 | 0 | [5 empty] | 964 | 36.0109 | 1
[9 empty] | 965 | 35.4935 | 1 | [5 empty] | 965 | 49.5522 | 0 | [5 empty] | 965 | 27.6855 | 1
[9 empty] | 966 | 35.6051 | 1 | [5 empty] | 966 | 44.9515 | 0 | [5 empty] | 966 | 37.6656 | 1
[9 empty] | 967 | 35.9001 | 1 | [5 empty] | 967 | 42.4324 | 0 | [5 empty] | 967 | 32.9254 | 1
[9 empty] | 968 | 35.2974 | 1 | [5 empty] | 968 | 49.9873 | 0 | [5 empty] | 968 | 35.784 | 1
[9 empty] | 969 | 36.0131 | 1 | [5 empty] | 969 | 51.0452 | 0 | [5 empty] | 969 | 30.2161 | 1
[9 empty] | 970 | 32.5511 | 1 | [5 empty] | 970 | 43.1698 | 0 | [5 empty] | 970 | 39.3283 | 0
[9 empty] | 971 | 39.8644 | 0 | [5 empty] | 971 | 38.9581 | 0 | [5 empty] | 971 | 41.2473 | 0
[9 empty] | 972 | 38.4138 | 0 | [5 empty] | 972 | 42.2414 | 0 | [5 empty] | 972 | 37.3886 | 1
[9 empty] | 973 | 36.9216 | 1 | [5 empty] | 973 | 50.2975 | 0 | [5 empty] | 973 | 34.9142 | 1
[9 empty] | 974 | 40.2224 | 0 | [5 empty] | 974 | 48.4155 | 0 | [5 empty] | 974 | 37.0719 | 1
[9 empty] | 975 | 38.6331 | 0 | [5 empty] | 975 | 40.7034 | 0 | [5 empty] | 975 | 35.0767 | 1
[9 empty] | 976 | 42.0555 | 0 | [5 empty] | 976 | 42.9352 | 0 | [5 empty] | 976 | 34.6185 | 1
[9 empty] | 977 | 42.1707 | 0 | [5 empty] | 977 | 47.6313 | 0 | [5 empty] | 977 | 43.6052 | 0
[9 empty] | 978 | 41.3285 | 0 | [5 empty] | 978 | 50.1907 | 0 | [5 empty] | 978 | 36.5837 | 1
[9 empty] | 979 | 39.6824 | 0 | [5 empty] | 979 | 38.6504 | 0 | [5 empty] | 979 | 35.3325 | 1
[9 empty] | 980 | 35.6656 | 1 | [5 empty] | 980 | 46.9871 | 0 | [5 empty] | 980 | 35.3765 | 1
[9 empty] | 981 | 38.7443 | 0 | [5 empty] | 981 | 46.4498 | 0 | [5 empty] | 981 | 36.1817 | 1
[9 empty] | 982 | 40.9079 | 0 | [5 empty] | 982 | 47.1388 | 0 | [5 empty] | 982 | 37.3571 | 1
[9 empty] | 983 | 34.2838 | 1 | [5 empty] | 983 | 37.7024 | 1 | [5 empty] | 983 | 38.5329 | 0
[9 empty] | 984 | 43.6896 | 0 | [5 empty] | 984 | 41.1589 | 0 | [5 empty] | 984 | 30.8124 | 1
[9 empty] | 985 | 32.8953 | 1 | [5 empty] | 985 | 39.0991 | 0 | [5 empty] | 985 | 34.4779 | 1
[9 empty] | 986 | 40.9669 | 0 | [5 empty] | 986 | 47.8004 | 0 | [5 empty] | 986 | 39.0935 | 0
[9 empty] | 987 | 42.4506 | 0 | [5 empty] | 987 | 43.957 | 0 | [5 empty] | 987 | 30.0885 | 1
[9 empty] | 988 | 37.1403 | 1 | [5 empty] | 988 | 47.7214 | 0 | [5 empty] | 988 | 34.6952 | 1
[9 empty] | 989 | 38.3929 | 0 | [5 empty] | 989 | 39.8143 | 0 | [5 empty] | 989 | 38.3545 | 0
[9 empty] | 990 | 44.9241 | 0 | [5 empty] | 990 | 48.7137 | 0 | [5 empty] | 990 | 31.3939 | 1
[9 empty] | 991 | 37.887 | 1 | [5 empty] | 991 | 43.9365 | 0 | [5 empty] | 991 | 35.2126 | 1
[9 empty] | 992 | 33.3188 | 1 | [5 empty] | 992 | 41.2083 | 0 | [5 empty] | 992 | 37.8248 | 1
[9 empty] | 993 | 41.3525 | 0 | [5 empty] | 993 | 45.8426 | 0 | [5 empty] | 993 | 39.6536 | 0
[9 empty] | 994 | 40.9642 | 0 | [5 empty] | 994 | 40.1193 | 0 | [5 empty] | 994 | 40.5533 | 0
[9 empty] | 995 | 37.3047 | 1 | [5 empty] | 995 | 45.809 | 0 | [5 empty] | 995 | 32.9609 | 1
[9 empty] | 996 | 32.069 | 1 | [5 empty] | 996 | 47.6034 | 0 | [5 empty] | 996 | 31.369 | 1
[9 empty] | 997 | 37.0654 | 1 | [5 empty] | 997 | 38.8952 | 0 | [5 empty] | 997 | 38.1684 | 0
[9 empty] | 998 | 38.1704 | 0 | [5 empty] | 998 | 49.5612 | 0 | [5 empty] | 998 | 33.6314 | 1
[9 empty] | 999 | 41.3851 | 0 | [5 empty] | 999 | 49.109 | 0 | [5 empty] | 999 | 35.0668 | 1
[9 empty] | 1000 | 39.5129 | 0 | [5 empty] | 1000 | 47.8098 | 0 | [5 empty] | 1000 | 39.4076 | 0